## Sheet1
Task Number |  | Project Manager Hourly Billable Rate | Hours | Cost | Project Engineer: Hydrologist Hourly Billable Rate | Hours | Cost | Engineer In Training Hourly Billable Rate | Hours | Cost | Engineering Technician: Surveyor Hourly Billable Rate | Hours | Cost | Administrative Hourly Billing Rate | Hours | Cost
1 | Project Management
1.1 | Coordination | 82.6558 | 3 | 247.9674 |  |  |  | 52.5053 | 3 | 157.516 |  |  |  | 46.3372 | 4 | 185.3488
1.2 | Team Meetings | 82.6558 | 60 | 4959.3486 | 67.6654 | 50 | 3383.2692 | 52.5053 | 60 | 3150.3198 | 47.6965 | 32 | 1526.2882
1.3 | Client/Advisor Meetings | 82.6558 | 5 | 413.279 | 67.6654 | 5 | 338.3269 | 52.5053 | 5 | 262.5267 | 47.6965 | 5 | 238.4825
2 | Data Collection
2.1 | Site Visits | 82.6558 | 4 | 330.6232 | 67.6654 | 4 | 270.6615 | 52.5053 | 4 | 210.0213 | 47.6965 | 4 | 190.786
2.2 | Research: Sinclair Wash Historical Data | 82.6558 | 4 | 330.6232 | 67.6654 | 4 | 270.6615 | 52.5053 | 8 | 420.0426
2.5 | Site Inventory |  |  |  | 67.6654 | 4 | 270.6615 | 52.5053 | 7 | 367.5373
2.6 | Surveying: Natural Channel | 82.6558 | 10 | 826.5581 | 67.6654 | 10 | 676.6538 | 52.5053 | 10 | 525.0533 | 47.6965 | 7 | 333.8755
2.7 | Surveying: Culverts | 82.6558 | 10 | 826.5581 | 67.6654 | 14 | 947.3154 | 52.5053 | 10 | 525.0533
3 | Hydrologic Analysis
3.1 | Watershed Deliniation | 82.6558 | 20 | 1653.1162 | 67.6654 | 5 | 338.3269
3.2 | Modeling | 82.6558 | 60 | 4959.3486
4 | Soil Analysis
4.1 | Sediment Testing | 82.6558 | 5 | 413.279 | 67.6654 | 8 | 541.3231 | 52.5053 | 5 | 262.5267 | 47.6965 | 5 | 238.4825
5 | Hydraulic Analysis
5.1 | Flow Calculations: Channel | 82.6558 | 10 | 826.5581 | 67.6654 | 2 | 135.3308
5.2 | Flow Calculations: Culverts | 82.6558 | 10 | 826.5581 | 67.6654 | 2 | 135.3308
7 | Final Submittal
7.1 | Suggested Design Alternitives | 82.6558 | 30 | 2479.6743 | 67.6654 | 20 | 1353.3077 | 52.5053 | 10 | 525.0533
7.4 | Cost Analysis | 82.6558 | 10 | 826.5581
7.5 | Document | 82.6558 | 30 | 2479.6743 | 67.6654 | 5 | 338.3269 | 52.5053 | 10 | 525.0533 |  |  |  | 46.3372 | 2 | 92.6744
| Total |  | 271 | 22399.7243 |  | 133 | 8999.4962 |  | 132 | 6930.7037 |  | 53 | 2527.9148 |  | 6 | 278.0232
| Number of Hours | 595
| Cost of Project | 41135.8621

## Sheet4
Job Title | Base Pay Rate ($/hr) | Benefits % of Base Pay Rate | Profit % of Actual Pay | Overhead% of Base Pay Rate | Hourly Billable Rate
Project Manager | 46.3188 | 27.2% | 12% | 39.25% | 82.6558
Project Engineer: Hydrologist | 35.0962 | 29% | 12% | 51.8% | 67.6654
Engineer in Training | 24.6736 | 27.1% | 12% | 73.7% | 52.5053
Engineering Technician: Surveyor | 20.6837 | 30.7% | 12% | 87.9% | 47.6965
Administrative | 19.6486 | 31.3% | 12% | 92.53% | 46.3372

## Sheet3
| Daily Cost | Dollars per
Office Rent | 100.0267 | 3000.8 | /month
Utilities
Water (Potable) | 3.67 | 3.67 | /1000 gallons
Water (Non-Potable) | 1.55 | 1.55 | /1000 gallons
Sewer | 4.01 | 4.01 | /1000 gallons
Electricity | 16.6209 | 0.1022 | /kWh
Internet/Phone | 2.3667 | 71 | /month
Supplies
Civil 3D | 17.2055 | 7850 | /licence
Administration
Liability Insurance | 16.6667 | 500 | /per month
Total | 162.1163 | 20.2645 | /hour
Time Spent on Project | 595 | hours
Total for Project | 12057.4031

## Sheet2
Overhead as a % of Base Pay |  | Project Specifics |  | Employee Specifics
Daily Overhead Rate | 162.1163 | Total Projected Hours | 595 | Job Title | Base Pay | OH as a % of Base Pay * | Base Pay + OH
Hourly Overhead Cost | 20.2645 | Project Overhead | 12057.4031 | Project Manager | 46.32 | 43.75% | 66.5845
|  |  |  | Project Engineer | 35.1 | 57.73% | 55.3645
|  |  |  | E.I.T. | 24.67 | 82.14% | 44.9345
|  |  |  | Surveyor | 20.68 | 97.99% | 40.9445
Based on an 8 hour work day |  |  |  | Admin | 19.65 | 103.1% | 39.9145
*OH as a % of Base Pay was calculated by taking the base pay divided by the hourly OH cost.
Total Hours * Hourly OH Cost

## Sheet5
Position | Hourly Billing Rate | Total Number of Hours | Cost
Project Manager | 82.6558 | 176 | 14547.4225
Project Engineer: Hydrologist | 67.6654 | 172 | 11638.4462
Engineer in Training | 52.5053 | 142 | 7455.757
Engineering Technician: Surveyor | 47.6965 | 157 | 7488.3514