## Sheet1
ROLE |  | SENG |  |  |  |  | ENG |  |  |  |  | LAB |  |  |  |  | INT
TASK | Scheduled Completion date | D | R | T | H | K | D | R | T | H | K | D | R | T | H | K | D | R | T | H | K
1.0 WORK PLAN | 2015-12-11 | SENG H: 4; INT K: 5
1.1 SAP | 2015-12-11 | SENG D: 17; SENG R: 17; SENG T: 17; SENG H: 18; SENG K: 5
1.2 HASP | 2015-12-11 | SENG D: -; SENG R: -; SENG T: -; SENG H: -; SENG K: 13; INT K: 5
2.0 SAMPLING | 2016-01-30
Sampling prep |  | INT D: 3; INT T: 3; INT H: 3
Actual sampling |  | ENG K: 27; INT D: 28; INT R: 28; INT T: 28; INT H: 28; INT K: 1
3.0 ANALYSIS | 2016-03-09
3.1 Sample Prep for XRF | 2/17/0216 | ENG K: 3.5; LAB D: 12; LAB R: 12; LAB T: 9; LAB H: 9; LAB K: 12; INT R: 3.5; INT T: 3
3.2 XRF | 2016-03-02 | LAB D: 8; LAB R: 8; LAB T: 10; LAB H: 17; LAB K: 9
3.2.1 XRF training |  | LAB D: 3; LAB R: 3; LAB T: 3; LAB H: 3; LAB K: 3
3.3 Sample Prep for AA | DONE 3/4/2016 to Chem lab 3/7/2016 | LAB D: 12; LAB R: 15; LAB T: 10; LAB H: 0; LAB K: 6
3.4 GIS Map |  | INT D: 10
4.0 RISK ASSESSMENT | 2016-03-24
4.1 Human Health |  | SENG D: 2; SENG R: 13; SENG H: 18; SENG K: 2; ENG H: 7
4.2 Ecological Health |  | SENG T: 7
5.0 PA/SI | 2016-05-06
5.1 50% PA/SI | 2016-03-11 | SENG D: 4; ENG R: 3; ENG T: 4; ENG H: 6; ENG K: 4
5.2 Final PA/SI | 2016-05-06 | SENG D: 3; SENG R: 3; SENG T: 3; SENG H: 3; SENG K: 3; ENG R: 3; ENG T: 3; ENG H: 3; ENG K: 3
6.0 PROJECT MANAGEMENT | 2016-05-09
6.1 Presentaion | 2016-04-29 | SENG D: 2; ENG R: 2; ENG T: 2; ENG H: 2; ENG K: 2; INT T: 1
6.2 Website | 2016-05-06 | ENG T: 15; INT D: 2; INT T: 7
6.3 Meetings | Ongoing | ENG D: 19; ENG R: 21; ENG T: 19; ENG H: 21; ENG K: 19
6.4 Status Updates | Ongoing | ENG D: 2.5; ENG R: 2.5; ENG T: 2.5; ENG H: 2.5; ENG K: 2.5
SENG | ENG | SENG D: LAB; SENG R: INT
writting (major) | writing | SENG D: XRF; SENG R: inventory
editing (major) | sieving | SENG D: AA Prep; SENG R: editing
client meetings | drying | SENG R: notes (memos)
| gridding | SENG R: sampling (30)
| sample collection | SENG R: Website
client meetings | bar: SENG D to SENG R
risk assesment analysis | bar: SENG D to SENG R
| AA Prep | SENG K: SENG; ENG D: 154
[6 empty] | EN | 201
Taylor | 146.5 | SENG K: LAB; ENG D: 164
Dani | 127.5 | SENG K: INT; ENG D: 158.5
Robert | 134
Haley | 144.5
Kelsey | 125
total: | 677.5 | SENG D: 750