## Compiled
Last Updated: 5/9/2017
Task | SENG |  |  | ENG |  |  | LAB |  |  |  | INT |  |  |  | ADMA
| Josue | Jessica | David | Josue | Jessica | David | Josue | Jessica | David | Bero | Josue | Jessica | David | Ziyan | Josue | Jessica | David
1.0 Work Plan | 6 | 6.5 | 10 | 6 | 6 | 9.5
2.0 Training
2.1 Field Safety |  |  |  | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
2.2 Chemical Hygiene |  |  |  | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
2.3 XRF |  |  |  | 0 | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 3 | 0
2.4 HAZWOPER |  |  |  | 0 | 40 | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 40 | 0
3.0 Sampling |  |  |  | 0 | 20 | 0 | 20 | 0 | 0 | 20 | 0 | 0 | 20 | 0
4.0 Lab Analysis
4.1 Sieving of Soil Samples | [6 empty] | 9 | 12 | 17.5 | 0 | 8 | 11 | 16 | 6
4.2 XRF Analysis | [6 empty] | 4 | 6 | 5 | 0 | 3 | 5 | 4 | 0
4.3 Acid Digestion | [6 empty] | 7.5 | 3.5 | 6.5 | 0 | 7.5 | 3.5 | 6.5 | 0
4.4 Atomic Absorption
4.5 XRF vs AA Correlation |  |  |  | 0.5 | 0 | 6.5
4.6 GIS Mapping |  |  |  | 1 | 8.5 | 0
5.0 Screening Risk Assessment
5.1 Human Health | 2.5 | 0 | 0 | 2.5 | 0 | 0
5.2 Ecological Risk | 3 | 0 | 0 | 2.5 | 0 | 0
6.0 PA/SI | 5.5 | 4 | 5.5 | 5.5 | 3.5 | 3.5
7.0 Project Management
7.1 Team Meetings | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0.5 | 0.5
7.2 Client Meetings | 0 | 0 | 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
7.3 Technical Advisor Meetings | 3.5 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 2.5
7.4 Website | [14 empty] | 0 | 0 | 1.5
7.5 Presentation(s) | 2 | 1.5 | 5 | 1 | 1.5 | 5 |  |  |  |  | 1 | 1.5 | 3 | 0
7.6 Project Management | [14 empty] | 4.5 | 8 | 14
Subtotals | 23 | 15.5 | 24 | 22.5 | 88 | 28 | 85.5 | 21.5 | 29 | 20 | 19.5 | 21 | 94.5 | 6 | 8 | 11.5 | 18.5
TOTAL | 62.5 |  |  | 138.5 |  |  | 156 |  |  |  | 141 |  |  |  | 38
GRAND TOTAL | 536
Josue total: | 158.5
Jessica total: | 157.5
David total: | 194

## Josue
Date | Hours | Task/Deliverable | Notes
| 12 | Work Plan | Did not keep good track of it
| 3 | XRF
| 1 | Chem Hygiene
| 1 | Field Safety
| 40 | HAZWOPER
Trip | 20
2017-01-28 | 4.5 | Sieving
2017-01-29 | 3.5 | Sieving
2017-01-30 | 2.5 | Pulverizing
2017-01-31 | 1.5 | Pulverizing
2017-02-04 | 3 | Sieving and drying
2017-01-23 | 2.5 | Project Management
2017-01-24 | 0.5 | drying
2017-01-27 | 1 | sieving
2017-02-10 | 1.5 | sieving
2017-02-12 | 2 | xrf
2017-02-15 | 1.5 | xrf
2017-02-14 | 1 | Project Management
2017-02-16 | 3.5 | xrf
2017-02-26 | 2 | PA/SI
2017-03-04 | 8.5 | Acid DIgestion
2017-03-05 | 3 | Centrifuge
2017-03-08 | 0.5 | Project Management
2017-03-16 | 1.5 | Centrifuge
2017-03-22 | 2 | Centrifuge
2017-03-23 | 0.5 | Prjct Mngmnt (Haz Waste)
2017-03-26 | 1.5 | Risk Assessment
2017-03-29 | 1 | Risk Assessment
2017-04-05 | 0.5 | Project Management (GPS)
2017-04-06 | 1 | Eco Risk Assessment
2017-04-10 | 0.5 | Correlation
2017-04-10 | 3 | Presentation
2017-04-06 | 0.5 | Bero mtg
2017-04-12 | 1.5 | Eco Risk Assessment
2017-04-13 | 1 | Human risk
2017-04-15 | 1.5 | Human risk
2017-04-17 | 1.5 | Eco Risk
2017-04-19 | 1.5 | Eco Risk
2017-04-24 | 0.5 | Grid
04-xx-2017 | 1 | Practice for presentation
2017-05-01 | 4 | PA/SI (Risk Assessment)
2017-05-07 | 5 | Pa/si

## Jessica
Date | Hours | Task/Deliverable | Notes
2016-10-11 | 1 | Work plan | Mtg w/ Bero about the Workplan, should be applied to all team members
2016-10-12 | 1 | Work plan | Team Mtg: work plan delegation, apply to all team members
2016-10-20 | 1 | Work plan | Mtg w/ Taylor about workplan, apply to all team members
2016-10-28 | 3 | XRF Training
2016-10-30 | 2 | Work plan | Research and writing of the SAP
2016-11-01 | 2 | Work plan | Research and writing of the SAP
2016-11-06 | 1 | Work plan | Research and writing of the SAP
2016-11-08 | 0.5 | Work plan | Mtg w/ Bero, applied to Josue & David
2016-11-09 | 1 | Work plan
2016-11-15 | 1 | Work plan
2016-11-17 | 2 | Work plan | Work plan bulk text
2016-12-19 | 2 | HAZWOPER
2016-12-21 | 6 | HAZWOPER
2016-12-22 | 6 | HAZWOPER
2016-12-23 | 6 | HAZWOPER
2016-12-24 | 6 | HAZWOPER
2016-12-25 | 3 | HAZWOPER
2016-12-26 | 6 | HAZWOPER
2017-01-17 | 1 | Sampling Trip | Mtg w/ Bero, applied to all team members
2017-01-17 | 1 | Chem Hygiene Training
2017-01-17 | 1 | Field Safety Training
2017-01-19 | 1 | Sampling Trip | Buying extra materials for trip
2017-01-19 | 1 | Sampling Trip | Packing van for trip
2017-01-20 | 10 | Sampling Trip | Day 1
2017-01-21 | 10 | Sampling Trip | Day 2
2017-01-24 | 0.5 | Team Mtg
2017-01-26 | 0.5 | TA Mtg
2017-01-26 | 0.5 | Bero Mtg
2017-01-26 | 3 | Drying & Sieving
2017-01-27 | 3 | Drying & Sieving
2017-01-28 | 2 | Drying & Sieving
2017-01-29 | 2 | Drying & Sieving
2017-01-30 | 2 | Drying & Sieving
2017-01-31 | 2.5 | Drying & Sieving
2017-02-01 | 1.5 | Drying & Sieving
2017-02-02 | 0.5 | Bero Mtg
2017-02-02 | 2 | Sieving
2017-02-02 | 1 | Status pres prep
2017-01-29 | 1 | Status pres prep
2017-02-05 | 2 | Sieving
2017-02-06 | 0.5 | Status pres prep
2017-02-07 | 1 | Sieving
2017-02-08 | 0.5 | Proj Management
2017-02-09 | 0.5 | TA Mtg
2017-02-09 | 3 | XRF
2017-02-10 | 0.5 | Proj Management
2017-02-10 | 4 | XRF
2017-02-11 | 2 | Sieving
2017-02-11 | 4 | XRF
2017-02-20 | 3 | PA/SI
2017-03-02 | 0.5 | Bero Mtg
2017-03-03 | 0.5 | Proj Management
2017-03-04 | 7 | Acid Digestion
2017-03-20 | 0.5 | Proj Management
2017-03-22 | 0.5 | Proj Management
2017-03-23 | 0.5 | Proj Management
2017-03-30 | 1 | Proj Management
2017-03-31 | 1 | Proj Management
2017-04-05 | 0.5 | Proj Management
2017-04-06 | 1 | Proj Management
2017-04-06 | 2.5 | GIS
2017-04-07 | 2.5 | GIS
2017-04-10 | 1 | GIS
2017-04-06 | 0.5 | Bero Mtg
2017-04-13 | 2 | TA & Bero Mtg
2017-04-14 | 1 | GIS
2017-04-18 | 1 | Bero Mtg
2017-04-18 | 1.5 | GIS
2017-04-26 | 0.5 | Presentation
2017-04-27 | 0.5 | Presentation
2017-04-28 | 1 | UGRADS
2017-04-29 | 2 | PA/SI
2017-05-04 | 0.5 | Proj Management
2017-05-05 | 2.5 | PA/SI

## David
Date | Hours | Task/Deliverable | Notes | KEY
2016-09-04 | 1 | NAU Chem Hyg |  | Training
2016-09-04 | 1 | NAU Field Safety |  | Work Plan
2016-10-11 | 1 | Work Plan | Mtg w/Bero | Sampling
2016-10-12 | 1 | Work Plan | Team Mtg | Lab Analysis
2016-10-20 | 1 | Work Plan | Mtg w/Taylor | Risk Assessment
2016-10-28 | 3 | XRF Training | 1-4pm if I remember right? | PA/SI
2016-11-06 | 3 | Work Plan | Writing HASP | Project Mgmt
2016-11-07 | 2 | Work Plan | Copy editing
2016-11-08 | 0.5 | Work Plan | Mtg w/ Bero
2016-11-19 | 1 | Work Plan | Editing HASP
2016-11-20 | 4 | Work Plan | Copy editing and Naser's content
2016-12-10 | 0.5 | Work Plan | Editing HASP
2016-12-11 | 3 | Work Plan | Copy editing
2016-12-14 | 0.5 | Work Plan | Individual mtg w/Bero
2016-12-18 | 2 | Work Plan | Copy editing
2016-12-28 | 1 | Project Mgmt | Set up the time log for spring semester
2016-12-31 | 4.5 | HAZWOPER
2017-01-01 | 3.5 | HAZWOPER
2017-01-06 | 5.5 | HAZWOPER
2017-01-07 | 3.5 | HAZWOPER
2017-01-09 | 3 | HAZWOPER
2017-01-11 | 6 | HAZWOPER
2017-01-12 | 5.5 | HAZWOPER
2017-01-13 | 3.5 | HAZWOPER | Completed
2017-01-17 | 1 | Tech Advisor | Mtg w/Bero
2017-01-19 | 1 | Project Mgmt | Packing for sampling trip
2017-01-20 | 10 | Sampling | 7am-
2017-01-21 | 10 | Sampling | 8am-6pm
2017-01-23 | 2.5 | Project Mgmt | Cleaned and moved supplies, worked on lab use request, downloaded pics to drive
2017-01-24 | 0.5 | Team | Team mtg
2017-01-26 | 1 | Tech Advisor | Mtg w/Taylor, mtg w/Bero
2017-01-26 | 1.5 | Sieving | Set up smpls to dry
2017-01-27 | 3 | Sieving | drying
2017-01-27 | 1.5 | Project Mgmt | Marked bags
2017-01-28 | 4.5 | Sieving
2017-01-29 | 4 | Sieving
2017-01-29 | 2 | Sieving
2017-01-30 | 1.5 | Sieving
2017-01-30 | 2 | Sieving
2017-01-31 | 1 | Sieving
2017-02-01 | 1.5 | Sieving
2017-02-02 | 0.5 | Tech Advisor | Bero mtg
2017-02-02 | 2 | Sieving
2017-02-04 | 2 | Sieving
2017-02-04 | 1.5 | Sieving
2017-02-05 | 1.5 | Sieving
2017-02-09 | 0.5 | Tech Advisor | Mtgs w Bero and Taylor
2017-02-10 | 2.5 | Sieving
2017-02-11 | 2 | Sieving
2017-02-11 | 0.5 | Project Mgmt | Organized sample bags in room 245
2017-02-14 | 0.5 | Team | Team mtg
2017-02-16 | 0.5 | Tech Advisor | Bero mtg
2017-02-18 | 8.5 | XRF | Finished XRF
2017-02-19 | 0.5 | XRF | Re-XRF'd some samples
2017-02-19 | 3 | Correlation | Filtered and averaged XRF data
2017-02-21 | 0.5 | PA/SI | Setting up paper format
2017-02-23 | 0.5 | Tech Advisor | Bero mtg
2017-02-28 | 0.5 | Correlation
2017-03-01 | 0.5 | PA/SI
2017-03-01 | 2.5 | PA/SI
2017-03-02 | 0.5 | Tech Advisor | Bero
2017-03-04 | 13 | Acid Digestion
2017-03-05 | 2.5 | Presentation | Status update 2
2017-03-06 | 0.5 | Project Mgmt | Labeling centrifuge tubes
2017-03-08 | 0.5 | Project Mgmt | Cleaning materials lab, applies to Jess also
2017-03-21 | 0.5 | Team Meeting
2017-03-22 | 0.5 | Project Mgmt | Labeled waste buckets
2017-03-22 | 0.5 | Project Mgmt | Wrote chain of custody and cover letter for Dr. Ketterer
2017-03-23 | 0.5 | Tech Advisor | Bero, all of team
2017-03-29 | 0.5 | Correlation
2017-03-30 | 0.5 | Tech Advisor | Taylor, all of team
2017-03-30 | 0.5 | Tech Advisor | Bero, all of team
2017-04-04 | 0.5 | Correlation | Histograms
2017-04-10 | 1.5 | Correlation
2017-04-11 | 0.5 | Project Mgmt | Agenda writing (accounts for past agenda writing to this point
2017-04-11 | 0.5 | Correlation
2017-04-16 | 1 | Presentation
2017-04-17 | 2.5 | Presentation
2017-04-18 | 0.5 | Tech Advisor | Bero
2017-04-19 | 1 | Project Mgmt | TA mtg minutes formatting and touch-up
2017-04-19 | 3 | Presentation | prax pres
2017-04-20 | 0.5 | Project Mgmt | Show Bero samples, talk with Gary re: samples
2017-04-22 | 2.5 | Project Mgmt | Packing samples, chain of custody, etc.
2017-04-26 | 3 | Presentation | UGrads prep
2017-04-28 | 1 | Presentation | All of team, doing the damn thing (presentation)
2017-04-29 | 0.5 | Project Mgmt | Scanning and uploading logbook scans for PA/SI
2017-04-30 | 0.5 | Project Mgmt | Wiping down empty crates
2017-05-06 | 3 | PA/SI
2017-05-06 | 1.5 | Website
2017-05-08 | 2.5 | PA/SI