## Slide 1: Mental Health Counseling Mobile Office Space
Bret Burkes, Kristen Henderson, Edwin Perez, Danielle Yamson
CENE-486C Presentation
April 26, 2019

## Slide 2: Project Introduction
Purpose
  Design a mobile office that can be utilized as a mental health consultation area
Client
  A Licensed Professional Counselor
Location
  The mobile office will operate mostly in Yavapai and Coconino County
Background
  Design an office space to provide health counseling for those without the abilities of transportation

## Slide 3: Project Constraints/Criteria
$50,000 budget
Solar Panels
  Removable Panels
  Main source of power
    Zero use of propane or gas
Composting Toilet System
Sound-proof Counseling Room
Removable Wall between Counseling Room and Waiting Area
Determine which Construction and Design Codes to follow
Last minute client request: shorten the trailer length

## Slide 4: Design standards
  Federal Motor Vehicle Standards
  National Fire Protection Association 70 (NFPA 70) Electrical Standards
  American National Standards Institute for Recreational Vehicles
  International Building Code (IBC)
  National Design Specification for Wood Construction
  Special Design Provisions for Wind & Seismic
  Arizona Department of Transportation (ADOT) Standards

## Slide 5: Project impacts
Social:
Clients who do not have access to mental health consultation in their area will now be offered that option
Economical:
Client is able to travel for business and reach out to more clients
Environmental:
Less gas emissions by reducing the amount of travel done by the clients

## Slide 6: Architectural plan

## Slide 12: structural Plan

## Slide 23
23

## Slide 24: Electrical Plan

## Slide 29: Plumbing Plan

## Slide 30
COLD AND HOT WATER PIPES - 1/2"
GREY WATER PIPES- 2"
BLACK WATER PIPES - 2"
12V WATER PUMP - 3 GPM

## Slide 31: Cost of Construction Estimate

## Slide 32
Table 1: Materials Cost Estimate
Materials Cost Estimate | 
Category | Cost
Soundproofing | $ 660.00
Trailer Frame | $ 10,176.00
Structure (includes wood frame, wall panels, doors, windows, flooring, sheathing, etc.) | $ 13,497.00
Roof (includes wood, metal, and underlayment) | $ 738.00
Solar Array | $ 12,638.00
Electrical (includes lighting and switching) | $ 297.00
Appliances (includes refrigerator, microwave, and oven) | $ 1,194.00
HVAC | $ 1,601.00
Plumbing (includes tanks, pump, pipes, water heater, hose, shower, sinks, toilet, etc.) | $ 1,739.00
Total Cost of Material | $ 42,540.00

## Slide 33
Table 2: Construction Cost Estimate
Construction Cost Estimate | 
Category | Cost
Electrical | $ 1,500.00
Plumbing | $ 1,500.00
Remaining Construction | $ 3,000.00
Total Cost of Construction | $6,000.00
Table 3: Estimated Total Project Cost Estimate
Estimated Total Cost of Project | 
Category | Cost
Total Cost of Material | $ 42,540.00
Total Cost of Construction | $ 6,000.00
Total Cost of Project | $ 48,540.00

## Slide 34: Cost of engineering services
Table 4: Original Estimated Cost of Engineering Services
 | Classification | Hours | Rate/Hour | Cost
1.0 Personnel | Senior Engineer | 102 | 194 | $19,788
 | Engineer | 356 | 98 | $34,888
 | Intern | 120 | 42 | $5,040
 | Project Manager | 250 | 129 | $32,250
 |  |  | Total Cost | $91,966

## Slide 35: Cost of engineering services
 | Classification | Hours | Rate/Hour | Cost
1.0 Personnel | Senior Engineer | 47 | 194 | $9,118
 | Engineer | 163 | 98 | $15,974
 | Intern | 55 | 42 | $2,310
 | Project Manager | 114 | 129 | $14,706
 |  |  | Total Cost | $42,108
Table 5: Actual Cost of Engineering Services

## Slide 36
 | Staff (hrs) |  |  |  | Task Total | Commenced Total
Project Tasks | ENG | SENG | INT | PM |  | 
1.0 Preliminary Layout | 129 | 13 | 39 | 41 | 222 | 101
1.1 Design Constraints & Criteria | 17 | 2 | 6 | 8 |  | 
1.2 Architectural Layout | 20 | 2 | 8 | 7 |  | 
1.3 Electrical Layout | 29 | 4 | 7 | 7 |  | 
1.4 Plumbing Layout | 16 | 1 | 5 | 7 |  | 
1.5 Structural Layout | 19 | 1 | 7 | 6 |  | 
1.6 Mechanical Layout | 28 | 3 | 6 | 6 |  | 
2.0 Design Plans | 138 | 47 | 63 | 7 | 255 | 156
2.1 Architectural Plan | 38 | 12 | 20 | 2 |  | 
2.2 Plumbing Plan | 18 | 5 | 10 | 1 |  | 
2.3 Electrical Plan | 20 | 7 | 10 | 1 |  | 
2.4 Structural Plan | 45 | 18 | 14 | 2 |  | 
2.5 Mechanical Plan | 17 | 5 | 9 | 1 |  | 
3.0 Cost Estimate | 27 | 13 | 9 | 42 | 91 | 44
3.1 Materials Cost | 15 | 6 | 4 | 15 |  | 
3.2 Construction Cost | 12 | 7 | 5 | 27 |  | 
4.0 Project Management | 62 | 29 | 9 | 160 | 260 | 78
4.1 Scheduling | 42 | 20 | 5 | 110 |  | 
4.1.1 Preliminary Design | 10 | 4 | 2 | 28 |  | 
4.1.2 Design Plans | 15 | 5 | 1 | 14 |  | 
4.1.3 Cost Estimate | 8 | 6 | 1 | 32 |  | 
4.1.4 Final Proposal/Final Presentation | 9 | 5 | 1 | 36 |  | 
4.2 Deliverables | 0 | 4 | 1 | 22 |  | 
4.3 Meetings | 20 | 5 | 3 | 28 |  | 
Staff Total | 356 | 102 | 120 | 250 | 828 | 379
Table 6: Comparison of Estimated vs Actual Hours

## Slide 37: Gantt chart

## Slide 38: Project Milestones
Milestone | Expected Date of Completion | Actual Date of Completion
Preliminary Plans | 1/29/2019 | 1/29/2019
30% Submittal | 2/12/2019 | 2/11/2019
60% Submittal | 3/12/2019 | 3/11/2019
Final Architectural Plan | 4/23/2019 | 4/12/2019
Final Structural Plan | 4/23/2019 | 4/15/2019
90% Submittal | 4/16/2019 | 4/16/2019
Final Submittal | 5/7/2019 | 
Table 7: Project Milestone Expected Completion vs. Actual Completion Dates

## Slide 39
Figure 1: Original Gantt Chart

## Slide 40
Figure 2: Updated Gantt Chart

## Slide 41: Conclusion
Met Fully Electric Recommendation
Met $50,000 Budget with Total Project Cost at $48,540
Met Office Space Recommendations
Met Low Waste/Efficient Plumbing System
Figure 3: Rendering 3D View
Figure 4: Rendering Floor Plan