## Billing rates
Position | Code | Base pay ($/hr) | Benefits (% of pay) | Actual pay ($/hr) | Overhead (% of base pay) | Actual pay + Overhead ($/hr) | Profit, % of actual pay + OH | Profit ($/hr) | Billing rate ($/hr) | Multiplier | Base pay as annual salary ($/yr)
Senior Engineer | SE | 64.59 | 40 | 90.426 | 70 | 135.639 | 12.5 | 16.9549 | 152.5939 | 2.3625 | 134347.2
Engineer | PE | 53.83 | 50 | 80.745 | 25 | 94.2025 | 12.5 | 11.7753 | 105.9778 | 1.9688 | 111966.4
Project Manager | PM | 43.06 | 70 | 73.202 | 15 | 79.661 | 12.5 | 9.9576 | 89.6186 | 2.0812 | 89564.8
Drafter | DR | 32.3 | 50 | 48.45 | 5 | 50.065 | 12.5 | 6.2581 | 56.3231 | 1.7437 | 67184
0
Total |  | 193.78 | [6 empty] | 404.5134 | 2.0875
* Base pay includes FICA and payroll taxes
|  | 60 | 64.59
|  | 50 | 53.825
|  | 40 | 43.06
|  | 30 | 32.295
|  | 19 | 20.4535
Billing rate summary table
Position | Code | Billing rate ($/hr) | Multiplier
Senior Engineer | SE | 152.5939 | 2.3625
Engineer | E | 105.9778 | 1.9688
Project Manager | PM | 89.6186 | 2.0812
Drafter | DR | 56.3231 | 1.7437

## Staffing Matrix
| Task | Senior Egr. | Project Egr. | Proj. Manager | Drafter | Total
| Task 1.0: Research and Regulatory Considerations | SE | E | PM | DR | Total | Days | Hours | 10 days
| Task 1.1: Review Past Solutions | 5 | 6 | 8 | 4 | 23 | 5 | 40
| Task 1.2: Regulatory Considerations | 6 | 16 | 16 | 13 | 51 | 5 | 40
Task 1.2.1: Federal Highway Administration (FHWA)
Task 1.2.2 ADOT Roadway Design Guidelines
| Total Task 1.0 | 11 | 22 | 24 | 17 | 74 |  |  | 13 days
| Task 2.0: Site Investigation | SE | E | PM | DR
2 | Task 2.1: Surveying and Soil Data | 1 | 2 | 2 | 4 | 9 | 2 | 16
| Task 2.2: Existing Geometry | 2 | 4 | 4 | 8 | 18 | 4 | 32
1 | Task 2.3: Identify Contributing Intersections | 1 | 3 | 2 | 3 | 9 | 3 | 24
3 | Task 2.4: Lane Configurations | 0 | 2 | 2 | 4 | 8 | 2 | 16 | Task | Days | Hours
| Task 2.5: Site Restrictions | 2 | 6 | 6 | 12 | 26 | 4 | 32 | 1 | 10 | 80
| Task 2.6: Investigate Proposed Developments | 1 | 2 | 6 | 6 | 15 | 4 | 32 | 2 | 13 | 104
| Total Task 2.0 | 7 | 19 | 22 | 37 | 85 |  |  | 3 | 10 | 80
| Task 3.0: Collection of Traffic Data from ADOT | SE | E | PM | DR |  |  |  | 4 | 7 | 56
1 | Task 3.1: Existing Plan Set | 3 | 6 | 6 | 14 | 29 | 9 | 72 | 5 | 24 | 192
2 | Task 3.2: Classification of Vehicles | 2 | 4 | 4 | 4 | 14 | 3 | 24 | 6 | 19 | 152
| Task 3.3: Five-Year Crash Data | 1 | 2 | 2 | 4 | 9 | 4 | 32 |  |  | 664
2.5 | Task 3.4: Signal Timing and Phasing | 2 | 4 | 4 | 6 | 16 | 3 | 24
| Total Task 3.0 | 8 | 16 | 16 | 28 | 68
| Task 4.0: Traffic Counts | SE | E | PM | DR
| Task 4.1: Field Safety Plan | 2 | 4 | 4 | 4 | 14 | 2 | 16
| Task 4.2: Peak Hour Volumes | 2 | 6 | 6 | 6 | 20 | 3 | 24
| Task 4.3: Upload Data | 0.5 | 3 | 3 | 3 | 9.5 | 2 | 16
| Total Task 4.0 | 4.5 | 13 | 13 | 13 | 43.5
| Task 5.0: Traffic Analysis | SE | E | PM | DR
| Task 5.1: Base Model Creation and Calibration | 14 | 28 | 28 | 28 | 98 | 9 | 72
| Task 5.2: VISSIM analysis of base conditions | 5 | 10.5 | 10.5 | 10.5 | 36.5 | 10 | 80
| Task 5.3: 20-Year Projection | 4.5 | 9 | 9 | 9 | 31.5 | 6 | 48
| Total Task 5.0 | 23.5 | 47.5 | 47.5 | 47.5 | 166 |  | 0
| Task 6.0: Alternatives and Evaluation of Impacts | SE | E | PM | DR
| Task 6.1: Scoring System | 8 | 16 | 16 | 16 | 56
| Task 6.1.1: Design Criteria | [5 empty] | 7
Task 6.1.2: Construction Considerations
Task 6.1.3: Evaluation of Impacts
| Task 6.2: Generate and Analyze Alternatives | 10 | 20 | 20 | 20 | 70 |  | 56
| Task 6.3: Scoring, Selection of Final Alternative | 2 | 6 | 4 | 4 | 16 | 9 | 72
| Task 6.4: Preliminary and Final Design Plan Sets | 8 | 32 | 32 | 40 | 112 | 2 | 16
| Total Task 6.0 | 28 | 74 | 72 | 80 | 254 | 4 | 32
| Task 7.0: Project Deliverables | SE | E | PM | DR |  | 10 | 80
| Task 7.1: 30% Report and Presentation | 3 | 6 | 6 | 6 | 21
| Task 7.2: 60% Report and Presentation | 3 | 6 | 6 | 6 | 21
| Task 7.3: 90% Report | 3 | 6 | 6 | 6 | 21 | 11 | 88
| Task 7.4: Final Report and Presentation | -- | -- | -- | -- | 0 | 11 | 88
| Task 7.4.1: Final Report | 3 | 6 | 6 | 6 | 21 | 11 | 88
| Task 7.4.2: UGRADS Presentation | 4 | 4 | 4 | 4 | 16
| Task 7.5: Website | -- | -- | -- | -- | 0 | 5 | 40
| Task 7.5.1: 90% Website | 2 | 4 | 4 | 4 | 14 | 5 | 40
| Task 7.5.2: Final Website | 1 | 2 | 2 | 2 | 7
| Total Task 7.0 | 19 | 34 | 34 | 34 | 121 | 5 | 40
| Task 8.0: Project Management | SE | E | PM | DR |  | 5 | 40
| Task 8.1: Resource Management | 5 | 10 | 20 | 0 | 35
| Task 8.2: Client and TA Meetings | -- | -- | -- | -- | 0
| Task 8.2.1: Client meeting 1 | 1 | 1 | 1 | 1 | 4 | 0 days | 592
| Task 8.2.2: TA meeting 1 | 1 | 1 | 1 | 1 | 4 | 74 days
| Task 8.2.3: TA meeting 2 | 1 | 1 | 1 | 1 | 4 | 74 days
| Task 8.2.4: Client meeting 2 | 1 | 1 | 1 | 1 | 4 | 74 days
| Task 8.2.5: TA/client meeting 3 | 1 | 1 | 1 | 1 | 4 | 0 days
| Task 8.2.6: Client meeting 4 | 1 | 1 | 1 | 1 | 4 | 0 days
| Task 8.2.7: TA meeting 4 | 1 | 1 | 1 | 1 | 4 | 0 days
| Task 8.3: GI Meetings | 8 | 8 | 8 | 8 | 32 | 0 days
| 129 | 8 | 8 | 8 | 8 | 32 | 0 days
| Total Task 8.0 | 28 | 33 | 43 | 23 | 127 | 74 days
| Total Of All Tasks | 129 | 258.5 | 271.5 | 279.5 | 938.5 | 74 days
1912
| Classification | Hours | Billing rate/hr | Total billed | Comments
| SE | 129 | 152.5939 | 19684.6099
| PE | 258.5 | 105.9778 | 27395.2645
| PM | 271.5 | 89.6186 | 24331.4567
| DR | 279.5 | 56.3231 | 15742.3134
| LT | #REF! |  | #REF!
Staffing Matrix Summary
| Position | SE | E | PM | DR | Total
| Task 1.0: Research and Regulatory Considerations | 11 | 22 | 24 | 17 | 74
| Task 2.0: Site Investigation | 7 | 19 | 22 | 37 | 85
| Task 3.0: Collection of Traffic Data from ADOT | 8 | 16 | 16 | 28 | 68
| Task 4.0: Traffic Counts | 4.5 | 13 | 13 | 13 | 43.5
| Task 5.0: Traffic Analysis | 23.5 | 47.5 | 47.5 | 47.5 | 166
| Task 6.0: Alternatives and Evaluation of Impacts | 28 | 74 | 72 | 80 | 254
| Task 7.0: Project Deliverables | 19 | 34 | 34 | 34 | 121
| Task 8.0: Project Management | 28 | 33 | 43 | 23 | 127
| Total Of All Tasks | 129 | 258.5 | 271.5 | 279.5 | 938.5

## Staffing matrix pres
Task | Senior Egr. | Project Egr. | Proj. Manager | Drafter | Total
Task 1.0: Research and Regulatory Considerations | 11 | 22 | 24 | 17 | 74
Task 1.1: Review Past Solutions | 5 | 6 | 8 | 4 | 23
Task 1.2: Regulatory Considerations | 6 | 16 | 16 | 13 | 51
Task 1.2.1: Federal Highway Administration (FHWA)
Task 1.2.2 ADOT Roadway Design Guidelines
Task 2.0: Site Investigation | 7 | 19 | 22 | 37 | 85
Task 2.1: Surveying and Soil Data | 1 | 2 | 2 | 4 | 9
Task 2.2: Existing Geometry | 2 | 4 | 4 | 8 | 18
Task 2.3: Identify Contributing Intersections | 1 | 3 | 2 | 3 | 9
Task 2.4: Lane Configurations | 0 | 2 | 2 | 4 | 8
Task 2.5: Site Restrictions | 2 | 6 | 6 | 12 | 26
Task 2.6: Investigate Proposed Developments | 1 | 2 | 6 | 6 | 15
Task 3.0: Collection of Traffic Data from ADOT | 8 | 16 | 16 | 28 | 68
Task 3.1: Existing Plan Set | 3 | 6 | 6 | 14 | 29
Task 3.2: Classification of Vehicles | 2 | 4 | 4 | 4 | 14
Task 3.3: Five-Year Crash Data | 1 | 2 | 2 | 4 | 9
Task 3.4: Signal Timing and Phasing | 2 | 4 | 4 | 6 | 16
Task | Senior Egr. | Project Egr. | Proj. Manager | Drafter | Total
Task 4.0: Traffic Counts | 4.5 | 13 | 13 | 13 | 43.5
Task 4.1: Field Safety Plan | 2 | 4 | 4 | 4 | 14
Task 4.2: Peak Hour Volumes | 2 | 6 | 6 | 6 | 20
Task 4.3: Upload Data | 0.5 | 3 | 3 | 3 | 9.5
Task 5.0: Traffic Analysis | 23.5 | 47.5 | 47.5 | 47.5 | 166
Task 5.1: Base Model Creation and Calibration | 14 | 28 | 28 | 28 | 98
Task 5.2: VISSIM analysis of base conditions | 5 | 10.5 | 10.5 | 10.5 | 36.5
Task 5.3: 20-Year Projection | 4.5 | 9 | 9 | 9 | 31.5
Task 6.0: Alternatives and Evaluation of Impacts | 28 | 74 | 72 | 80 | 254
Task 6.1: Scoring System | 8 | 16 | 16 | 16 | 56
Task 6.1.1: Design Criteria
Task 6.1.2: Construction Considerations
Task 6.1.3: Evaluation of Impacts
Task 6.2: Generate and Analyze Alternatives | 10 | 20 | 20 | 20 | 70
Task 6.3: Scoring, Selection of Final Alternative | 2 | 6 | 4 | 4 | 16
Task 6.4: Preliminary and Final Design Plan Sets | 8 | 32 | 32 | 40 | 112
Task 7.0: Project Deliverables | 19 | 34 | 34 | 34 | 121
Task 8.0: Project Management | 28 | 33 | 43 | 23 | 127
Total Of All Tasks | 129 | 258.5 | 271.5 | 279.5 | 938.5
Task 8.1: Resource Management | 5 | 10 | 20 | 0 | 35
Task 8.2: Client and TA Meetings | -- | -- | -- | -- | 0
Task 8.2.1: Client meeting 1 | 1 | 1 | 1 | 1 | 4
Task 8.2.2: TA meeting 1 | 1 | 1 | 1 | 1 | 4
Task 8.2.3: TA meeting 2 | 1 | 1 | 1 | 1 | 4
Task 8.2.4: Client meeting 2 | 1 | 1 | 1 | 1 | 4
Task 8.2.5: TA/client meeting 3 | 1 | 1 | 1 | 1 | 4
Task 8.2.6: Client meeting 4 | 1 | 1 | 1 | 1 | 4
Task 8.2.7: TA meeting 4 | 1 | 1 | 1 | 1 | 4
Task 8.3: GI Meetings | 8 | 8 | 8 | 8 | 32
Task 8.4: Team Meetings | 8 | 8 | 8 | 8 | 32
Total Task 8.0 | 28 | 33 | 43 | 23 | 127

## Cost of Egr. Services
1.0 Personnel | Classification | Unit | Rate per Unit | Quantity | Cost | Source of rate | Calculation of rate
| SE | Hours | 152.5939 | 129 | 19684.6099 | Billing rate sheet
| E | Hours | 105.9778 | 258.5 | 27395.2645 | Billing rate sheet
| PM | Hours | 89.6186 | 271.5 | 24331.4567 | Billing rate sheet
| DR | Hours | 56.3231 | 279.5 | 15742.3134 | Billing rate sheet
| Total personnel |  |  |  | 87153.6445
2.0 Travel | Classification |  | Rate per Mile | Miles | Cost | Source of rate | Calculation of rate
| Travel to site |  |  |  |  | AZ GAO
| 3 vehicles, 2 round trips, 130 miles R/T, @ $0.445/mile |  | 0.445 | 780 | 347.1
| Total travel |  |  |  | 347.1
3.0 Supplies | Classification |  | Rate per Day | Days | Cost | AZ GAO
Traffic Lab access
| 20 days @ $100/day |  | 100 | 20 | 2000
| Total supplies |  |  |  | 2000
4.0 Total Cost of Engineering Services |  |  |  |  | 89500.7445 | Source of rate
Estimated share of NAU CEnE program fee