|  | Weekly Team Task and Status Meeting Report | Report#: 08 |
| --- | --- | --- |

| # Team: Egg Men Industries | Meeting Date: March 24, 2011 |
| --- | --- |
| Project Title: SCREEN3 |  |
| Team members present: Cyle Chad Ryan | On-time: Cyle Chad Ryan |

### Progress of Team Meetings

- last meeting(s): 	03/23/2011, 12:00pm – 2:00pm, bldg 69

- next meeting(s): 	03/24/2011, 2:00pm – 4:00pm, bldg. 69

- Communication Problems?  None

### Last week’s Tasks: Status

| Task Title: Website Forms (SCREEN3) | Task Initiation: 02/08/2011 | Orig. Due Date: 02/15/2011 | Status: FINISHED |
| --- | --- | --- | --- |
| Description: Creating the form of the SCREEN3 data entry page. This includes a dynamic entry screen for the different options. |  |  |  |
| Responsible for Task: - Cyle (100%) Create the SCREEN3 data entry page and find data entry ranges |  |  |  |
| Outcome(s) and Progress: - The input form is completed, with each input placed where it should be, and all forms flowing correctly. The correct form entities (text boxes, radio buttons, etc.) are all used in the correct spots. |  |  |  |
| Evaluation: When coding the forms used a uniform variable naming scheme, commenting at every section for ease of maintenance. |  |  |  |

| Task Title: Website Forms (Flow Diagram) | Task Initiation: 02/08/2011 | Orig. Due Date: 02/15/2011 | Status: DELAYED until 3/31/2011 |
| --- | --- | --- | --- |
| Description: Main web pages created (Home, About, Contact Us, Create User/Sign up, Graph, Archive, Admin) with full connectivity established along with all basic form completed. |  |  |  |
| Responsible for Task: - Ryan (100%) Create the websites with all parts. General form of final website |  |  |  |
| Outcome(s) and Progress: - Create User page finished, new users can be added to database - Admin page functionality improved, users are removed from the database - Login page verifies user’s username/password correctly |  |  |  |
| Evaluation: Ryan has run into some problems attempting to send emails through the local WAMP server, which were to be used to send users their initial passwords. Other than that, creating a user works perfectly, as does deleting a user. All that remains for the website are the 3 “descriptive” pages (Home, About, Contact Us) as well as the Archive and Graph pages. |  |  |  |

| Task Title: Form Functionality | Task Initiation: 03/02/2011 | Orig. Due Date: 03/10/2011 | Status: DELAYED until 3/31/2011 |
| --- | --- | --- | --- |
| Description: Adding functionality to the forms created with WebStep. Functionality includes halting progress if required inputs are empty, also accepting only valid data types & ranges. |  |  |  |
| Responsible for Task: - Cyle (30%) - Chad (70%) |  |  |  |
| Outcome(s) and Progress: - Pages that exist are mostly functional |  |  |  |
| Evaluation: With the delayed SCREEN3 form creation the following functionality is also lacking. |  |  |  |

### This week’s Tasks: Work plan

Continue work on existing projects

| Task Title: Website Forms (Flow Diagram) | Task Initiation: 02/08/2011 | Orig. Due Date: 02/21/2011 | Status: DELAYED until 03/31/2011 |
| --- | --- | --- | --- |
| Description: Create descriptive pages, as well as Archive and Graph. Put all pages together into one single flowing website. Creates CSS sheet for website design (currently all pages are basic, black text on white background). |  |  |  |
| Responsible for Task: - Ryan (100%) |  |  |  |

| Task Title: Form Functionality | Task Initiation: 03/02/2011 | Orig. Due Date: 03/17/2011 | Status: DELAYED until 3/31/2011 |
| --- | --- | --- | --- |
| Description: Adding functionality to the forms created with WebStep. Functionality includes halting progress if required inputs are empty, also accepting only valid data types & ranges. |  |  |  |
| Responsible for Task: - Cyle (30%) - Chad (70%) |  |  |  |

| Task Title: Form Submit/Input (Basic) | Task Initiation: 03/23/2011 | Orig. Due Date: 03/29/2011 | Status: ON-TIME |
| --- | --- | --- | --- |
| Description: Having the forms create an output DAT file, and taking an archived file that will automatically fill the forms. |  |  |  |
| Responsible for Task: - Cyle (25%) - Chad (75%) |  |  |  |

### Upcoming Tasks: Planning

| Task Title: Finished Website | Who (%): - Undecided | Rough Due Date: 04/05/2011 |
| --- | --- | --- |
| Description: Fully functioning website. |  |  |

### Timeline check:

- Website Status: Forms (DELAYED)

- Website Status: SCREEN3 (DELAYED)

### Other Problems / Other Issues:

None