## Week 1
Date | [24 empty] | Unassigned
2022-01-10 | Timothy Giroux |  | tlg292@nau.edu |  |  |  | Kyle Steven Austria |  | kaa474@nau.edu |  |  |  | Gustavo Valencia |  | gmv43@nau.edu |  |  |  | Pengfei Liu |  | pl384@nau.edu |  |  |  | --
2022-01-17 | Task Name | Description & Expected Outcome | Start Date | Due Date | Actual Time (hr) | Progress | Task Name | Description & Expected Outcome | Start Date | Due Date | Actual Time (hr) | Progress | Task Name | Description & Expected Outcome | Start Date | Due Date | Actual Time (hr) | Progress | Task Name | Description & Expected Outcome | Start Date | Due Date | Actual Time (hr) | Progress | Task Name | Description & Expected Outcome | Start Date | Due Date | Actual Time (hr) | Progress
Done
1
2
3
4
0 | Actual Total Time: |  |  |  | 0 | hrs | Actual Total Time: |  |  |  | 0 | hrs | Actual Total Time: |  |  |  | 0 | hrs | Actual Total Time: |  |  |  | 0 | hrs | Actual Total Time: |  |  |  | 0 | hrs
Todo | Task Name | Description & Expected Outcome | Start Date | Due Date | Expected Time | Progress | Task Name | Description & Expected Outcome | Start Date | Due Date | Expected Time | Progress | Task Name | Description & Expected Outcome | Start Date | Due Date | Expected Time | Progress | Task Name | Description & Expected Outcome | Start Date | Due Date | Expected Time | Progress | Task Name | Description & Expected Outcome | Start Date | Due Date | Expected Time | Progress
1 | architecture | lead a team meeting to go over the full architecture, codebase, and other dev details for GeekSurvey |  |  | 1 |  | architecture | attend and participate in architecture meeting |  |  | 1 |  | architecture | attend and participate in architecture meeting |  |  | 1 |  | architecture | attend and participate in architecture meeting |  |  | 1
2 | contribute | make a code contribution for the User Account Creation sprint |  |  | 1 |  | contribute | make a code contribution for the User Account Creation sprint |  |  | 1 |  | contribute | make a code contribution for the User Account Creation sprint |  |  | 1 |  | contribute | make a code contribution for the User Account Creation sprint |  |  | 1
3
4
2 | Expected Total Time: |  |  |  | 2 | hrs | Expected Total Time: |  |  |  | 2 | hrs | Expected Total Time: |  |  |  | 2 | hrs | Expected Total Time: |  |  |  | 2 | hrs | Expected Total Time: |  |  |  | 0 | hrs
Upcoming | Task Name | Description & Expected Outcome | Start Date | Due Date | Expected Time | Progress | Task Name | Description & Expected Outcome | Start Date | Due Date | Expected Time | Progress | Task Name | Description & Expected Outcome | Start Date | Due Date | Expected Time | Progress | Task Name | Description & Expected Outcome | Start Date | Due Date | Expected Time | Progress | Task Name | Description & Expected Outcome | Start Date | Due Date | Expected Time | Progress
1
2
3
4
0 | Expected Total Time: |  |  |  | 0 | hrs | Expected Total Time: |  |  |  | 0 | hrs | Expected Total Time: |  |  |  | 0 | hrs | Expected Total Time: |  |  |  | 0 | hrs | Expected Total Time: |  |  |  | 0 | hrs
| Additional comments questions or concerns: | [5 empty] | Additional comments questions or concerns: | [5 empty] | Additional comments questions or concerns: | [5 empty] | Additional comments questions or concerns: | [5 empty] | Additional comments questions or concerns:
Current Major Deliverables:
| 1 | Communication Strategy Memo
| 2 | Design Document Draft
3
4
etc
Instructions:
| 1 | Every week your team should fill out the "Next Week" and "Upcoming" section together.
| 2 | You should fill in your respective "This Week" section as you finish your individual tasks.
| 3 | The unassigned section is mostly for upcoming tasks that the team has not delegated. If you have time and have not done many tasks this week, you might want to pick up an unassigned task.
| 4 | Record how long each task took in the time column. Actual time should be recorded when the task is finished (i.e. in the This Week section). Expected time should be recorded when the task is assigned (i.e. in the Next Week section).
| 5 | Times should be recorded in hrs. E.g. if a task took 1/2 an hour put 0.5, if a task takes 10 minutes put 0.17, ect.
| 6 | When adding a task right click last task row number and click "+ insert 1 row below"
Notes:
| 1 | Don't change previous weeks, google sheets has version history. I can see when and who changed a sheet.
| 2 | Don't inflate the time you spend on things. Worse than not investing enough time on the project, is appearing have to wasted time on something that shouldn't take that long.
| 3 | You should fill in your own tasks and review what others have gotten done.
| 4 | If there's ever a problem with a (the) task report(s), you can leave a comment or notify me.
| 5 | Everyone should complete at least one task a week. If one or two members appear to be doing all the work, your team should consider reevaluating your task delegation.

## Week 2
Date | [24 empty] | Unassigned
2022-01-17 | Timothy Giroux |  | tlg292@nau.edu |  |  |  | Kyle Steven Austria |  | kaa474@nau.edu |  |  |  | Gustavo Valencia |  | gmv43@nau.edu |  |  |  | Pengfei Liu |  | pl384@nau.edu |  |  |  | --
2022-01-23 | Task Name | Description & Expected Outcome | Start Date | Due Date | Actual Time (hr) | Progress | Task Name | Description & Expected Outcome | Start Date | Due Date | Actual Time (hr) | Progress | Task Name | Description & Expected Outcome | Start Date | Due Date | Actual Time (hr) | Progress | Task Name | Description & Expected Outcome | Start Date | Due Date | Actual Time (hr) | Progress | Task Name | Description & Expected Outcome | Start Date | Due Date | Actual Time (hr) | Progress
Done
1 | Architecture | Lead a team meeting to go over the full architecture, codebase, and other dev details for GeekSurvey | 2022-01-10 | 2022-01-17 | 1 | 100% | Architecture | Attend and participate in architecture meeting | 2022-01-10 | 2022-01-17 | 1 | 100% | Architecture | Attend and participate in architecture meeting | 2022-01-10 | 2022-01-17 | 1 | 100% | Architecture | Attend and participate in architecture meeting | 2022-01-10 | 2022-01-17 | 1 | 100%
2 | Contribute | Make a code contribution for the User Account Creation sprint | 2022-01-10 | 2022-01-17 | 2 | 100% | Contribute | Make a code contribution for the User Account Creation sprint | 2022-01-10 | 2022-01-17 | 2 | 100% | Contribute | Make a code contribution for the User Account Creation sprint | 2022-01-10 | 2022-01-17 | 2 | 100% | Contribute | Make a code contribution for the User Account Creation sprint | 2022-01-10 | 2022-01-17 | 2 | 100%
3
4
3 | Actual Total Time: |  |  |  | 3 | hrs | Actual Total Time: |  |  |  | 3 | hrs | Actual Total Time: |  |  |  | 3 | hrs | Actual Total Time: |  |  |  | 3 | hrs | Actual Total Time: |  |  |  | 0 | hrs
Todo | Task Name | Description & Expected Outcome | Start Date | Due Date | Expected Time | Progress | Task Name | Description & Expected Outcome | Start Date | Due Date | Expected Time | Progress | Task Name | Description & Expected Outcome | Start Date | Due Date | Expected Time | Progress | Task Name | Description & Expected Outcome | Start Date | Due Date | Expected Time | Progress | Task Name | Description & Expected Outcome | Start Date | Due Date | Expected Time | Progress
1 | General Meetings | Contribute to team planning at meetings | 2022-01-17 | 2022-01-24 | 1 |  | General Meetings | Contribute to team planning at meetings | 2022-01-17 | 2022-01-24 | 1 | 100% | General Meetings | Contribute to team planning at meetings | 2022-01-17 | 2022-01-24 | 1 | 100% | General Meetings | Contribute to team planning at meetings | 2022-01-17 | 2022-01-24 | 1
2 | Programming | Complete 3.1 user story | 2022-01-17 | 2022-01-24 | 2 |  | Programming | Complete 2.4.4 user story | 2022-01-17 | 2022-01-24 | 2 | 100% | Programming | Complete 2.4.2 and 2.4.5 user stories | 2022-01-17 | 2022-01-24 | 2 | 100% | Programming | Complete 2.4.1 and 2.4.3 user stories | 2022-01-17 | 2022-01-24 | 2
3 | Design Doc Draft | Refine implementation overview and architecture overview | 2022-01-17 | 2022-01-24 | 2 |  | Design Doc Draft | Update introduction and write conclusion | 2022-01-17 | 2022-01-24 | 2 | 100% | Design Doc Draft | 4.1 Templates and help with 4.2 and 4.3 | 2022-01-17 | 2022-01-24 | 2 | 100% | Design Doc Draft | 4.2 Accounts and 4.3 Studies | 2022-01-17 | 2022-01-24 | 2
4
5 | Expected Total Time: |  |  |  | 5 | hrs | Expected Total Time: |  |  |  | 5 | hrs | Expected Total Time: |  |  |  | 5 | hrs | Expected Total Time: |  |  |  | 5 | hrs | Expected Total Time: |  |  |  | 0 | hrs
Upcoming | Task Name | Description & Expected Outcome | Start Date | Due Date | Expected Time | Progress | Task Name | Description & Expected Outcome | Start Date | Due Date | Expected Time | Progress | Task Name | Description & Expected Outcome | Start Date | Due Date | Expected Time | Progress | Task Name | Description & Expected Outcome | Start Date | Due Date | Expected Time | Progress | Task Name | Description & Expected Outcome | Start Date | Due Date | Expected Time | Progress
1 | General Meetings | Contribute to team planning at meetings | 2022-01-24 | 2022-01-31 | 1 |  | General Meetings | Contribute to team planning at meetings | 2022-01-24 | 2022-01-31 | 1 |  | General Meetings | Contribute to team planning at meetings | 2022-01-24 | 2022-01-31 | 1 |  | General Meetings | Contribute to team planning at meetings | 2022-01-24 | 2022-01-31 | 1
2 | Programming | Contribute to GeekSurvey codebase | 2022-01-24 | 2022-01-31 | 2 |  | Programming | Contribute to GeekSurvey codebase | 2022-01-24 | 2022-01-31 | 4 |  | Programming | Contribute to GeekSurvey codebase | 2022-01-24 | 2022-01-31 | 2 |  | Programming | Contribute to GeekSurvey codebase | 2022-01-24 | 2022-01-31 | 4
3 | Design Doc Draft | Work on Design Document draft | 2022-01-24 | 2022-01-31 | 2 | [7 empty] | Design Doc Draft | Work on Design Document draft | 2022-01-24 | 2022-01-31 | 2
4
5 | Expected Total Time: |  |  |  | 5 | hrs | Expected Total Time: |  |  |  | 5 | hrs | Expected Total Time: |  |  |  | 5 | hrs | Expected Total Time: |  |  |  | 5 | hrs | Expected Total Time: |  |  |  | 0 | hrs
| Additional comments questions or concerns: | [5 empty] | Additional comments questions or concerns: | [5 empty] | Additional comments questions or concerns: | [5 empty] | Additional comments questions or concerns: | [5 empty] | Additional comments questions or concerns:
This task report has not been properly completed. Tasks should be descriptive and distinct to record who completed what fuction/feature of the project or which section/part of a document.
Current Major Deliverables:
| 1 | Design Document Draft
2
3
4
etc
Instructions:
| 1 | Every week your team should fill out the "Next Week" and "Upcoming" section together.
| 2 | You should fill in your respective "This Week" section as you finish your individual tasks.
| 3 | The unassigned section is mostly for upcoming tasks that the team has not delegated. If you have time and have not done many tasks this week, you might want to pick up an unassigned task.
| 4 | Record how long each task took in the time column. Actual time should be recorded when the task is finished (i.e. in the This Week section). Expected time should be recorded when the task is assigned (i.e. in the Next Week section).
| 5 | Times should be recorded in hrs. E.g. if a task took 1/2 an hour put 0.5, if a task takes 10 minutes put 0.17, ect.
| 6 | When adding a task right click last task row number and click "+ insert 1 row below"
Notes:
| 1 | Don't change previous weeks, google sheets has version history. I can see when and who changed a sheet.
| 2 | Don't inflate the time you spend on things. Worse than not investing enough time on the project, is appearing have to wasted time on something that shouldn't take that long.
| 3 | You should fill in your own tasks and review what others have gotten done.
| 4 | If there's ever a problem with a (the) task report(s), you can leave a comment or notify me.
| 5 | Everyone should complete at least one task a week. If one or two members appear to be doing all the work, your team should consider reevaluating your task delegation.

## Week 3
Date | [24 empty] | Unassigned
2022-01-24 | Timothy Giroux |  | tlg292@nau.edu |  |  |  | Kyle Steven Austria |  | kaa474@nau.edu |  |  |  | Gustavo Valencia |  | gmv43@nau.edu |  |  |  | Pengfei Liu |  | pl384@nau.edu |  |  |  | --
2022-01-30 | Task Name | Description & Expected Outcome | Start Date | Due Date | Actual Time (hr) | Progress | Task Name | Description & Expected Outcome | Start Date | Due Date | Actual Time (hr) | Progress | Task Name | Description & Expected Outcome | Start Date | Due Date | Actual Time (hr) | Progress | Task Name | Description & Expected Outcome | Start Date | Due Date | Actual Time (hr) | Progress | Task Name | Description & Expected Outcome | Start Date | Due Date | Actual Time (hr) | Progress
Done
1 | General Meetings | Contribute to team planning at meetings | 2022-01-17 | 2022-01-24 | 1 | 100% | General Meetings | Contribute to team planning at meetings | 2022-01-17 | 2022-01-24 | 1 | 100% | General Meetings | Contribute to team planning at meetings | 2022-01-17 | 2022-01-24 | 1 | 100% | General Meetings | Contribute to team planning at meetings | 2022-01-17 | 2022-01-24 | 1 | 100%
2 | Programming | Complete 3.1 user story | 2022-01-17 | 2022-01-24 | 3 | 100% | Programming | Complete 2.4.4 user story | 2022-01-17 | 2022-01-24 | 1 | 100% | Programming | Complete 2.4.2 and 2.4.5 user stories | 2022-01-17 | 2022-01-24 | 1.5 | 100% | Programming | Complete 2.4.1 and 2.4.3 user stories | 2022-01-17 | 2022-01-24 | 2.5 | 100%
3 | Design Doc Draft | Refine implementation overview and architecture overview | 2022-01-17 | 2022-01-24 | 2 | 100% | Design Doc Draft | Update intro and write conclusion | 2022-01-17 | 2022-01-24 | 2 | 100% | Design Doc Draft | 4.1 Templates and help with 4.2 and 4.3 | 2022-01-17 | 2022-01-24 | 3.5 | 100% | Design Doc Draft | 4.2 Accounts and 4.3 Studies | 2022-01-17 | 2022-01-24 | 4 | 100%
4
6 | Actual Total Time: |  |  |  | 6 | hrs | Actual Total Time: |  |  |  | 4 | hrs | Actual Total Time: |  |  |  | 6 | hrs | Actual Total Time: |  |  |  | 7.5 | hrs | Actual Total Time: |  |  |  | 0 | hrs
Todo | Task Name | Description & Expected Outcome | Start Date | Due Date | Expected Time | Progress | Task Name | Description & Expected Outcome | Start Date | Due Date | Expected Time | Progress | Task Name | Description & Expected Outcome | Start Date | Due Date | Expected Time | Progress | Task Name | Description & Expected Outcome | Start Date | Due Date | Expected Time | Progress | Task Name | Description & Expected Outcome | Start Date | Due Date | Expected Time | Progress
1 | General Meetings | Contribute to team planning at meetings | 2022-01-24 | 2022-02-02 | 1 |  | General Meetings | Contribute to team planning at meetings | 2022-01-24 | 2022-02-02 | 1 | 100% | General Meetings | Contribute to team planning at meetings | 2022-01-24 | 2022-02-02 | 1 | 100% | General Meetings | Contribute to team planning at meetings | 2022-01-24 | 2022-02-02 | 1 | 100%
2 | Programming | Complete 3.2, 3.3, 3.7 user stories | 2022-01-24 | 2022-02-02 | 4 |  | Programming | Complete 3.1 and 3.2.1 user stories | 2022-01-24 | 2022-02-02 | 4 | 100% | Programming | Complete 3.10, 3.11 user stories | 2022-01-24 | 2022-02-02 | 4 | 100% | Programming | Complete 3.4, 3.5 user stories | 2022-01-24 | 2022-02-02 | 3 | 100%
3 | Design Doc Draft | Complete implementation plan, implementation overview, and architecture overview | 2022-01-24 | 2022-02-02 | 3 |  | Design Doc Draft | Finalize introduction and write conclusion | 2022-01-24 | 2022-02-02 | 2 | 100% | Design Doc Draft | Finalize 4.1 Templates and help finalize 4.2 and 4.3 | 2022-01-24 | 2022-02-02 | 2 | 100% | Design Doc Draft | Finalize 4.2 Accounts and 4.3 Studies | 2022-01-24 | 2022-02-02 | 4 | 100%
4 | [12 empty] | Gantt Chart Redesign | Rebuild team Gantt Chart to include sprint tasks and class assignments | 2022-01-24 | 2022-02-02 | 2 | 100%
5 | [12 empty] | Create and Updated Repo Documentation | Updated README.md and created the CONTRIBUTING.md, CODE_OF_CONDUCT.md, and LICENSE files on the repository to document the project and rules for contributing and respository conduct. | 2022-01-24 | 2022-02-02 | 1 | 100%
8 | Expected Total Time: |  |  |  | 8 | hrs | Expected Total Time: |  |  |  | 7 | hrs | Expected Total Time: |  |  |  | 10 | hrs | Expected Total Time: |  |  |  | 8 | hrs | Expected Total Time: |  |  |  | 0 | hrs
Upcoming | Task Name | Description & Expected Outcome | Start Date | Due Date | Expected Time | Progress | Task Name | Description & Expected Outcome | Start Date | Due Date | Expected Time | Progress | Task Name | Description & Expected Outcome | Start Date | Due Date | Expected Time | Progress | Task Name | Description & Expected Outcome | Start Date | Due Date | Expected Time | Progress | Task Name | Description & Expected Outcome | Start Date | Due Date | Expected Time | Progress
1 | General Meetings | Contribute to team planning at meetings | 2022-02-02 | 2022-02-09 | 1 |  | General Meetings | Contribute to team planning at meetings | 2022-02-02 | 2022-02-09 | 1 |  | General Meetings | Contribute to team planning at meetings | 2022-02-02 | 2022-02-09 | 1 |  | General Meetings | Contribute to team planning at meetings | 2022-02-02 | 2022-02-09 | 1
2 | Programming | Contribute to GeekSurvey codebase | 2022-02-02 | 2022-02-09 | 2 |  | Programming | Contribute to GeekSurvey codebase | 2022-02-02 | 2022-02-09 | 2 |  | Programming | Contribute to GeekSurvey codebase | 2022-02-02 | 2022-02-09 | 2 |  | Programming | Contribute to GeekSurvey codebase | 2022-02-02 | 2022-02-09 | 2
3
4
3 | Expected Total Time: |  |  |  | 3 | hrs | Expected Total Time: |  |  |  | 3 | hrs | Expected Total Time: |  |  |  | 3 | hrs | Expected Total Time: |  |  |  | 3 | hrs | Expected Total Time: |  |  |  | 0 | hrs
| Additional comments questions or concerns: | [5 empty] | Additional comments questions or concerns: | [5 empty] | Additional comments questions or concerns: | [5 empty] | Additional comments questions or concerns: | [5 empty] | Additional comments questions or concerns:
Discuss moving our meeting time? It's difficult for us to have TR ready (and of good quality) first thing on Monday mornings
Current Major Deliverables:
| 1 | Design Document Draft | [5 empty] | Gantt Chart | [5 empty] | Commit History
| 2 | [6 empty] | https://docs.google.com/spreadsheets/d/1f7RZwt7m7hIaU-dNwV-3LjXIOoSCrCGt7WCVYpEjwIY/edit?usp=sharing | [5 empty] | https://github.com/NAU-SuperGeeks/geeksurvey/graphs/contributors
3
4
etc
Instructions:
| 1 | Every week your team should fill out the "Next Week" and "Upcoming" section together.
| 2 | You should fill in your respective "This Week" section as you finish your individual tasks.
| 3 | The unassigned section is mostly for upcoming tasks that the team has not delegated. If you have time and have not done many tasks this week, you might want to pick up an unassigned task.
| 4 | Record how long each task took in the time column. Actual time should be recorded when the task is finished (i.e. in the This Week section). Expected time should be recorded when the task is assigned (i.e. in the Next Week section).
| 5 | Times should be recorded in hrs. E.g. if a task took 1/2 an hour put 0.5, if a task takes 10 minutes put 0.17, ect.
| 6 | When adding a task right click last task row number and click "+ insert 1 row below"
Notes:
| 1 | Don't change previous weeks, google sheets has version history. I can see when and who changed a sheet.
| 2 | Don't inflate the time you spend on things. Worse than not investing enough time on the project, is appearing have to wasted time on something that shouldn't take that long.
| 3 | You should fill in your own tasks and review what others have gotten done.
| 4 | If there's ever a problem with a (the) task report(s), you can leave a comment or notify me.
| 5 | Everyone should complete at least one task a week. If one or two members appear to be doing all the work, your team should consider reevaluating your task delegation.

## Week 4
Date | [24 empty] | Unassigned
2022-02-02 | Timothy Giroux |  | tlg292@nau.edu |  |  |  | Kyle Steven Austria |  | kaa474@nau.edu |  |  |  | Gustavo Valencia |  | gmv43@nau.edu |  |  |  | Pengfei Liu |  | pl384@nau.edu |  |  |  | --
2022-02-09 | Task Name | Description & Expected Outcome | Start Date | Due Date | Actual Time (hr) | Progress | Task Name | Description & Expected Outcome | Start Date | Due Date | Actual Time (hr) | Progress | Task Name | Description & Expected Outcome | Start Date | Due Date | Actual Time (hr) | Progress | Task Name | Description & Expected Outcome | Start Date | Due Date | Actual Time (hr) | Progress | Task Name | Description & Expected Outcome | Start Date | Due Date | Actual Time (hr) | Progress
Done
1 | General Meetings | Contribute to team planning at meetings | 2022-01-24 | 2022-02-02 | 1 | 100% | General Meetings | Contribute to team planning at meetings | 2022-01-24 | 2022-02-02 | 1 | 100% | General Meetings | Contribute to team planning at meetings | 2022-01-24 | 2022-02-02 | 1 | 100% | General Meetings | Contribute to team planning at meetings | 2022-01-24 | 2022-02-02 | 1 | 100%
2 | Programming | Complete 4.1, 4.2 user stories | 2022-01-24 | 2022-02-02 | 4 | 100% | Programming | Complete 3.1 and 3.2.1 user stories | 2022-01-24 | 2022-02-02 | 4 | 100% | Programming | Complete 3.10, 3.11 user stories | 2022-01-24 | 2022-02-02 | 2 | 100% | Programming | Complete 3.4, 3.5 user stories | 2022-01-24 | 2022-02-02 | 3 | 100%
3 | Design Doc Draft | Complete implementation plan, implementation overview, and architecture overview | 2022-01-24 | 2022-02-02 | 3 | 100% | Design Doc Draft | Finalize introduction and conclusion, draft implementation plan | 2022-01-24 | 2022-02-02 | 3 | 100% | Design Doc Draft | Finalize 4.1 Templates and help finalize 4.2 and 4.3 | 2022-01-24 | 2022-02-02 | 5 | 100% | Design Doc Draft | Finalize 4.2 Accounts and 4.3 Studies | 2022-01-24 | 2022-02-02 | 4 | 100%
4 | [12 empty] | Gantt Chart Redesign | Rebuild team Gantt Chart to include sprint tasks and class assignments | 2022-01-24 | 2022-02-02 | 2 | 100%
5 | [12 empty] | Create and Updated Repo Documentation | Updated README.md and created the CONTRIBUTING.md, CODE_OF_CONDUCT.md, and LICENSE files on the repository to document the project and rules for contributing and respository conduct. | 2022-01-24 | 2022-02-02 | 1.5 | 100%
8 | Actual Total Time: |  |  |  | 8 | hrs | Actual Total Time: |  |  |  | 8 | hrs | Actual Total Time: |  |  |  | 11.5 | hrs | Actual Total Time: |  |  |  | 8 | hrs | Actual Total Time: |  |  |  | 0 | hrs
Todo | Task Name | Description & Expected Outcome | Start Date | Due Date | Expected Time | Progress | Task Name | Description & Expected Outcome | Start Date | Due Date | Expected Time | Progress | Task Name | Description & Expected Outcome | Start Date | Due Date | Expected Time | Progress | Task Name | Description & Expected Outcome | Start Date | Due Date | Expected Time | Progress | Task Name | Description & Expected Outcome | Start Date | Due Date | Expected Time | Progress
1 | General Meetings | Contribute to team planning at meetings | 2022-02-02 | 2022-02-09 | 1 | 100% | General Meetings | Contribute to team planning at meetings | 2022-02-02 | 2022-02-09 | 1 | 100% | General Meetings | Contribute to team planning at meetings | 2022-02-02 | 2022-02-09 | 1 | 100% | General Meetings | Contribute to team planning at meetings | 2022-02-02 | 2022-02-09 | 1 | 100%
2 | Programming | Complete user stories 3.3, 3.7, 5.2 | 2022-02-02 | 2022-02-09 | 4 | 100% | Programming | Complete user story 3.3 | 2022-02-02 | 2022-02-09 | 4 | 100% | Programming | Add client-requested features to the user profile | 2022-02-02 | 2022-02-09 | 4 | 100% | Programming | Complete user stories 3.8, 3.9, 5.2 | 2022-02-02 | 2022-02-09 | 4 | 100%
3 | Design Doc | Review feedback and make changes to respective sections | 2022-02-02 | 2022-02-09 | 2 | 100% | Design Doc | Review feedback and make changes to respective sections | 2022-02-02 | 2022-02-09 | 2 | 100% | Design Doc | Review feedback and make changes to respective sections | 2022-02-02 | 2022-02-09 | 2 | 100% | Design Doc | Review feedback and make changes to respective sections | 2022-02-02 | 2022-02-09 | 2 | 100%
4 | Investigate NAUITS hosting problems | Either figure out a fix for hosting geeksurvey under a sub URL or abandon this hosting solution | 2022-02-02 | 2022-02-09 | 2 | 100% | Payment Processing Research | Research ways to implement a payment processing system into a Django application using PayPal and document findings in Google Doc on shared drive | 2022-02-02 | 2022-02-09 | 1 | 100% | Payment Processing Research | Research ways to implement a payment processing system into a Django application using PayPal and document findings in Google Doc on shared drive | 2022-02-02 | 2022-02-09 | 1 | 100%
9 | Expected Total Time: |  |  |  | 9 | hrs | Expected Total Time: |  |  |  | 8 | hrs | Expected Total Time: |  |  |  | 8 | hrs | Expected Total Time: |  |  |  | 7 | hrs | Expected Total Time: |  |  |  | 0 | hrs
Upcoming | Task Name | Description & Expected Outcome | Start Date | Due Date | Expected Time | Progress | Task Name | Description & Expected Outcome | Start Date | Due Date | Expected Time | Progress | Task Name | Description & Expected Outcome | Start Date | Due Date | Expected Time | Progress | Task Name | Description & Expected Outcome | Start Date | Due Date | Expected Time | Progress | Task Name | Description & Expected Outcome | Start Date | Due Date | Expected Time | Progress
1 | General Meetings | Contribute to team planning at meetings | 2022-02-09 | 2022-02-16 | 1 |  | General Meeting | Contribute to team planning at meetings | 2022-02-09 | 2022-02-16 | 1 |  | General Meetings | Contribute to team planning at meetings | 2022-02-09 | 2022-02-16 | 1 |  | General Meetings | Contribute to team planning at meetings | 2022-02-09 | 2022-02-16 | 1
2 | Programming | Contribute to GeekSurvey codebase | 2022-02-09 | 2022-02-16 | 2 |  | Programming | Contribute to GeekSurvey codebase | 2022-02-09 | 2022-02-16 | 2 |  | Programming | Contribute to GeekSurvey codebase | 2022-02-09 | 2022-02-16 | 2 |  | Programming | Contribute to GeekSurvey codebase | 2022-02-09 | 2022-02-16 | 2
3
4
3 | Expected Total Time: |  |  |  | 3 | hrs | Expected Total Time: |  |  |  | 3 | hrs | Expected Total Time: |  |  |  | 3 | hrs | Expected Total Time: |  |  |  | 3 | hrs | Expected Total Time: |  |  |  | 0 | hrs
| Additional comments questions or concerns: | [5 empty] | Additional comments questions or concerns: | [5 empty] | Additional comments questions or concerns: | [5 empty] | Additional comments questions or concerns: | [5 empty] | Additional comments questions or concerns:
Current Major Deliverables:
| 1 | Design Document Final | [5 empty] | Gantt Chart | [5 empty] | Commit History
| 2 | [6 empty] | https://docs.google.com/spreadsheets/d/1f7RZwt7m7hIaU-dNwV-3LjXIOoSCrCGt7WCVYpEjwIY/edit?usp=sharing | [5 empty] | https://github.com/NAU-SuperGeeks/geeksurvey/graphs/contributors
3
4
etc
Instructions:
| 1 | Every week your team should fill out the "Next Week" and "Upcoming" section together.
| 2 | You should fill in your respective "This Week" section as you finish your individual tasks.
| 3 | The unassigned section is mostly for upcoming tasks that the team has not delegated. If you have time and have not done many tasks this week, you might want to pick up an unassigned task.
| 4 | Record how long each task took in the time column. Actual time should be recorded when the task is finished (i.e. in the This Week section). Expected time should be recorded when the task is assigned (i.e. in the Next Week section).
| 5 | Times should be recorded in hrs. E.g. if a task took 1/2 an hour put 0.5, if a task takes 10 minutes put 0.17, ect.
| 6 | When adding a task right click last task row number and click "+ insert 1 row below"
Notes:
| 1 | Don't change previous weeks, google sheets has version history. I can see when and who changed a sheet.
| 2 | Don't inflate the time you spend on things. Worse than not investing enough time on the project, is appearing have to wasted time on something that shouldn't take that long.
| 3 | You should fill in your own tasks and review what others have gotten done.
| 4 | If there's ever a problem with a (the) task report(s), you can leave a comment or notify me.
| 5 | Everyone should complete at least one task a week. If one or two members appear to be doing all the work, your team should consider reevaluating your task delegation.

## Week 5
Date | [24 empty] | Unassigned
2022-02-09 | Timothy Giroux |  | tlg292@nau.edu |  |  |  | Kyle Steven Austria |  | kaa474@nau.edu |  |  |  | Gustavo Valencia |  | gmv43@nau.edu |  |  |  | Pengfei Liu |  | pl384@nau.edu |  |  |  | --
2022-02-16 | Task Name | Description & Expected Outcome | Start Date | Due Date | Actual Time (hr) | Progress | Task Name | Description & Expected Outcome | Start Date | Due Date | Actual Time (hr) | Progress | Task Name | Description & Expected Outcome | Start Date | Due Date | Actual Time (hr) | Progress | Task Name | Description & Expected Outcome | Start Date | Due Date | Actual Time (hr) | Progress | Task Name | Description & Expected Outcome | Start Date | Due Date | Actual Time (hr) | Progress
Done
1 | General Meetings | Contribute to team planning at meetings | 2022-02-02 | 2022-02-09 | 1 | 100% | General Meetings | Contribute to team planning at meetings | 2022-02-02 | 2022-02-09 | 1 | 100% | General Meetings | Contribute to team planning at meetings | 2022-02-02 | 2022-02-09 | 1 | 100% | General Meetings | Contribute to team planning at meetings | 2022-02-02 | 2022-02-09 | 1 | 100%
2 | Programming | Complete user stories 3.3, 3.7, 5.2 | 2022-02-02 | 2022-02-09 | 4 | 100% | Programming | Complete user story 3.3 | 2022-02-02 | 2022-02-09 | 4 | 100% | Programming | Add client-requested features to the user profile | 2022-02-02 | 2022-02-09 | 2.5 | 100% | Programming | Complete user stories 3.8, 3.9, 5.2 | 2022-02-02 | 2022-02-09 | 4 | 100%
3 | Design Doc | Review feedback and make changes to respective sections | 2022-02-02 | 2022-02-09 | 2 | 100% | Design Doc | Review feedback and make changes to respective sections | 2022-02-02 | 2022-02-09 | 2 | 100% | Design Doc | Review feedback and make changes to respective sections | 2022-02-02 | 2022-02-09 | 2.5 | 100% | Design Doc | Review feedback and make changes to respective sections | 2022-02-02 | 2022-02-09 | 2 | 100%
4 | Investigate NAUITS hosting problems | Either figure out a fix for hosting geeksurvey under a sub URL or abandon this hosting solution | 2022-02-02 | 2022-02-09 | 2 | 100% | Payment Processing Research | Research ways to implement a payment processing system into a Django application using PayPal and document findings in Google Doc on shared drive | 2022-02-02 | 2022-02-09 | 1 | 100% | Payment Processing Research | Research ways to implement a payment processing system into a Django application using PayPal and document findings in Google Doc on shared drive | 2022-02-02 | 2022-02-09 | 1 | 100%
9 | Actual Total Time: |  |  |  | 9 | hrs | Actual Total Time: |  |  |  | 8 | hrs | Actual Total Time: |  |  |  | 7 | hrs | Actual Total Time: |  |  |  | 7 | hrs | Actual Total Time: |  |  |  | 0 | hrs
Todo | Task Name | Description & Expected Outcome | Start Date | Due Date | Expected Time | Progress | Task Name | Description & Expected Outcome | Start Date | Due Date | Expected Time | Progress | Task Name | Description & Expected Outcome | Start Date | Due Date | Expected Time | Progress | Task Name | Description & Expected Outcome | Start Date | Due Date | Expected Time | Progress | Task Name | Description & Expected Outcome | Start Date | Due Date | Expected Time | Progress
1 | General Meetings | Contribute to team planning at meetings | 2022-02-09 | 2022-02-16 | 1 | 100% | General Meetings | Contribute to team planning at meetings | 2022-02-09 | 2022-02-16 | 1 | 100% | General Meetings | Contribute to team planning at meetings | 2022-02-09 | 2022-02-16 | 1 | 100% | General Meetings | Contribute to team planning at meetings | 2022-02-09 | 2022-02-16 | 1 | 100%
2 | Programming | Complete user story 4.1.1, 4.3 | 2022-02-09 | 2022-02-16 | 5 | 50% | Programming | Complete user story 4.1.1, 4.1.2 | 2022-02-09 | 2022-02-16 | 5 | 100% | Programming | Add/refine additional client-requested features to the user profile | 2022-02-09 | 2022-02-16 | 2 | 100% | Programming | Complete user story 4.1.1, 4.3.1 | 2022-02-09 | 2022-02-16 | 5 | 100%
3 | UGRADS Abstract | Complete draft of UGRADS abstract | 2022-02-09 | 2022-02-16 | 1 | 100% | [6 empty] | Django-Bootstrap Research | Research Django-Bootstrap for updating templating and UI on GeekSurvey as requested by clients | 2022-02-09 | 2022-02-16 | 3 | 100%
4
7 | Expected Total Time: |  |  |  | 7 | hrs | Expected Total Time: |  |  |  | 6 | hrs | Expected Total Time: |  |  |  | 6 | hrs | Expected Total Time: |  |  |  | 6 | hrs | Expected Total Time: |  |  |  | 0 | hrs
Upcoming | Task Name | Description & Expected Outcome | Start Date | Due Date | Expected Time | Progress | Task Name | Description & Expected Outcome | Start Date | Due Date | Expected Time | Progress | Task Name | Description & Expected Outcome | Start Date | Due Date | Expected Time | Progress | Task Name | Description & Expected Outcome | Start Date | Due Date | Expected Time | Progress | Task Name | Description & Expected Outcome | Start Date | Due Date | Expected Time | Progress
1 | General Meetings | Contribute to team planning at meetings | 2022-02-16 | 2022-02-23 | 1 |  | General Meetings | Contribute to team planning at meetings | 2022-02-16 | 2022-02-23 | 1 |  | General Meetings | Contribute to team planning at meetings | 2022-02-16 | 2022-02-23 | 1 |  | General Meetings | Contribute to team planning at meetings | 2022-02-16 | 2022-02-23 | 1
2 | Programming | Contribute to GeekSurvey codebase | 2022-02-16 | 2022-02-23 | 2 |  | Programming | Contribute to GeekSurvey codebase | 2022-02-16 | 2022-02-23 | 2 |  | Programming | Contribute to GeekSurvey codebase | 2022-02-16 | 2022-02-23 | 2 |  | Programming | Contribute to GeekSurvey codebase | 2022-02-16 | 2022-02-23 | 2
3
4
3 | Expected Total Time: |  |  |  | 3 | hrs | Expected Total Time: |  |  |  | 3 | hrs | Expected Total Time: |  |  |  | 3 | hrs | Expected Total Time: |  |  |  | 3 | hrs | Expected Total Time: |  |  |  | 0 | hrs
| Additional comments questions or concerns: | [5 empty] | Additional comments questions or concerns: | [5 empty] | Additional comments questions or concerns: | [5 empty] | Additional comments questions or concerns: | [5 empty] | Additional comments questions or concerns:
UGRADS Registration
Current Major Deliverables:
| 1 | [6 empty] | Gantt Chart | [5 empty] | Commit History
| 2 | [6 empty] | https://docs.google.com/spreadsheets/d/1f7RZwt7m7hIaU-dNwV-3LjXIOoSCrCGt7WCVYpEjwIY/edit?usp=sharing | [5 empty] | https://github.com/NAU-SuperGeeks/geeksurvey/graphs/contributors
3
4
etc
Instructions:
| 1 | Every week your team should fill out the "Next Week" and "Upcoming" section together.
| 2 | You should fill in your respective "This Week" section as you finish your individual tasks.
| 3 | The unassigned section is mostly for upcoming tasks that the team has not delegated. If you have time and have not done many tasks this week, you might want to pick up an unassigned task.
| 4 | Record how long each task took in the time column. Actual time should be recorded when the task is finished (i.e. in the This Week section). Expected time should be recorded when the task is assigned (i.e. in the Next Week section).
| 5 | Times should be recorded in hrs. E.g. if a task took 1/2 an hour put 0.5, if a task takes 10 minutes put 0.17, ect.
| 6 | When adding a task right click last task row number and click "+ insert 1 row below"
Notes:
| 1 | Don't change previous weeks, google sheets has version history. I can see when and who changed a sheet.
| 2 | Don't inflate the time you spend on things. Worse than not investing enough time on the project, is appearing have to wasted time on something that shouldn't take that long.
| 3 | You should fill in your own tasks and review what others have gotten done.
| 4 | If there's ever a problem with a (the) task report(s), you can leave a comment or notify me.
| 5 | Everyone should complete at least one task a week. If one or two members appear to be doing all the work, your team should consider reevaluating your task delegation.

## Week 6
Date | [24 empty] | Unassigned
2022-02-16 | Timothy Giroux |  | tlg292@nau.edu |  |  |  | Kyle Steven Austria |  | kaa474@nau.edu |  |  |  | Gustavo Valencia |  | gmv43@nau.edu |  |  |  | Pengfei Liu |  | pl384@nau.edu |  |  |  | --
2022-02-23 | Task Name | Description & Expected Outcome | Start Date | Due Date | Actual Time (hr) | Progress | Task Name | Description & Expected Outcome | Start Date | Due Date | Actual Time (hr) | Progress | Task Name | Description & Expected Outcome | Start Date | Due Date | Actual Time (hr) | Progress | Task Name | Description & Expected Outcome | Start Date | Due Date | Actual Time (hr) | Progress | Task Name | Description & Expected Outcome | Start Date | Due Date | Actual Time (hr) | Progress
Done
1 | General Meetings | Contribute to team planning at meetings | 2022-02-09 | 2022-02-16 | 1 | 100% | General Meetings | Contribute to team planning at meetings | 2022-02-09 | 2022-02-16 | 1 | 100% | General Meetings | Contribute to team planning at meetings | 2022-02-09 | 2022-02-16 | 1 | 100% | General Meetings | Contribute to team planning at meetings | 2022-02-09 | 2022-02-16 | 1 | 100%
2 | Programming | Complete user story 4.1.1, 4.3 | 2022-02-09 | 2022-02-16 | 5 | 50% | Programming | Complete user story 4.1.1, 4.1.2 | 2022-02-09 | 2022-02-16 | 4 | 100% | Programming | Add/refine additional client-requested features to the user profile | 2022-02-09 | 2022-02-16 | 2 | 100% | Programming | Complete user story 4.1.1, 4.3.1 | 2022-02-09 | 2022-02-16 | 5 | 50%
3 | UGRADS Abstract | Complete draft of UGRADS abstract | 2022-02-09 | 2022-02-16 | 1 | 100% | [6 empty] | Django-Bootstrap Research | Research Django-Bootstrap for updating templating and UI on GeekSurvey as requested by clients | 2022-02-09 | 2022-02-16 | 3 | 100%
4
7 | Actual Total Time: |  |  |  | 7 | hrs | Actual Total Time: |  |  |  | 5 | hrs | Actual Total Time: |  |  |  | 6 | hrs | Actual Total Time: |  |  |  | 6 | hrs | Actual Total Time: |  |  |  | 0 | hrs
Todo | Task Name | Description & Expected Outcome | Start Date | Due Date | Expected Time | Progress | Task Name | Description & Expected Outcome | Start Date | Due Date | Expected Time | Progress | Task Name | Description & Expected Outcome | Start Date | Due Date | Expected Time | Progress | Task Name | Description & Expected Outcome | Start Date | Due Date | Expected Time | Progress | Task Name | Description & Expected Outcome | Start Date | Due Date | Expected Time | Progress
1 | General Meetings | Contribute to team planning at meetings | 2022-02-16 | 2022-02-23 | 2 | 100% | General Meetings | Contribute to team planning at meetings | 2022-02-16 | 2022-02-23 | 1 | 100% | General Meetings | Contribute to team planning at meetings | 2022-02-16 | 2022-02-23 | 1 | 100% | General Meetings | Contribute to team planning at meetings | 2022-02-16 | 2022-02-23 | 1 | 100%
2 | Programming | Continue adding and refining enrollment criteria as requested by clients and start work on user stories 7.1 and 7.6 | 2022-02-16 | 2022-02-23 | 5 | 100% | Programming | Start work on user stories 7.1 and 7.6 | 2022-02-16 | 2022-02-23 | 5 | 100% | Programming | Start work on UI overhaul | 2022-02-16 | 2022-02-23 | 6 | 100% | Programming | Continue work on user stories 4.3 and 4.3.1 | 2022-02-16 | 2022-02-23 | 3 | 100%
3 | Revise UGRADS abstract | Address feedback from Felicity | 2022-02-16 | 2022-02-23 | 1 | 100%
4
8 | Expected Total Time: |  |  |  | 8 | hrs | Expected Total Time: |  |  |  | 6 | hrs | Expected Total Time: |  |  |  | 7 | hrs | Expected Total Time: |  |  |  | 4 | hrs | Expected Total Time: |  |  |  | 0 | hrs
Upcoming | Task Name | Description & Expected Outcome | Start Date | Due Date | Expected Time | Progress | Task Name | Description & Expected Outcome | Start Date | Due Date | Expected Time | Progress | Task Name | Description & Expected Outcome | Start Date | Due Date | Expected Time | Progress | Task Name | Description & Expected Outcome | Start Date | Due Date | Expected Time | Progress | Task Name | Description & Expected Outcome | Start Date | Due Date | Expected Time | Progress
1 | General Meetings | Contribute to team planning at meetings | 2022-02-23 | 2022-03-02 | 1 |  | General Meetings | Contribute to team planning at meetings | 2022-02-23 | 2022-03-02 | 1 |  | General Meetings | Contribute to team planning at meetings | 2022-02-23 | 2022-03-02 | 1 |  | General Meetings | Contribute to team planning at meetings | 2022-02-23 | 2022-03-02 | 1
2 | Programming | Contribute to GeekSurvey codebase | 2022-02-23 | 2022-03-02 | 2 |  | Programming | Contribute to GeekSurvey codebase | 2022-02-23 | 2022-03-02 | 2 |  | Programming | Contribute to GeekSurvey codebase | 2022-02-23 | 2022-03-02 | 2 |  | Programming | Contribute to GeekSurvey codebase | 2022-02-23 | 2022-03-02 | 2
3
4
3 | Expected Total Time: |  |  |  | 3 | hrs | Expected Total Time: |  |  |  | 3 | hrs | Expected Total Time: |  |  |  | 3 | hrs | Expected Total Time: |  |  |  | 3 | hrs | Expected Total Time: |  |  |  | 0 | hrs
| Additional comments questions or concerns: | [5 empty] | Additional comments questions or concerns: | [5 empty] | Additional comments questions or concerns: | [5 empty] | Additional comments questions or concerns: | [5 empty] | Additional comments questions or concerns:
UGRADS Abstract Review
Current Major Deliverables:
| 1 | [6 empty] | Gantt Chart | [5 empty] | Commit History
| 2 | [6 empty] | https://docs.google.com/spreadsheets/d/1f7RZwt7m7hIaU-dNwV-3LjXIOoSCrCGt7WCVYpEjwIY/edit?usp=sharing | [5 empty] | https://github.com/NAU-SuperGeeks/geeksurvey/graphs/contributors
3
4
etc
Instructions:
| 1 | Every week your team should fill out the "Next Week" and "Upcoming" section together.
| 2 | You should fill in your respective "This Week" section as you finish your individual tasks.
| 3 | The unassigned section is mostly for upcoming tasks that the team has not delegated. If you have time and have not done many tasks this week, you might want to pick up an unassigned task.
| 4 | Record how long each task took in the time column. Actual time should be recorded when the task is finished (i.e. in the This Week section). Expected time should be recorded when the task is assigned (i.e. in the Next Week section).
| 5 | Times should be recorded in hrs. E.g. if a task took 1/2 an hour put 0.5, if a task takes 10 minutes put 0.17, ect.
| 6 | When adding a task right click last task row number and click "+ insert 1 row below"
Notes:
| 1 | Don't change previous weeks, google sheets has version history. I can see when and who changed a sheet.
| 2 | Don't inflate the time you spend on things. Worse than not investing enough time on the project, is appearing have to wasted time on something that shouldn't take that long.
| 3 | You should fill in your own tasks and review what others have gotten done.
| 4 | If there's ever a problem with a (the) task report(s), you can leave a comment or notify me.
| 5 | Everyone should complete at least one task a week. If one or two members appear to be doing all the work, your team should consider reevaluating your task delegation.

## Week 7
Date | [24 empty] | Unassigned
2022-02-23 | Timothy Giroux |  | tlg292@nau.edu |  |  |  | Kyle Steven Austria |  | kaa474@nau.edu |  |  |  | Gustavo Valencia |  | gmv43@nau.edu |  |  |  | Pengfei Liu |  | pl384@nau.edu |  |  |  | --
2022-03-02 | Task Name | Description & Expected Outcome | Start Date | Due Date | Actual Time (hr) | Progress | Task Name | Description & Expected Outcome | Start Date | Due Date | Actual Time (hr) | Progress | Task Name | Description & Expected Outcome | Start Date | Due Date | Actual Time (hr) | Progress | Task Name | Description & Expected Outcome | Start Date | Due Date | Actual Time (hr) | Progress | Task Name | Description & Expected Outcome | Start Date | Due Date | Actual Time (hr) | Progress
Done
1 | General Meetings | Contribute to team planning at meetings | 2022-02-16 | 2022-02-23 | 2 | 100% | General Meetings | Contribute to team planning at meetings | 2022-02-16 | 2022-02-23 | 1 | 100% | General Meetings | Contribute to team planning at meetings | 2022-02-16 | 2022-02-23 | 1 | 100% | General Meetings | Contribute to team planning at meetings | 2022-02-16 | 2022-02-23 | 1 | 100%
2 | Programming | Continue adding and refining enrollment criteria as requested by clients and start work on user stories 7.1 and 7.6 | 2022-02-16 | 2022-02-23 | 5 | 100% | Programming | Start work on user stories 7.1 and 7.6 | 2022-02-16 | 2022-02-23 | 5 | 100% | Programming | Start work on UI overhaul | 2022-02-16 | 2022-02-23 | 6 | 100% | Programming | Continue work on user stories 4.3 and 4.3.1 | 2022-02-16 | 2022-02-23 | 3 | 100%
3 | Revise UGRADS abstract | Address feedback from Felicity | 2022-02-16 | 2022-02-23 | 1 | 100%
4
| Actual Total Time: |  |  |  | 8 | hrs | Actual Total Time: |  |  |  | 6 | hrs | Actual Total Time: |  |  |  | 7 | hrs | Actual Total Time: |  |  |  | 4 | hrs | Actual Total Time: |  |  |  | 0 | hrs
Todo | Task Name | Description & Expected Outcome | Start Date | Due Date | Expected Time | Progress | Task Name | Description & Expected Outcome | Start Date | Due Date | Expected Time | Progress | Task Name | Description & Expected Outcome | Start Date | Due Date | Expected Time | Progress | Task Name | Description & Expected Outcome | Start Date | Due Date | Expected Time | Progress | Task Name | Description & Expected Outcome | Start Date | Due Date | Expected Time | Progress
1 | General Meetings | Contribute to team planning at meetings | 2022-02-23 | 2022-03-02 | 1 | 100% | General Meetings | Contribute to team planning at meetings | 2022-02-23 | 2022-03-02 | 1 | 100% | General Meetings | Contribute to team planning at meetings | 2022-02-23 | 2022-03-02 | 1 | 100% | General Meetings | Contribute to team planning at meetings | 2022-02-23 | 2022-03-02 | 1 | 100%
2 | Programming | Complete Payments Sprint, create server on client cloud account | 2022-02-23 | 2022-03-02 | 2 | 100% | Programming | Complete user story 8.1(CRUNCH) | 2022-02-23 | 2022-03-02 | 2 | 100% | Programming | Start work on user story 8.2 | 2022-02-23 | 2022-03-02 | 2 | 100% | Programming | Continue work on UI overhaul | 2022-02-23 | 2022-03-02 | 2 | 100%
3 | Design Review II Sections | Draft Implementation Overview, Implementation Details, and Challenges and Resolutions sections | 2022-02-23 | 2022-03-02 | 4 | 100% | Design Review II Sections | Draft Introduction and Problem Statement sections | 2022-02-23 | 2022-03-02 | 4 | 100% | Design Review II Sections | Draft Solution Overview and Requirements Review sections | 2022-02-23 | 2022-03-02 | 4 | 100% | Design Review II Sections | Draft Schedule and Conclusion sections | 2022-02-23 | 2022-03-02 | 4 | 100%
4 | Write Alpha Demo Flight Plan | Fill out steps for Use Cases 1 and 2 | 2022-02-23 | 2022-03-02 | 1 | 100% | [6 empty] | Write Alpha Demo Flight Plan | Fill out steps for Use Case 3 | 2022-02-23 | 2022-03-02 | 0.5 | 100%
| Expected Total Time: |  |  |  | 8 | hrs | Expected Total Time: |  |  |  | 7 | hrs | Expected Total Time: |  |  |  | 7.5 | hrs | Expected Total Time: |  |  |  | 7 | hrs | Expected Total Time: |  |  |  | 0 | hrs
Upcoming | Task Name | Description & Expected Outcome | Start Date | Due Date | Expected Time | Progress | Task Name | Description & Expected Outcome | Start Date | Due Date | Expected Time | Progress | Task Name | Description & Expected Outcome | Start Date | Due Date | Expected Time | Progress | Task Name | Description & Expected Outcome | Start Date | Due Date | Expected Time | Progress | Task Name | Description & Expected Outcome | Start Date | Due Date | Expected Time | Progress
1 | General Meetings | Contribute to team planning at meetings | 2022-03-02 | 2022-03-09 | 1 |  | General Meetings | Contribute to team planning at meetings | 2022-03-02 | 2022-03-09 | 1 |  | General Meetings | Contribute to team planning at meetings | 2022-03-02 | 2022-03-09 | 1 |  | General Meetings | Contribute to team planning at meetings | 2022-03-02 | 2022-03-09 | 1
2 | Programming | Contribute to GeekSurvey codebase | 2022-03-02 | 2022-03-09 | 2 |  | Programming | Contribute to GeekSurvey codebase | 2022-03-02 | 2022-03-09 | 2 |  | Programming | Contribute to GeekSurvey codebase | 2022-03-02 | 2022-03-09 | 2 |  | Programming | Contribute to GeekSurvey codebase | 2022-03-02 | 2022-03-09 | 2
3 | Finalize Design Review II Sections | Finalize respective presentation sections and video recording | 2022-03-02 | 2022-03-09 | 2 |  | Finalize Design Review II Sections | Finalize respective presentation sections and video recording | 2022-03-02 | 2022-03-09 | 2 |  | Finalize Design Review II Sections | Finalize respective presentation sections and video recording | 2022-03-02 | 2022-03-09 | 2 |  | Finalize Design Review II Sections | Finalize respective presentation sections and video recording | 2022-03-02 | 2022-03-09 | 2
4
| Expected Total Time: |  |  |  | 5 | hrs | Expected Total Time: |  |  |  | 5 | hrs | Expected Total Time: |  |  |  | 5 | hrs | Expected Total Time: |  |  |  | 5 | hrs | Expected Total Time: |  |  |  | 0 | hrs
| Additional comments questions or concerns: | [5 empty] | Additional comments questions or concerns: | [5 empty] | Additional comments questions or concerns: | [5 empty] | Additional comments questions or concerns: | [5 empty] | Additional comments questions or concerns:
| Submit UGRADS? | [11 empty] | UGRADS Abstract Review
Current Major Deliverables:
| 1 | Design Review II | [5 empty] | Gantt Chart | [5 empty] | Commit History
| 2 | [6 empty] | https://docs.google.com/spreadsheets/d/1f7RZwt7m7hIaU-dNwV-3LjXIOoSCrCGt7WCVYpEjwIY/edit?usp=sharing | [5 empty] | https://github.com/NAU-SuperGeeks/geeksurvey/graphs/contributors
3
4
etc
Instructions:
| 1 | Every week your team should fill out the "Next Week" and "Upcoming" section together.
| 2 | You should fill in your respective "This Week" section as you finish your individual tasks.
| 3 | The unassigned section is mostly for upcoming tasks that the team has not delegated. If you have time and have not done many tasks this week, you might want to pick up an unassigned task.
| 4 | Record how long each task took in the time column. Actual time should be recorded when the task is finished (i.e. in the This Week section). Expected time should be recorded when the task is assigned (i.e. in the Next Week section).
| 5 | Times should be recorded in hrs. E.g. if a task took 1/2 an hour put 0.5, if a task takes 10 minutes put 0.17, ect.
| 6 | When adding a task right click last task row number and click "+ insert 1 row below"
Notes:
| 1 | Don't change previous weeks, google sheets has version history. I can see when and who changed a sheet.
| 2 | Don't inflate the time you spend on things. Worse than not investing enough time on the project, is appearing have to wasted time on something that shouldn't take that long.
| 3 | You should fill in your own tasks and review what others have gotten done.
| 4 | If there's ever a problem with a (the) task report(s), you can leave a comment or notify me.
| 5 | Everyone should complete at least one task a week. If one or two members appear to be doing all the work, your team should consider reevaluating your task delegation.

## Week 8
Date | [24 empty] | Unassigned
2022-03-02 | Timothy Giroux |  | tlg292@nau.edu |  |  |  | Kyle Steven Austria |  | kaa474@nau.edu |  |  |  | Gustavo Valencia |  | gmv43@nau.edu |  |  |  | Pengfei Liu |  | pl384@nau.edu |  |  |  | --
2022-03-09 | Task Name | Description & Expected Outcome | Start Date | Due Date | Actual Time (hr) | Progress | Task Name | Description & Expected Outcome | Start Date | Due Date | Actual Time (hr) | Progress | Task Name | Description & Expected Outcome | Start Date | Due Date | Actual Time (hr) | Progress | Task Name | Description & Expected Outcome | Start Date | Due Date | Actual Time (hr) | Progress | Task Name | Description & Expected Outcome | Start Date | Due Date | Actual Time (hr) | Progress
Done
1 | General Meetings | Contribute to team planning at meetings | 2022-02-23 | 2022-03-02 | 2 | 100% | General Meetings | Contribute to team planning at meetings | 2022-02-23 | 2022-03-02 | 1 | 100% | General Meetings | Contribute to team planning at meetings | 2022-02-23 | 2022-03-02 | 1 | 100% | General Meetings | Contribute to team planning at meetings | 2022-02-23 | 2022-03-02 | 1 | 100%
2 | Programming | Complete Payments Sprint, create server on client cloud account | 2022-02-23 | 2022-03-02 | 5 | 100% | Programming | Complete user story 8.1(CRUNCH) | 2022-02-23 | 2022-03-02 | 4 | 100% | Programming | Start work on user story 8.2 | 2022-02-23 | 2022-03-02 | 2 | 100% | Programming | Continue work on UI overhaul | 2022-02-23 | 2022-03-02 | 2 | 100%
3 | Design Review II Sections | Draft Implementation Overview, Implementation Details, and Challenges and Resolutions sections | 2022-02-23 | 2022-03-02 | 2 | 100% | Design Review II Sections | Draft Introduction and Problem Statement sections | 2022-02-23 | 2022-03-02 | 3 | 100% | Design Review II Sections | Draft Solution Overview and Requirements Review sections | 2022-02-23 | 2022-03-02 | 4 | 100% | Design Review II Sections | Draft Schedule and Conclusion sections | 2022-02-23 | 2022-03-02 | 4 | 100%
4 | Write Alpha Demo Flight Plan | Fill out steps for Use Cases 1 and 2 | 2022-02-23 | 2022-03-02 | 1 | 100% | [6 empty] | Write Alpha Demo Flight Plan | Fill out steps for Use Case 3 | 2022-02-23 | 2022-03-02 | 0.5 | 100%
| Actual Total Time: |  |  |  | 10 | hrs | Actual Total Time: |  |  |  | 8 | hrs | Actual Total Time: |  |  |  | 7.5 | hrs | Actual Total Time: |  |  |  | 7 | hrs | Actual Total Time: |  |  |  | 0 | hrs
Todo | Task Name | Description & Expected Outcome | Start Date | Due Date | Expected Time | Progress | Task Name | Description & Expected Outcome | Start Date | Due Date | Expected Time | Progress | Task Name | Description & Expected Outcome | Start Date | Due Date | Expected Time | Progress | Task Name | Description & Expected Outcome | Start Date | Due Date | Expected Time | Progress | Task Name | Description & Expected Outcome | Start Date | Due Date | Expected Time | Progress
1 | General Meetings | Contribute to team planning at meetings | 2022-03-02 | 2022-03-09 | 1 | 100% | General Meetings | Contribute to team planning at meetings | 2022-03-02 | 2022-03-09 | 1 | 100% | General Meetings | Contribute to team planning at meetings | 2022-03-02 | 2022-03-09 | 1 | 100% | General Meetings | Contribute to team planning at meetings | 2022-03-02 | 2022-03-09 | 1 | 100%
2 | Programming | User stories 8.4 and 8.5 | 2022-03-02 | 2022-03-09 | 4 | 100% | Programming | Complete user stories 8.3 and 8.3.1(CRUNCH) | 2022-03-02 | 2022-03-09 | 4 | 100% | Programming | Complete user stories 8.2 and 8.6 | 2022-03-02 | 2022-03-09 | 4 | 100% | Programming | Complete the user story 8.3 and 8.3.1(CRUNCH) | 2022-03-02 | 2022-03-09 | 4 | 100%
3 | Finalize Design Review II Sections | Finalize and record Implementation Overview, Implementation Details, and Challenges and Resolutions sections | 2022-03-02 | 2022-03-09 | 2 | 100% | Finalize Design Review II Sections | Finalize and record Introduction and Problem Statement sections | 2022-03-02 | 2022-03-09 | 2 | 100% | Finalize Design Review II Sections | Finalize and record Solution Overview and Requirements Review sections | 2022-03-02 | 2022-03-09 | 2 | 100% | Finalize Design Review II Sections | Finalize and record Schedule and Conclusion sections | 2022-03-02 | 2022-03-09 | 2 | 100%
4 | Prepare Alpha Demo | Prepare material for Alpha Demo, make sure there are no bugs. | 2022-03-02 | 2022-03-09 | 2 | 100% | Revise Alpha Demo Flight Plan | Revise all Use Case steps to be more detailed and comprehensive | 2022-03-02 | 2022-03-09 | 2 | 100% | Revise Alpha Demo Flight Plan | Revise all Use Case steps to be more detailed and comprehensive | 2022-03-02 | 2022-03-09 | 2 | 100% | Revise Alpha Demo Flight Plan | Revise all Use Case steps to be more detailed and comprehensive | 2022-03-02 | 2022-03-09 | 2 | 100%
| Expected Total Time: |  |  |  | 9 | hrs | Expected Total Time: |  |  |  | 9 | hrs | Expected Total Time: |  |  |  | 9 | hrs | Expected Total Time: |  |  |  | 9 | hrs | Expected Total Time: |  |  |  | 0 | hrs
Upcoming | Task Name | Description & Expected Outcome | Start Date | Due Date | Expected Time | Progress | Task Name | Description & Expected Outcome | Start Date | Due Date | Expected Time | Progress | Task Name | Description & Expected Outcome | Start Date | Due Date | Expected Time | Progress | Task Name | Description & Expected Outcome | Start Date | Due Date | Expected Time | Progress | Task Name | Description & Expected Outcome | Start Date | Due Date | Expected Time | Progress
1 | General Meetings | Contribute to team planning at meetings | 2022-03-09 | 2022-03-16 | 1 |  | General Meetings | Contribute to team planning at meetings | 2022-03-09 | 2022-03-16 | 1 |  | General Meetings | Contribute to team planning at meetings | 2022-03-09 | 2022-03-16 | 1 |  | General Meetings | Contribute to team planning at meetings | 2022-03-09 | 2022-03-16 | 1
2 | Programming | Contribute to GeekSurvey codebase | 2022-03-09 | 2022-03-16 | 2 |  | Programming | Contribute to GeekSurvey codebase | 2022-03-09 | 2022-03-16 | 2 |  | Programming | Contribute to GeekSurvey codebase | 2022-03-09 | 2022-03-16 | 2 |  | Programming | Contribute to GeekSurvey codebase | 2022-03-09 | 2022-03-16 | 2
3
4
| Expected Total Time: |  |  |  | 3 | hrs | Expected Total Time: |  |  |  | 3 | hrs | Expected Total Time: |  |  |  | 3 | hrs | Expected Total Time: |  |  |  | 3 | hrs | Expected Total Time: |  |  |  | 0 | hrs
| Additional comments questions or concerns: | [5 empty] | Additional comments questions or concerns: | [5 empty] | Additional comments questions or concerns: | [5 empty] | Additional comments questions or concerns: | [5 empty] | Additional comments questions or concerns:
DRII Presentation Draft
Current Major Deliverables:
| 1 | Design Review II Step 1 | [5 empty] | Gantt Chart | [5 empty] | Commit History
| 2 | Alpha Prototype Demo | [5 empty] | https://docs.google.com/spreadsheets/d/1f7RZwt7m7hIaU-dNwV-3LjXIOoSCrCGt7WCVYpEjwIY/edit?usp=sharing | [5 empty] | https://github.com/NAU-SuperGeeks/geeksurvey/graphs/contributors
3
4
etc
Instructions:
| 1 | Every week your team should fill out the "Next Week" and "Upcoming" section together.
| 2 | You should fill in your respective "This Week" section as you finish your individual tasks.
| 3 | The unassigned section is mostly for upcoming tasks that the team has not delegated. If you have time and have not done many tasks this week, you might want to pick up an unassigned task.
| 4 | Record how long each task took in the time column. Actual time should be recorded when the task is finished (i.e. in the This Week section). Expected time should be recorded when the task is assigned (i.e. in the Next Week section).
| 5 | Times should be recorded in hrs. E.g. if a task took 1/2 an hour put 0.5, if a task takes 10 minutes put 0.17, ect.
| 6 | When adding a task right click last task row number and click "+ insert 1 row below"
Notes:
| 1 | Don't change previous weeks, google sheets has version history. I can see when and who changed a sheet.
| 2 | Don't inflate the time you spend on things. Worse than not investing enough time on the project, is appearing have to wasted time on something that shouldn't take that long.
| 3 | You should fill in your own tasks and review what others have gotten done.
| 4 | If there's ever a problem with a (the) task report(s), you can leave a comment or notify me.
| 5 | Everyone should complete at least one task a week. If one or two members appear to be doing all the work, your team should consider reevaluating your task delegation.

## Week 9
Date | [24 empty] | Unassigned
2022-03-09 | Timothy Giroux |  | tlg292@nau.edu |  |  |  | Kyle Steven Austria |  | kaa474@nau.edu |  |  |  | Gustavo Valencia |  | gmv43@nau.edu |  |  |  | Pengfei Liu |  | pl384@nau.edu |  |  |  | --
2022-03-16 | Task Name | Description & Expected Outcome | Start Date | Due Date | Actual Time (hr) | Progress | Task Name | Description & Expected Outcome | Start Date | Due Date | Actual Time (hr) | Progress | Task Name | Description & Expected Outcome | Start Date | Due Date | Actual Time (hr) | Progress | Task Name | Description & Expected Outcome | Start Date | Due Date | Actual Time (hr) | Progress | Task Name | Description & Expected Outcome | Start Date | Due Date | Actual Time (hr) | Progress
Done
1 | General Meetings | Contribute to team planning at meetings | 2022-03-02 | 2022-03-09 | 1 | 100% | General Meetings | Contribute to team planning at meetings | 2022-03-02 | 2022-03-09 | 1 | 100% | General Meetings | Contribute to team planning at meetings | 2022-03-02 | 2022-03-09 | 1 | 100% | General Meetings | Contribute to team planning at meetings | 2022-03-02 | 2022-03-09 | 1 | 100%
2 | Programming | User stories 8.4 and 8.5 | 2022-03-02 | 2022-03-09 | 4 | 100% | Programming | Complete user stories 8.3 and 8.3.1(CRUNCH) | 2022-03-02 | 2022-03-09 | 4 | 100% | Programming | Complete user stories 8.2 and 8.6 | 2022-03-02 | 2022-03-09 | 4 | 100% | Programming | Complete the user story 8.3 and 8.3.1(CRUNCH) | 2022-03-02 | 2022-03-09 | 4 | 100%
3 | Finalize Design Review II Sections | Finalize and record Implementation Overview, Implementation Details, and Challenges and Resolutions sections | 2022-03-02 | 2022-03-09 | 2 | 100% | Finalize Design Review II Sections | Finalize and record Introduction and Problem Statement sections | 2022-03-02 | 2022-03-09 | 2 | 100% | Finalize Design Review II Sections | Finalize and record Solution Overview and Requirements Review sections | 2022-03-02 | 2022-03-09 | 2 | 100% | Finalize Design Review II Sections | Finalize and record Schedule and Conclusion sections | 2022-03-02 | 2022-03-09 | 2 | 100%
4 | Prepare Alpha Demo | Prepare material for Alpha Demo, make sure there are no bugs. | 2022-03-02 | 2022-03-09 | 2 | 100% | Revise Alpha Demo Flight Plan | Revise all Use Case steps to be more detailed and comprehensive | 2022-03-02 | 2022-03-09 | 2 | 100% | Revise Alpha Demo Flight Plan | Revise all Use Case steps to be more detailed and comprehensive | 2022-03-02 | 2022-03-09 | 2 | 100% | Revise Alpha Demo Flight Plan | Revise all Use Case steps to be more detailed and comprehensive | 2022-03-02 | 2022-03-09 | 2 | 100%
| Actual Total Time: |  |  |  | 9 | hrs | Actual Total Time: |  |  |  | 9 | hrs | Actual Total Time: |  |  |  | 9 | hrs | Actual Total Time: |  |  |  | 9 | hrs | Actual Total Time: |  |  |  | 0 | hrs
Todo | Task Name | Description & Expected Outcome | Start Date | Due Date | Expected Time | Progress | Task Name | Description & Expected Outcome | Start Date | Due Date | Expected Time | Progress | Task Name | Description & Expected Outcome | Start Date | Due Date | Expected Time | Progress | Task Name | Description & Expected Outcome | Start Date | Due Date | Expected Time | Progress | Task Name | Description & Expected Outcome | Start Date | Due Date | Expected Time | Progress
1 | Complete Design Review 2 Step 2 | Review presentations for each assigned team and discuss final feedback as a team | 2022-03-09 | 2022-03-11 | 2 | 100% | Complete Design Review 2 Step 2 | Review presentations for each assigned team and discuss final feedback as a team | 2022-03-09 | 2022-03-11 | 2 |  | Complete Design Review 2 Step 2 | Review presentations for each assigned team and discuss final feedback as a team | 2022-03-09 | 2022-03-11 | 2 |  | Complete Design Review 2 Step 2 | Review presentations for each assigned team and discuss final feedback as a team | 2022-03-09 | 2022-03-11 | 2
2
3
4
| Expected Total Time: |  |  |  | 2 | hrs | Expected Total Time: |  |  |  | 2 | hrs | Expected Total Time: |  |  |  | 2 | hrs | Expected Total Time: |  |  |  | 2 | hrs | Expected Total Time: |  |  |  | 0 | hrs
Upcoming | Task Name | Description & Expected Outcome | Start Date | Due Date | Expected Time | Progress | Task Name | Description & Expected Outcome | Start Date | Due Date | Expected Time | Progress | Task Name | Description & Expected Outcome | Start Date | Due Date | Expected Time | Progress | Task Name | Description & Expected Outcome | Start Date | Due Date | Expected Time | Progress | Task Name | Description & Expected Outcome | Start Date | Due Date | Expected Time | Progress
1 | General Meetings | Contribute to team planning at meetings | 2022-03-23 | 2022-03-30 | 1 |  | General Meetings | Contribute to team planning at meetings | 2022-03-23 | 2022-03-30 | 1 |  | General Meetings | Contribute to team planning at meetings | 2022-03-23 | 2022-03-30 | 1 |  | General Meetings | Contribute to team planning at meetings | 2022-03-23 | 2022-03-30 | 1
2 | Programming | Contribute to GeekSurvey codebase | 2022-03-23 | 2022-03-30 | 2 |  | Programming | Contribute to GeekSurvey codebase | 2022-03-23 | 2022-03-30 | 2 |  | Programming | Contribute to GeekSurvey codebase | 2022-03-23 | 2022-03-30 | 2 |  | Programming | Contribute to GeekSurvey codebase | 2022-03-23 | 2022-03-30 | 2
3
4
| Expected Total Time: |  |  |  | 3 | hrs | Expected Total Time: |  |  |  | 3 | hrs | Expected Total Time: |  |  |  | 3 | hrs | Expected Total Time: |  |  |  | 3 | hrs | Expected Total Time: |  |  |  | 0 | hrs
| Additional comments questions or concerns: | [5 empty] | Additional comments questions or concerns: | [5 empty] | Additional comments questions or concerns: | [5 empty] | Additional comments questions or concerns: | [5 empty] | Additional comments questions or concerns:
Current Major Deliverables:
| 1 | Design Review II Step 2 | [5 empty] | Gantt Chart | [5 empty] | Commit History
| 2 | Alpha Prototype Demo | [5 empty] | https://docs.google.com/spreadsheets/d/1f7RZwt7m7hIaU-dNwV-3LjXIOoSCrCGt7WCVYpEjwIY/edit?usp=sharing | [5 empty] | https://github.com/NAU-SuperGeeks/geeksurvey/graphs/contributors
3
4
etc
Instructions:
| 1 | Every week your team should fill out the "Next Week" and "Upcoming" section together.
| 2 | You should fill in your respective "This Week" section as you finish your individual tasks.
| 3 | The unassigned section is mostly for upcoming tasks that the team has not delegated. If you have time and have not done many tasks this week, you might want to pick up an unassigned task.
| 4 | Record how long each task took in the time column. Actual time should be recorded when the task is finished (i.e. in the This Week section). Expected time should be recorded when the task is assigned (i.e. in the Next Week section).
| 5 | Times should be recorded in hrs. E.g. if a task took 1/2 an hour put 0.5, if a task takes 10 minutes put 0.17, ect.
| 6 | When adding a task right click last task row number and click "+ insert 1 row below"
Notes:
| 1 | Don't change previous weeks, google sheets has version history. I can see when and who changed a sheet.
| 2 | Don't inflate the time you spend on things. Worse than not investing enough time on the project, is appearing have to wasted time on something that shouldn't take that long.
| 3 | You should fill in your own tasks and review what others have gotten done.
| 4 | If there's ever a problem with a (the) task report(s), you can leave a comment or notify me.
| 5 | Everyone should complete at least one task a week. If one or two members appear to be doing all the work, your team should consider reevaluating your task delegation.

## Week 10
Date | [24 empty] | Unassigned
2022-03-16 | Timothy Giroux |  | tlg292@nau.edu |  |  |  | Kyle Steven Austria |  | kaa474@nau.edu |  |  |  | Gustavo Valencia |  | gmv43@nau.edu |  |  |  | Pengfei Liu |  | pl384@nau.edu |  |  |  | --
2022-03-23 | Task Name | Description & Expected Outcome | Start Date | Due Date | Actual Time (hr) | Progress | Task Name | Description & Expected Outcome | Start Date | Due Date | Actual Time (hr) | Progress | Task Name | Description & Expected Outcome | Start Date | Due Date | Actual Time (hr) | Progress | Task Name | Description & Expected Outcome | Start Date | Due Date | Actual Time (hr) | Progress | Task Name | Description & Expected Outcome | Start Date | Due Date | Actual Time (hr) | Progress
Done
1 | Relocate Geeksurvey to Client Server | Edit DNS records, renew SSL certificate, configure client server, redeploy geeksurvey on client server | 2022-03-11 | 2022-03-23 | 3 | 100% | [6 empty] | Team Website Redesign | Redesign team website to use Bootstrap 5 and thematically look like the main GeekSurvey site | 2022-03-11 | 2022-03-23 | 6 | 100%
2
3
4
3 | Actual Total Time: |  |  |  | 3 | hrs | Actual Total Time: |  |  |  | 0 | hrs | Actual Total Time: |  |  |  | 6 | hrs | Actual Total Time: |  |  |  | 0 | hrs | Actual Total Time: |  |  |  | 0 | hrs
Todo | Task Name | Description & Expected Outcome | Start Date | Due Date | Expected Time | Progress | Task Name | Description & Expected Outcome | Start Date | Due Date | Expected Time | Progress | Task Name | Description & Expected Outcome | Start Date | Due Date | Expected Time | Progress | Task Name | Description & Expected Outcome | Start Date | Due Date | Expected Time | Progress | Task Name | Description & Expected Outcome | Start Date | Due Date | Expected Time | Progress
1
2
3
4
0 | Expected Total Time: |  |  |  | 0 | hrs | Expected Total Time: |  |  |  | 0 | hrs | Expected Total Time: |  |  |  | 0 | hrs | Expected Total Time: |  |  |  | 0 | hrs | Expected Total Time: |  |  |  | 0 | hrs
Upcoming | Task Name | Description & Expected Outcome | Start Date | Due Date | Expected Time | Progress | Task Name | Description & Expected Outcome | Start Date | Due Date | Expected Time | Progress | Task Name | Description & Expected Outcome | Start Date | Due Date | Expected Time | Progress | Task Name | Description & Expected Outcome | Start Date | Due Date | Expected Time | Progress | Task Name | Description & Expected Outcome | Start Date | Due Date | Expected Time | Progress
1
2
3
4
0 | Expected Total Time: |  |  |  | 0 | hrs | Expected Total Time: |  |  |  | 0 | hrs | Expected Total Time: |  |  |  | 0 | hrs | Expected Total Time: |  |  |  | 0 | hrs | Expected Total Time: |  |  |  | 0 | hrs
| Additional comments questions or concerns: | [5 empty] | Additional comments questions or concerns: | [5 empty] | Additional comments questions or concerns: | [5 empty] | Additional comments questions or concerns: | [5 empty] | Additional comments questions or concerns:
Current Major Deliverables:
| 1 | [6 empty] | Gantt Chart | [5 empty] | Commit History
| 2 | [6 empty] | https://docs.google.com/spreadsheets/d/1f7RZwt7m7hIaU-dNwV-3LjXIOoSCrCGt7WCVYpEjwIY/edit?usp=sharing | [5 empty] | https://github.com/NAU-SuperGeeks/www_supergeeks/graphs/contributors
3
4
etc
Instructions:
| 1 | Every week your team should fill out the "Next Week" and "Upcoming" section together.
| 2 | You should fill in your respective "This Week" section as you finish your individual tasks.
| 3 | The unassigned section is mostly for upcoming tasks that the team has not delegated. If you have time and have not done many tasks this week, you might want to pick up an unassigned task.
| 4 | Record how long each task took in the time column. Actual time should be recorded when the task is finished (i.e. in the This Week section). Expected time should be recorded when the task is assigned (i.e. in the Next Week section).
| 5 | Times should be recorded in hrs. E.g. if a task took 1/2 an hour put 0.5, if a task takes 10 minutes put 0.17, ect.
| 6 | When adding a task right click last task row number and click "+ insert 1 row below"
Notes:
| 1 | Don't change previous weeks, google sheets has version history. I can see when and who changed a sheet.
| 2 | Don't inflate the time you spend on things. Worse than not investing enough time on the project, is appearing have to wasted time on something that shouldn't take that long.
| 3 | You should fill in your own tasks and review what others have gotten done.
| 4 | If there's ever a problem with a (the) task report(s), you can leave a comment or notify me.
| 5 | Everyone should complete at least one task a week. If one or two members appear to be doing all the work, your team should consider reevaluating your task delegation.

## Week 11
Unassigned
2022-03-23 | Timothy Giroux |  | tlg292@nau.edu |  |  |  | Kyle Steven Austria |  | kaa474@nau.edu |  |  |  | Gustavo Valencia |  | gmv43@nau.edu |  |  |  | Pengfei Liu |  | pl384@nau.edu |  |  |  | --
2022-03-30 | Task Name | Description & Expected Outcome | Start Date | Due Date | Actual Time (hr) | Progress | Task Name | Description & Expected Outcome | Start Date | Due Date | Actual Time (hr) | Progress | Task Name | Description & Expected Outcome | Start Date | Due Date | Actual Time (hr) | Progress | Task Name | Description & Expected Outcome | Start Date | Due Date | Actual Time (hr) | Progress | Task Name | Description & Expected Outcome | Start Date | Due Date | Actual Time (hr) | Progress
Done
1 | Complete Design Review 2 Step 2 | Review presentations for each assigned team and discuss final feedback as a team | 2022-03-09 | 2022-03-11 | 2 | 100% | Complete Design Review 2 Step 2 | Review presentations for each assigned team and discuss final feedback as a team | 2022-03-09 | 2022-03-11 | 2 | 100% | Complete Design Review 2 Step 2 | Review presentations for each assigned team and discuss final feedback as a team | 2022-03-09 | 2022-03-11 | 2 | 100% | Complete Design Review 2 Step 2 | Review presentations for each assigned team and discuss final feedback as a team | 2022-03-09 | 2022-03-11 | 2 | 100%
2
3
4
2 | Actual Total Time: |  |  |  | 2 | hrs | Actual Total Time: |  |  |  | 2 | hrs | Actual Total Time: |  |  |  | 2 | hrs | Actual Total Time: |  |  |  | 2 | hrs | Actual Total Time: |  |  |  | 0 | hrs
Todo | Task Name | Description & Expected Outcome | Start Date | Due Date | Expected Time | Progress | Task Name | Description & Expected Outcome | Start Date | Due Date | Expected Time | Progress | Task Name | Description & Expected Outcome | Start Date | Due Date | Expected Time | Progress | Task Name | Description & Expected Outcome | Start Date | Due Date | Expected Time | Progress | Task Name | Description & Expected Outcome | Start Date | Due Date | Expected Time | Progress
1 | Draft Testing Plan Section | Complete a draft for Unit Testing section of the Testing Plan document | 2022-03-23 | 2022-03-27 | 4 | 100% | Draft Testing Plan Section | Complete a draft for Introduction and Conclusion sections of the Testing Plan document | 2022-03-23 | 2022-03-27 | 4 | 100% | Draft Testing Plan Section | Complete a draft for Usability Testing section of the Testing Plan document | 2022-03-23 | 2022-03-27 | 4 | 100% | Draft Testing Plan Section | Complete a draft for Integration Testing section of the Testing Plan document | 2022-03-23 | 2022-03-27 | 4 | 100%
2 | Set up SSL autorenew for geeksurvey.xyz | SSL certificates for geeksurvey.xyz and www.geeksurvey.xyz will expire in 90 days. Set up autorenew so that they will renew instead of expiring (which would break the website) | 2022-03-23 | 2022-03-27 | 2 | 100% | [6 empty] | Create Document/Presentation Skeletons | Create skeleton document for Software Testing Plan and skeleton presentation for Design Review 3 Presentation. These skeletons will be used to outline required content and to distribute work amongst team. | 2022-03-23 | 2022-03-23 | 1 | 100%
3 | Amend Requirements Doc | The clients have expressed approval for deploying geeksurvey without containerization. The Requirements Document should be amended to reflect this. | 2022-03-23 | 2022-03-27 | 1 | 100%
4
7 | Expected Total Time: |  |  |  | 7 | hrs | Expected Total Time: |  |  |  | 4 | hrs | Expected Total Time: |  |  |  | 5 | hrs | Expected Total Time: |  |  |  | 4 | hrs | Expected Total Time: |  |  |  | 0 | hrs
Upcoming | Task Name | Description & Expected Outcome | Start Date | Due Date | Expected Time | Progress | Task Name | Description & Expected Outcome | Start Date | Due Date | Expected Time | Progress | Task Name | Description & Expected Outcome | Start Date | Due Date | Expected Time | Progress | Task Name | Description & Expected Outcome | Start Date | Due Date | Expected Time | Progress | Task Name | Description & Expected Outcome | Start Date | Due Date | Expected Time | Progress
1 | Finalize Testing Plan Section | Finalize Unit Testing section of the Testing Plan document | 2022-03-28 | 2022-04-01 | 4 |  | Finalize Testing Plan Section | Finalize Unit Introduction and Conclusion sections of the Testing Plan document | 2022-03-28 | 2022-04-01 | 4 |  | Finalize Testing Plan Section | Finalize Usability Testing section of the Testing Plan document | 2022-03-28 | 2022-04-01 | 4 |  | Finalize Testing Plan Section | Finalize Integration Testing section of the Testing Plan document | 2022-03-28 | 2022-04-01 | 4
2 | Draft Design Review 3 Sections | Complete a draft for respective Design Review 3 Presentation sections | 2022-03-30 | 2022-04-06 | 4 |  | Draft Design Review 3 Sections | Complete a draft for respective Design Review 3 Presentation sections | 2022-03-30 | 2022-04-06 | 4 |  | Draft Design Review 3 Sections | Complete a draft for respective Design Review 3 Presentation sections | 2022-03-30 | 2022-04-06 | 4 |  | Draft Design Review 3 Sections | Complete a draft for respective Design Review 3 Presentation sections | 2022-03-30 | 2022-04-06 | 4
3
4
8 | Expected Total Time: |  |  |  | 8 | hrs | Expected Total Time: |  |  |  | 8 | hrs | Expected Total Time: |  |  |  | 8 | hrs | Expected Total Time: |  |  |  | 8 | hrs | Expected Total Time: |  |  |  | 0 | hrs
| Additional comments questions or concerns: | [5 empty] | Additional comments questions or concerns: | [5 empty] | Additional comments questions or concerns: | [5 empty] | Additional comments questions or concerns: | [5 empty] | Additional comments questions or concerns:
| We are filling week 10 out for Spring break and starting with week 11, correct? When should we give you a DR3 draft? | [11 empty] | Is there anything else we need to do for UGRADS registration? Given that we have deviated from some of the things mentioned in our Requirements Document, should we update it and get it re-signed by our clients?
Current Major Deliverables:
| 1 | DR3 | [5 empty] | Gantt Chart | [5 empty] | Commit History
| 2 | Software Testing Plan | [5 empty] | https://docs.google.com/spreadsheets/d/1f7RZwt7m7hIaU-dNwV-3LjXIOoSCrCGt7WCVYpEjwIY/edit?usp=sharing | [5 empty] | https://github.com/NAU-SuperGeeks/geeksurvey/graphs/contributors
3
4
etc
Instructions:
| 1 | Every week your team should fill out the "Next Week" and "Upcoming" section together.
| 2 | You should fill in your respective "This Week" section as you finish your individual tasks.
| 3 | The unassigned section is mostly for upcoming tasks that the team has not delegated. If you have time and have not done many tasks this week, you might want to pick up an unassigned task.
| 4 | Record how long each task took in the time column. Actual time should be recorded when the task is finished (i.e. in the This Week section). Expected time should be recorded when the task is assigned (i.e. in the Next Week section).
| 5 | Times should be recorded in hrs. E.g. if a task took 1/2 an hour put 0.5, if a task takes 10 minutes put 0.17, ect.
| 6 | When adding a task right click last task row number and click "+ insert 1 row below"
Notes:
| 1 | Don't change previous weeks, google sheets has version history. I can see when and who changed a sheet.
| 2 | Don't inflate the time you spend on things. Worse than not investing enough time on the project, is appearing have to wasted time on something that shouldn't take that long.
| 3 | You should fill in your own tasks and review what others have gotten done.
| 4 | If there's ever a problem with a (the) task report(s), you can leave a comment or notify me.
| 5 | Everyone should complete at least one task a week. If one or two members appear to be doing all the work, your team should consider reevaluating your task delegation.

## Week 12
Date | [24 empty] | Unassigned
2022-03-30 | Timothy Giroux |  | tlg292@nau.edu |  |  |  | Kyle Steven Austria |  | kaa474@nau.edu |  |  |  | Gustavo Valencia |  | gmv43@nau.edu |  |  |  | Pengfei Liu |  | pl384@nau.edu |  |  |  | --
2022-04-06 | Task Name | Description & Expected Outcome | Start Date | Due Date | Actual Time (hr) | Progress | Task Name | Description & Expected Outcome | Start Date | Due Date | Actual Time (hr) | Progress | Task Name | Description & Expected Outcome | Start Date | Due Date | Actual Time (hr) | Progress | Task Name | Description & Expected Outcome | Start Date | Due Date | Actual Time (hr) | Progress | Task Name | Description & Expected Outcome | Start Date | Due Date | Actual Time (hr) | Progress
Done
1 | Draft Testing Plan Section | Complete a draft for Unit Testing section of the Testing Plan document | 2022-03-23 | 2022-03-27 | 4 | 100% | Draft Testing Plan Section | Complete a draft for Introduction and Conclusion sections of the Testing Plan document | 2022-03-23 | 2022-03-27 | 4 | 100% | Draft Testing Plan Section | Complete a draft for Usability Testing section of the Testing Plan document | 2022-03-23 | 2022-03-27 | 4 | 100% | Draft Testing Plan Section | Complete a draft for Integration Testing section of the Testing Plan document | 2022-03-23 | 2022-03-27 | 4 | 100%
2 | Set up SSL autorenew for geeksurvey.xyz | SSL certificates for geeksurvey.xyz and www.geeksurvey.xyz will expire in 90 days. Set up autorenew so that they will renew instead of expiring (which would break the website) | 2022-03-23 | 2022-03-27 | 2 | 100% | [6 empty] | Create Document/Presentation Skeletons | Create skeleton document for Software Testing Plan and skeleton presentation for Design Review 3 Presentation. These skeletons will be used to outline required content and to distribute work amongst team. | 2022-03-23 | 2022-03-23 | 1 | 100%
3 | Amend Requirements Doc | The clients have expressed approval for deploying geeksurvey without containerization. The Requirements Document should be amended to reflect this. | 2022-03-23 | 2022-03-27 | 1 | 100%
4
7 | Actual Total Time: |  |  |  | 7 | hrs | Actual Total Time: |  |  |  | 4 | hrs | Actual Total Time: |  |  |  | 5 | hrs | Actual Total Time: |  |  |  | 4 | hrs | Actual Total Time: |  |  |  | 0 | hrs
Todo | Task Name | Description & Expected Outcome | Start Date | Due Date | Expected Time | Progress | Task Name | Description & Expected Outcome | Start Date | Due Date | Expected Time | Progress | Task Name | Description & Expected Outcome | Start Date | Due Date | Expected Time | Progress | Task Name | Description & Expected Outcome | Start Date | Due Date | Expected Time | Progress | Task Name | Description & Expected Outcome | Start Date | Due Date | Expected Time | Progress
1 | Finalize Testing Plan Section | Finalize Unit Testing section of the Testing Plan document | 2022-03-28 | 2022-04-01 | 4 | 100% | Finalize Testing Plan Section | Finalize Unit Introduction and Conclusion sections of the Testing Plan document | 2022-03-28 | 2022-04-01 | 4 | 100% | Finalize Testing Plan Section | Finalize Usability Testing section of the Testing Plan document | 2022-03-28 | 2022-04-01 | 4 | 100% | Finalize Testing Plan Section | Finalize Integration Testing section of the Testing Plan document | 2022-03-28 | 2022-04-01 | 4 | 100%
2 | Draft Design Review 3 Sections | Complete a draft for respective Design Review 3 Presentation sections | 2022-03-30 | 2022-04-06 | 4 | 100% | Draft Design Review 3 Sections | Complete a draft for respective Design Review 3 Presentation sections | 2022-03-30 | 2022-04-06 | 4 | 100% | Draft Design Review 3 Sections | Complete a draft for respective Design Review 3 Presentation sections | 2022-03-30 | 2022-04-06 | 4 | 100% | Draft Design Review 3 Sections | Complete a draft for respective Design Review 3 Presentation sections | 2022-03-30 | 2022-04-06 | 4 | 100%
3
4
8 | Expected Total Time: |  |  |  | 8 | hrs | Expected Total Time: |  |  |  | 8 | hrs | Expected Total Time: |  |  |  | 8 | hrs | Expected Total Time: |  |  |  | 8 | hrs | Expected Total Time: |  |  |  | 0 | hrs
Upcoming | Task Name | Description & Expected Outcome | Start Date | Due Date | Expected Time | Progress | Task Name | Description & Expected Outcome | Start Date | Due Date | Expected Time | Progress | Task Name | Description & Expected Outcome | Start Date | Due Date | Expected Time | Progress | Task Name | Description & Expected Outcome | Start Date | Due Date | Expected Time | Progress | Task Name | Description & Expected Outcome | Start Date | Due Date | Expected Time | Progress
1 | Finalize Design Review 3 Sections | Finalize respective Design Review 3 Presentation sections | 2022-03-30 | 2022-04-06 | 4 |  | Finalize Design Review 3 Sections | Finalize respective Design Review 3 Presentation sections | 2022-03-30 | 2022-04-06 | 4 |  | Finalize Design Review 3 Sections | Finalize respective Design Review 3 Presentation sections | 2022-03-30 | 2022-04-06 | 4 |  | Finalize Design Review 3 Sections | Finalize respective Design Review 3 Presentation sections | 2022-03-30 | 2022-04-06 | 4
2
3
4
4 | Expected Total Time: |  |  |  | 4 | hrs | Expected Total Time: |  |  |  | 4 | hrs | Expected Total Time: |  |  |  | 4 | hrs | Expected Total Time: |  |  |  | 4 | hrs | Expected Total Time: |  |  |  | 0 | hrs
| Additional comments questions or concerns: | [5 empty] | Additional comments questions or concerns: | [5 empty] | Additional comments questions or concerns: | [5 empty] | Additional comments questions or concerns: | [5 empty] | Additional comments questions or concerns:
Current Major Deliverables:
| 1 | DR3 | [5 empty] | Gantt Chart | [5 empty] | Commit History
| 2 | Software Testing Plan | [5 empty] | https://docs.google.com/spreadsheets/d/1f7RZwt7m7hIaU-dNwV-3LjXIOoSCrCGt7WCVYpEjwIY/edit?usp=sharing | [5 empty] | https://github.com/NAU-SuperGeeks/geeksurvey/graphs/contributors
| 3 | [12 empty] | https://github.com/NAU-SuperGeeks/www_supergeeks/graphs/contributors
4
etc
Instructions:
| 1 | Every week your team should fill out the "Next Week" and "Upcoming" section together.
| 2 | You should fill in your respective "This Week" section as you finish your individual tasks.
| 3 | The unassigned section is mostly for upcoming tasks that the team has not delegated. If you have time and have not done many tasks this week, you might want to pick up an unassigned task.
| 4 | Record how long each task took in the time column. Actual time should be recorded when the task is finished (i.e. in the This Week section). Expected time should be recorded when the task is assigned (i.e. in the Next Week section).
| 5 | Times should be recorded in hrs. E.g. if a task took 1/2 an hour put 0.5, if a task takes 10 minutes put 0.17, ect.
| 6 | When adding a task right click last task row number and click "+ insert 1 row below"
Notes:
| 1 | Don't change previous weeks, google sheets has version history. I can see when and who changed a sheet.
| 2 | Don't inflate the time you spend on things. Worse than not investing enough time on the project, is appearing have to wasted time on something that shouldn't take that long.
| 3 | You should fill in your own tasks and review what others have gotten done.
| 4 | If there's ever a problem with a (the) task report(s), you can leave a comment or notify me.
| 5 | Everyone should complete at least one task a week. If one or two members appear to be doing all the work, your team should consider reevaluating your task delegation.

## Week 13
Date | [24 empty] | Unassigned
2022-04-06 | Timothy Giroux |  | tlg292@nau.edu |  |  |  | Kyle Steven Austria |  | kaa474@nau.edu |  |  |  | Gustavo Valencia |  | gmv43@nau.edu |  |  |  | Pengfei Liu |  | pl384@nau.edu |  |  |  | --
2022-04-13 | Task Name | Description & Expected Outcome | Start Date | Due Date | Actual Time (hr) | Progress | Task Name | Description & Expected Outcome | Start Date | Due Date | Actual Time (hr) | Progress | Task Name | Description & Expected Outcome | Start Date | Due Date | Actual Time (hr) | Progress | Task Name | Description & Expected Outcome | Start Date | Due Date | Actual Time (hr) | Progress | Task Name | Description & Expected Outcome | Start Date | Due Date | Actual Time (hr) | Progress
Done
1 | Finalize Testing Plan Section | Finalize Unit Testing section of the Testing Plan document | 2022-03-28 | 2022-04-01 | 4 | 100% | Finalize Testing Plan Section | Finalize Unit Introduction and Conclusion sections of the Testing Plan document | 2022-03-28 | 2022-04-01 | 4 | 100% | Finalize Testing Plan Section | Finalize Usability Testing section of the Testing Plan document | 2022-03-28 | 2022-04-01 | 4 | 100% | Finalize Testing Plan Section | Finalize Integration Testing section of the Testing Plan document | 2022-03-28 | 2022-04-01 | 4 | 100%
2 | Draft Design Review 3 Sections | Complete a draft for respective Design Review 3 Presentation sections | 2022-03-30 | 2022-04-06 | 4 | 100% | Draft Design Review 3 Sections | Complete a draft for respective Design Review 3 Presentation sections | 2022-03-30 | 2022-04-06 | 4 | 100% | Draft Design Review 3 Sections | Complete a draft for respective Design Review 3 Presentation sections | 2022-03-30 | 2022-04-06 | 4 | 100% | Draft Design Review 3 Sections | Complete a draft for respective Design Review 3 Presentation sections | 2022-03-30 | 2022-04-06 | 4 | 100%
3
4
8 | Actual Total Time: |  |  |  | 8 | hrs | Actual Total Time: |  |  |  | 8 | hrs | Actual Total Time: |  |  |  | 8 | hrs | Actual Total Time: |  |  |  | 8 | hrs | Actual Total Time: |  |  |  | 0 | hrs
Todo | Task Name | Description & Expected Outcome | Start Date | Due Date | Expected Time | Progress | Task Name | Description & Expected Outcome | Start Date | Due Date | Expected Time | Progress | Task Name | Description & Expected Outcome | Start Date | Due Date | Expected Time | Progress | Task Name | Description & Expected Outcome | Start Date | Due Date | Expected Time | Progress | Task Name | Description & Expected Outcome | Start Date | Due Date | Expected Time | Progress
1 | Finalize Design Review 3 Sections | Finalize respective Design Review 3 Presentation sections | 2022-04-06 | 2022-04-08 | 2 | 100% | Finalize Design Review 3 Sections | Finalize respective Design Review 3 Presentation sections | 2022-04-06 | 2022-04-08 | 1 | 100% | Finalize Design Review 3 Sections | Finalize respective Design Review 3 Presentation sections | 2022-04-06 | 2022-04-08 | 1 | 100% | Finalize Design Review 3 Sections | Finalize respective Design Review 3 Presentation sections | 2022-04-06 | 2022-04-08 | 1 | 100%
2 | [6 empty] | Rehearse Design Review 3 Presentation | Rehearse presentation with team so that the team is well prepared for the live presentation | 2022-04-06 | 2022-04-08 | 4 | 100% | Rehearse Design Review 3 Presentation | Rehearse presentation with team so that the team is well prepared for the live presentation | 2022-04-06 | 2022-04-08 | 4 | 100% | Rehearse Design Review 3 Presentation | Rehearse presentation with team so that the team is well prepared for the live presentation | 2022-04-06 | 2022-04-08 | 4 | 100%
3
4
2 | Expected Total Time: |  |  |  | 2 | hrs | Expected Total Time: |  |  |  | 5 | hrs | Expected Total Time: |  |  |  | 5 | hrs | Expected Total Time: |  |  |  | 5 | hrs | Expected Total Time: |  |  |  | 0 | hrs
Upcoming | Task Name | Description & Expected Outcome | Start Date | Due Date | Expected Time | Progress | Task Name | Description & Expected Outcome | Start Date | Due Date | Expected Time | Progress | Task Name | Description & Expected Outcome | Start Date | Due Date | Expected Time | Progress | Task Name | Description & Expected Outcome | Start Date | Due Date | Expected Time | Progress | Task Name | Description & Expected Outcome | Start Date | Due Date | Expected Time | Progress
1 | Miscellaneous UGRADS Assignments | Start working on project mini-video, finalized team website, capstone poster, and capstone presentation | 2022-04-13 | 2022-04-20 | 8 |  | Miscellaneous UGRADS Assignments | Start working on project mini-video, finalized team website, capstone poster, and capstone presentation | 2022-04-13 | 2022-04-20 | 8 |  | Miscellaneous UGRADS Assignments | Start working on project mini-video, finalized team website, capstone poster, and capstone presentation | 2022-04-13 | 2022-04-20 | 8 |  | Miscellaneous UGRADS Assignments | Start working on project mini-video, finalized team website, capstone poster, and capstone presentation | 2022-04-13 | 2022-04-20 | 8
2
3
4
8 | Expected Total Time: |  |  |  | 8 | hrs | Expected Total Time: |  |  |  | 8 | hrs | Expected Total Time: |  |  |  | 8 | hrs | Expected Total Time: |  |  |  | 8 | hrs | Expected Total Time: |  |  |  | 0 | hrs
| Additional comments questions or concerns: | [5 empty] | Additional comments questions or concerns: | [5 empty] | Additional comments questions or concerns: | [5 empty] | Additional comments questions or concerns: | [5 empty] | Additional comments questions or concerns:
DR3 content and length concerns.
Current Major Deliverables:
| 1 | DR3 | [5 empty] | Gantt Chart | [5 empty] | Commit History
| 2 | [6 empty] | https://docs.google.com/spreadsheets/d/1f7RZwt7m7hIaU-dNwV-3LjXIOoSCrCGt7WCVYpEjwIY/edit?usp=sharing | [5 empty] | https://github.com/NAU-SuperGeeks/geeksurvey/graphs/contributors
| 3 | [12 empty] | https://github.com/NAU-SuperGeeks/www_supergeeks/graphs/contributors
4
etc
Instructions:
| 1 | Every week your team should fill out the "Next Week" and "Upcoming" section together.
| 2 | You should fill in your respective "This Week" section as you finish your individual tasks.
| 3 | The unassigned section is mostly for upcoming tasks that the team has not delegated. If you have time and have not done many tasks this week, you might want to pick up an unassigned task.
| 4 | Record how long each task took in the time column. Actual time should be recorded when the task is finished (i.e. in the This Week section). Expected time should be recorded when the task is assigned (i.e. in the Next Week section).
| 5 | Times should be recorded in hrs. E.g. if a task took 1/2 an hour put 0.5, if a task takes 10 minutes put 0.17, ect.
| 6 | When adding a task right click last task row number and click "+ insert 1 row below"
Notes:
| 1 | Don't change previous weeks, google sheets has version history. I can see when and who changed a sheet.
| 2 | Don't inflate the time you spend on things. Worse than not investing enough time on the project, is appearing have to wasted time on something that shouldn't take that long.
| 3 | You should fill in your own tasks and review what others have gotten done.
| 4 | If there's ever a problem with a (the) task report(s), you can leave a comment or notify me.
| 5 | Everyone should complete at least one task a week. If one or two members appear to be doing all the work, your team should consider reevaluating your task delegation.

## Week 14
Date | [24 empty] | Unassigned
2022-04-13 | Timothy Giroux |  | tlg292@nau.edu |  |  |  | Kyle Steven Austria |  | kaa474@nau.edu |  |  |  | Gustavo Valencia |  | gmv43@nau.edu |  |  |  | Pengfei Liu |  | pl384@nau.edu |  |  |  | --
2022-04-20 | Task Name | Description & Expected Outcome | Start Date | Due Date | Actual Time (hr) | Progress | Task Name | Description & Expected Outcome | Start Date | Due Date | Actual Time (hr) | Progress | Task Name | Description & Expected Outcome | Start Date | Due Date | Actual Time (hr) | Progress | Task Name | Description & Expected Outcome | Start Date | Due Date | Actual Time (hr) | Progress | Task Name | Description & Expected Outcome | Start Date | Due Date | Actual Time (hr) | Progress
Done
1 | Finalize Design Review 3 Sections | Finalize respective Design Review 3 Presentation sections | 2022-04-06 | 2022-04-08 | 2 | 100% | Finalize Design Review 3 Sections | Finalize respective Design Review 3 Presentation sections | 2022-04-06 | 2022-04-08 | 1 | 100% | Finalize Design Review 3 Sections | Finalize respective Design Review 3 Presentation sections | 2022-04-06 | 2022-04-08 | 1 | 100% | Finalize Design Review 3 Sections | Finalize respective Design Review 3 Presentation sections | 2022-04-06 | 2022-04-08 | 1 | 100%
2 | [6 empty] | Rehearse Design Review 3 Presentation | Rehearse presentation with team so that the team is well prepared for the live presentation | 2022-04-06 | 2022-04-08 | 4 | 100% | Rehearse Design Review 3 Presentation | Rehearse presentation with team so that the team is well prepared for the live presentation | 2022-04-06 | 2022-04-08 | 4 | 100% | Rehearse Design Review 3 Presentation | Rehearse presentation with team so that the team is well prepared for the live presentation | 2022-04-06 | 2022-04-08 | 4 | 100%
3
4
2 | Actual Total Time: |  |  |  | 2 | hrs | Actual Total Time: |  |  |  | 5 | hrs | Actual Total Time: |  |  |  | 5 | hrs | Actual Total Time: |  |  |  | 5 | hrs | Actual Total Time: |  |  |  | 0 | hrs
Todo | Task Name | Description & Expected Outcome | Start Date | Due Date | Expected Time | Progress | Task Name | Description & Expected Outcome | Start Date | Due Date | Expected Time | Progress | Task Name | Description & Expected Outcome | Start Date | Due Date | Expected Time | Progress | Task Name | Description & Expected Outcome | Start Date | Due Date | Expected Time | Progress | Task Name | Description & Expected Outcome | Start Date | Due Date | Expected Time | Progress
1 | Miscellaneous UGRADS Assignments | Start working on project mini-video, finalized team website, capstone poster, and capstone presentation | 2022-04-13 | 2022-04-20 | 6 | 100% | Miscellaneous UGRADS Assignments | Start working on project mini-video, finalized team website, capstone poster, and capstone presentation | 2022-04-13 | 2022-04-20 | 8 | 100% | Miscellaneous UGRADS Assignments | Start working on project mini-video, finalized team website, capstone poster, and capstone presentation | 2022-04-13 | 2022-04-20 | 8 | 100% | Miscellaneous UGRADS Assignments | Start working on project mini-video, finalized team website, capstone poster, and capstone presentation | 2022-04-13 | 2022-04-20 | 8 | 100%
2 | Write GeekSurvey Tests | Write tests for the geeksurvey codebase | 2022-04-13 | 2022-04-20 | 2 | 100%
3
4
8 | Expected Total Time: |  |  |  | 8 | hrs | Expected Total Time: |  |  |  | 8 | hrs | Expected Total Time: |  |  |  | 8 | hrs | Expected Total Time: |  |  |  | 8 | hrs | Expected Total Time: |  |  |  | 0 | hrs
Upcoming | Task Name | Description & Expected Outcome | Start Date | Due Date | Expected Time | Progress | Task Name | Description & Expected Outcome | Start Date | Due Date | Expected Time | Progress | Task Name | Description & Expected Outcome | Start Date | Due Date | Expected Time | Progress | Task Name | Description & Expected Outcome | Start Date | Due Date | Expected Time | Progress | Task Name | Description & Expected Outcome | Start Date | Due Date | Expected Time | Progress
1 | Complete Miscellaneous UGRADS Assignments | Finish work on project mini-video, finalized team website, capstone poster, and capstone presentation | 2022-04-20 | 2022-04-22 | 8 |  | Complete Miscellaneous UGRADS Assignments | Finish work on project mini-video, finalized team website, capstone poster, and capstone presentation | 2022-04-20 | 2022-04-22 | 8 |  | Complete Miscellaneous UGRADS Assignments | Finish work on project mini-video, finalized team website, capstone poster, and capstone presentation | 2022-04-20 | 2022-04-22 | 8 |  | Complete Miscellaneous UGRADS Assignments | Finish work on project mini-video, finalized team website, capstone poster, and capstone presentation | 2022-04-20 | 2022-04-22 | 8
2 | Draft Final Product Acceptance Demo | Start work on the final product acceptance demo | 2022-04-20 | 2022-04-27 | 2 |  | Draft Final Product Acceptance Demo | Start work on the final product acceptance demo | 2022-04-20 | 2022-04-27 | 2 |  | Draft Final Product Acceptance Demo | Start work on the final product acceptance demo | 2022-04-20 | 2022-04-27 | 2 |  | Draft Final Product Acceptance Demo | Start work on the final product acceptance demo | 2022-04-20 | 2022-04-27 | 2
3
4
10 | Expected Total Time: |  |  |  | 10 | hrs | Expected Total Time: |  |  |  | 10 | hrs | Expected Total Time: |  |  |  | 10 | hrs | Expected Total Time: |  |  |  | 10 | hrs | Expected Total Time: |  |  |  | 0 | hrs
| Additional comments questions or concerns: | [5 empty] | Additional comments questions or concerns: | [5 empty] | Additional comments questions or concerns: | [5 empty] | Additional comments questions or concerns: | [5 empty] | Additional comments questions or concerns:
UGRADS Poster Content
Current Major Deliverables:
| 1 | Completed Team Website | [5 empty] | Gantt Chart | [5 empty] | Commit History
| 2 | Capstone Poster | [5 empty] | https://docs.google.com/spreadsheets/d/1f7RZwt7m7hIaU-dNwV-3LjXIOoSCrCGt7WCVYpEjwIY/edit?usp=sharing | [5 empty] | https://github.com/NAU-SuperGeeks/geeksurvey/graphs/contributors
| 3 | Capstone Presentation + Dry Run | [11 empty] | https://github.com/NAU-SuperGeeks/www_supergeeks/graphs/contributors
| 4 | Project Mini-Video
etc
Instructions:
| 1 | Every week your team should fill out the "Next Week" and "Upcoming" section together.
| 2 | You should fill in your respective "This Week" section as you finish your individual tasks.
| 3 | The unassigned section is mostly for upcoming tasks that the team has not delegated. If you have time and have not done many tasks this week, you might want to pick up an unassigned task.
| 4 | Record how long each task took in the time column. Actual time should be recorded when the task is finished (i.e. in the This Week section). Expected time should be recorded when the task is assigned (i.e. in the Next Week section).
| 5 | Times should be recorded in hrs. E.g. if a task took 1/2 an hour put 0.5, if a task takes 10 minutes put 0.17, ect.
| 6 | When adding a task right click last task row number and click "+ insert 1 row below"
Notes:
| 1 | Don't change previous weeks, google sheets has version history. I can see when and who changed a sheet.
| 2 | Don't inflate the time you spend on things. Worse than not investing enough time on the project, is appearing have to wasted time on something that shouldn't take that long.
| 3 | You should fill in your own tasks and review what others have gotten done.
| 4 | If there's ever a problem with a (the) task report(s), you can leave a comment or notify me.
| 5 | Everyone should complete at least one task a week. If one or two members appear to be doing all the work, your team should consider reevaluating your task delegation.

## Week 15
Date | [24 empty] | Unassigned
2022-04-20 | Timothy Giroux |  | tlg292@nau.edu |  |  |  | Kyle Steven Austria |  | kaa474@nau.edu |  |  |  | Gustavo Valencia |  | gmv43@nau.edu |  |  |  | Pengfei Liu |  | pl384@nau.edu |  |  |  | --
2022-04-27 | Task Name | Description & Expected Outcome | Start Date | Due Date | Actual Time (hr) | Progress | Task Name | Description & Expected Outcome | Start Date | Due Date | Actual Time (hr) | Progress | Task Name | Description & Expected Outcome | Start Date | Due Date | Actual Time (hr) | Progress | Task Name | Description & Expected Outcome | Start Date | Due Date | Actual Time (hr) | Progress | Task Name | Description & Expected Outcome | Start Date | Due Date | Actual Time (hr) | Progress
Done
1 | Miscellaneous UGRADS Assignments | Start working on project mini-video, finalized team website, capstone poster, and capstone presentation | 2022-04-13 | 2022-04-20 | 6 | 100% | Miscellaneous UGRADS Assignments | Start working on project mini-video, finalized team website, capstone poster, and capstone presentation | 2022-04-13 | 2022-04-20 | 8 | 100% | Miscellaneous UGRADS Assignments | Start working on project mini-video, finalized team website, capstone poster, and capstone presentation | 2022-04-13 | 2022-04-20 | 8 | 100% | Miscellaneous UGRADS Assignments | Start working on project mini-video, finalized team website, capstone poster, and capstone presentation | 2022-04-13 | 2022-04-20 | 8 | 100%
2 | Write GeekSurvey Tests | Write tests for the geeksurvey codebase | 2022-04-13 | 2022-04-20 | 2 | 100%
3
4
8 | Actual Total Time: |  |  |  | 8 | hrs | Actual Total Time: |  |  |  | 8 | hrs | Actual Total Time: |  |  |  | 8 | hrs | Actual Total Time: |  |  |  | 8 | hrs | Actual Total Time: |  |  |  | 0 | hrs
Todo | Task Name | Description & Expected Outcome | Start Date | Due Date | Expected Time | Progress | Task Name | Description & Expected Outcome | Start Date | Due Date | Expected Time | Progress | Task Name | Description & Expected Outcome | Start Date | Due Date | Expected Time | Progress | Task Name | Description & Expected Outcome | Start Date | Due Date | Expected Time | Progress | Task Name | Description & Expected Outcome | Start Date | Due Date | Expected Time | Progress
1 | Complete Miscellaneous UGRADS Assignments | Finish work on finalized team website, capstone poster, and capstone presentation | 2022-04-20 | 2022-04-22 | 8 | 100% | Complete Miscellaneous UGRADS Assignments | Finish work on finalized team website, capstone poster, and capstone presentation | 2022-04-20 | 2022-04-22 | 8 | 100% | Complete Miscellaneous UGRADS Assignments | Finish work on finalized team website, capstone poster, and capstone presentation | 2022-04-20 | 2022-04-22 | 8 | 100% | Complete Miscellaneous UGRADS Assignments | Finish work on finalized team website, capstone poster, and capstone presentation | 2022-04-20 | 2022-04-22 | 8 | 100%
2 | Draft Final Product Acceptance Demo | Start work on the final product acceptance demo | 2022-04-20 | 2022-04-27 | 2 | 100% | Draft Final Product Acceptance Demo | Start work on the final product acceptance demo | 2022-04-20 | 2022-04-27 | 2 | 100% | Draft Final Product Acceptance Demo | Start work on the final product acceptance demo | 2022-04-20 | 2022-04-27 | 2 | 100% | Draft Final Product Acceptance Demo | Start work on the final product acceptance demo | 2022-04-20 | 2022-04-27 | 2 | 100%
3 | [12 empty] | Conduct Usability Testing Interviews | Conduct two usability testing interviews with users with a technical or research background. Results and feedback should be properly and professionally noted in the usability testing documents. | 2022-04-20 | 2022-04-22 | 3 | 100%
4
10 | Expected Total Time: |  |  |  | 10 | hrs | Expected Total Time: |  |  |  | 10 | hrs | Expected Total Time: |  |  |  | 13 | hrs | Expected Total Time: |  |  |  | 10 | hrs | Expected Total Time: |  |  |  | 0 | hrs
Upcoming | Task Name | Description & Expected Outcome | Start Date | Due Date | Expected Time | Progress | Task Name | Description & Expected Outcome | Start Date | Due Date | Expected Time | Progress | Task Name | Description & Expected Outcome | Start Date | Due Date | Expected Time | Progress | Task Name | Description & Expected Outcome | Start Date | Due Date | Expected Time | Progress | Task Name | Description & Expected Outcome | Start Date | Due Date | Expected Time | Progress
1 | Complete Final Product Acceptance Demo | Finish work on the final product acceptance demo | 2022-04-27 | 2022-04-29 | 2 |  | Complete Final Product Acceptance Demo | Finish work on the final product acceptance demo | 2022-04-27 | 2022-04-29 | 2 |  | Complete Final Product Acceptance Demo | Finish work on the final product acceptance demo | 2022-04-27 | 2022-04-29 | 2 |  | Complete Final Product Acceptance Demo | Finish work on the final product acceptance demo | 2022-04-27 | 2022-04-29 | 2
2 | Complete Project Mini-Video | Finish work on the project mini-video | 2022-04-27 | 2022-04-29 | 2 |  | Complete Project Mini-Video | Finish work on the project mini-video | 2022-04-27 | 2022-04-29 | 2 |  | Complete Project Mini-Video | Finish work on the project mini-video | 2022-04-27 | 2022-04-29 | 2 |  | Complete Project Mini-Video | Finish work on the project mini-video | 2022-04-27 | 2022-04-29 | 2
3 | Project Delivery Assignments | Work on final project report, user manual and completed/signed checkoff sheet, and the team reflection document | 2022-04-27 | 2022-05-05 | 8 |  | Project Delivery Assignments | Work on final project report, user manual and completed/signed checkoff sheet, and the team reflection document | 2022-04-27 | 2022-05-05 | 8 |  | Project Delivery Assignments | Work on final project report, user manual and completed/signed checkoff sheet, and the team reflection document | 2022-04-27 | 2022-05-05 | 8 |  | Project Delivery Assignments | Work on final project report, user manual and completed/signed checkoff sheet, and the team reflection document | 2022-04-27 | 2022-05-05 | 8
4
12 | Expected Total Time: |  |  |  | 12 | hrs | Expected Total Time: |  |  |  | 12 | hrs | Expected Total Time: |  |  |  | 12 | hrs | Expected Total Time: |  |  |  | 12 | hrs | Expected Total Time: |  |  |  | 0 | hrs
| Additional comments questions or concerns: | [5 empty] | Additional comments questions or concerns: | [5 empty] | Additional comments questions or concerns: | [5 empty] | Additional comments questions or concerns: | [5 empty] | Additional comments questions or concerns:
Current Major Deliverables:
| 1 | Completed Team Website | [5 empty] | Gantt Chart | [5 empty] | Commit History
| 2 | Capstone Poster | [5 empty] | https://docs.google.com/spreadsheets/d/1f7RZwt7m7hIaU-dNwV-3LjXIOoSCrCGt7WCVYpEjwIY/edit?usp=sharing | [5 empty] | https://github.com/NAU-SuperGeeks/geeksurvey/graphs/contributors
| 3 | Capstone Presentation | [11 empty] | https://github.com/NAU-SuperGeeks/www_supergeeks/graphs/contributors
| 4 | Project Mini-Video
etc
Instructions:
| 1 | Every week your team should fill out the "Next Week" and "Upcoming" section together.
| 2 | You should fill in your respective "This Week" section as you finish your individual tasks.
| 3 | The unassigned section is mostly for upcoming tasks that the team has not delegated. If you have time and have not done many tasks this week, you might want to pick up an unassigned task.
| 4 | Record how long each task took in the time column. Actual time should be recorded when the task is finished (i.e. in the This Week section). Expected time should be recorded when the task is assigned (i.e. in the Next Week section).
| 5 | Times should be recorded in hrs. E.g. if a task took 1/2 an hour put 0.5, if a task takes 10 minutes put 0.17, ect.
| 6 | When adding a task right click last task row number and click "+ insert 1 row below"
Notes:
| 1 | Don't change previous weeks, google sheets has version history. I can see when and who changed a sheet.
| 2 | Don't inflate the time you spend on things. Worse than not investing enough time on the project, is appearing have to wasted time on something that shouldn't take that long.
| 3 | You should fill in your own tasks and review what others have gotten done.
| 4 | If there's ever a problem with a (the) task report(s), you can leave a comment or notify me.
| 5 | Everyone should complete at least one task a week. If one or two members appear to be doing all the work, your team should consider reevaluating your task delegation.

## Week 16
Unassigned
2022-04-27 | Timothy Giroux |  | tlg292@nau.edu |  |  |  | Kyle Steven Austria |  | kaa474@nau.edu |  |  |  | Gustavo Valencia |  | gmv43@nau.edu |  |  |  | Pengfei Liu |  | pl384@nau.edu |  |  |  | --
2022-05-05 | Task Name | Description & Expected Outcome | Start Date | Due Date | Actual Time (hr) | Progress | Task Name | Description & Expected Outcome | Start Date | Due Date | Actual Time (hr) | Progress | Task Name | Description & Expected Outcome | Start Date | Due Date | Actual Time (hr) | Progress | Task Name | Description & Expected Outcome | Start Date | Due Date | Actual Time (hr) | Progress | Task Name | Description & Expected Outcome | Start Date | Due Date | Actual Time (hr) | Progress
Done
1 | Complete Miscellaneous UGRADS Assignments | Finish work on finalized team website, capstone poster, and capstone presentation | 2022-04-20 | 2022-04-22 | 8 | 100% | Complete Miscellaneous UGRADS Assignments | Finish work on finalized team website, capstone poster, and capstone presentation | 2022-04-20 | 2022-04-22 | 8 | 100% | Complete Miscellaneous UGRADS Assignments | Finish work on finalized team website, capstone poster, and capstone presentation | 2022-04-20 | 2022-04-22 | 8 | 100% | Complete Miscellaneous UGRADS Assignments | Finish work on finalized team website, capstone poster, and capstone presentation | 2022-04-20 | 2022-04-22 | 8 | 100%
2 | Draft Final Product Acceptance Demo | Start work on the final product acceptance demo | 2022-04-20 | 2022-04-27 | 2 | 100% | Draft Final Product Acceptance Demo | Start work on the final product acceptance demo | 2022-04-20 | 2022-04-27 | 2 | 100% | Draft Final Product Acceptance Demo | Start work on the final product acceptance demo | 2022-04-20 | 2022-04-27 | 2 | 100% | Draft Final Product Acceptance Demo | Start work on the final product acceptance demo | 2022-04-20 | 2022-04-27 | 2 | 100%
3 | [12 empty] | Conduct Usability Testing Interviews | Conduct two usability testing interviews with users with a technical or research background. Results and feedback should be properly and professionally noted in the usability testing documents. | 2022-04-20 | 2022-04-22 | 3 | 100%
4
10 | Actual Total Time: |  |  |  | 10 | hrs | Actual Total Time: |  |  |  | 10 | hrs | Actual Total Time: |  |  |  | 13 | hrs | Actual Total Time: |  |  |  | 10 | hrs | Actual Total Time: |  |  |  | 0 | hrs
Todo | Task Name | Description & Expected Outcome | Start Date | Due Date | Expected Time | Progress | Task Name | Description & Expected Outcome | Start Date | Due Date | Expected Time | Progress | Task Name | Description & Expected Outcome | Start Date | Due Date | Expected Time | Progress | Task Name | Description & Expected Outcome | Start Date | Due Date | Expected Time | Progress | Task Name | Description & Expected Outcome | Start Date | Due Date | Expected Time | Progress
1 | Complete Final Product Acceptance Demo | Finish work on the final product acceptance demo | 2022-04-27 | 2022-04-29 | 2 | 100% | Complete Final Product Acceptance Demo | Finish work on the final product acceptance demo | 2022-04-27 | 2022-04-29 | 2 | 100% | Complete Final Product Acceptance Demo | Finish work on the final product acceptance demo | 2022-04-27 | 2022-04-29 | 2 | 100% | Complete Final Product Acceptance Demo | Finish work on the final product acceptance demo | 2022-04-27 | 2022-04-29 | 2 | 100%
2 | Complete Project Mini-Video | Finish work on the project mini-video | 2022-04-27 | 2022-04-29 | 2 | 100% | Project Delivery Assignments | Work on final project report, user manual and completed/signed checkoff sheet, and the team reflection document | 2022-04-27 | 2022-05-05 | 8 | 100% | Project Delivery Assignments | Work on final project report, user manual and completed/signed checkoff sheet, and the team reflection document | 2022-04-27 | 2022-05-05 | 8 | 100% | Project Delivery Assignments | Work on final project report, user manual and completed/signed checkoff sheet, and the team reflection document | 2022-04-27 | 2022-05-05 | 8 | 100%
3 | Project Delivery Assignments | Work on final project report, user manual and completed/signed checkoff sheet, and the team reflection document | 2022-04-27 | 2022-05-05 | 8 | 100% | Conduct Usability Testing Interview | Conduct one usability testing interview with user with a technical or research background. Results and feedback should be properly and professionally noted in the usability testing document. | 2022-04-27 | 2022-05-05 | 1.5 | 100% | Conduct Usability Testing Interview | Conduct one usability testing interview with user with a technical or research background. Results and feedback should be properly and professionally noted in the usability testing document. | 2022-04-27 | 2022-05-05 | 1.5 | 100% | Conduct Usability Testing Interview | Conduct one usability testing interview with user with a technical or research background. Results and feedback should be properly and professionally noted in the usability testing document. | 2022-04-27 | 2022-05-05 | 1.5 | 100%
4 | Finalize GitHub Integration | Provide way to clearly distinguish GeekSurvey accounts with and without GitHub integration. | 2022-04-27 | 2022-05-05 | 1.5 | 100%
13.5 | Expected Total Time: |  |  |  | 13.5 | hrs | Expected Total Time: |  |  |  | 11.5 | hrs | Expected Total Time: |  |  |  | 11.5 | hrs | Expected Total Time: |  |  |  | 11.5 | hrs | Expected Total Time: |  |  |  | 0 | hrs
Upcoming | Task Name | Description & Expected Outcome | Start Date | Due Date | Expected Time | Progress | Task Name | Description & Expected Outcome | Start Date | Due Date | Expected Time | Progress | Task Name | Description & Expected Outcome | Start Date | Due Date | Expected Time | Progress | Task Name | Description & Expected Outcome | Start Date | Due Date | Expected Time | Progress | Task Name | Description & Expected Outcome | Start Date | Due Date | Expected Time | Progress
1
2
3
4
0 | Expected Total Time: |  |  |  | 0 | hrs | Expected Total Time: |  |  |  | 0 | hrs | Expected Total Time: |  |  |  | 0 | hrs | Expected Total Time: |  |  |  | 0 | hrs | Expected Total Time: |  |  |  | 0 | hrs
| Additional comments questions or concerns: | [5 empty] | Additional comments questions or concerns: | [5 empty] | Additional comments questions or concerns: | [5 empty] | Additional comments questions or concerns: | [5 empty] | Additional comments questions or concerns:
can we please make the final report a google drive folder or github repo or something. also, can we just not demo to our clients
Current Major Deliverables:
| 1 | Project Mini-Video | [5 empty] | Gantt Chart | [5 empty] | Commit History
| 2 | Final Product Acceptance Demo | [5 empty] | https://docs.google.com/spreadsheets/d/1f7RZwt7m7hIaU-dNwV-3LjXIOoSCrCGt7WCVYpEjwIY/edit?usp=sharing | [5 empty] | https://github.com/NAU-SuperGeeks/geeksurvey/graphs/contributors
| 3 | Final (as-built) Report | [11 empty] | https://github.com/NAU-SuperGeeks/www_supergeeks/graphs/contributors
| 4 | Team Reflection Document
| 5 | Final Project Delivery
| 6 | Product Delivery Check-off Sheet
etc
Instructions:
| 1 | Every week your team should fill out the "Next Week" and "Upcoming" section together.
| 2 | You should fill in your respective "This Week" section as you finish your individual tasks.
| 3 | The unassigned section is mostly for upcoming tasks that the team has not delegated. If you have time and have not done many tasks this week, you might want to pick up an unassigned task.
| 4 | Record how long each task took in the time column. Actual time should be recorded when the task is finished (i.e. in the This Week section). Expected time should be recorded when the task is assigned (i.e. in the Next Week section).
| 5 | Times should be recorded in hrs. E.g. if a task took 1/2 an hour put 0.5, if a task takes 10 minutes put 0.17, ect.
| 6 | When adding a task right click last task row number and click "+ insert 1 row below"
Notes:
| 1 | Don't change previous weeks, google sheets has version history. I can see when and who changed a sheet.
| 2 | Don't inflate the time you spend on things. Worse than not investing enough time on the project, is appearing have to wasted time on something that shouldn't take that long.
| 3 | You should fill in your own tasks and review what others have gotten done.
| 4 | If there's ever a problem with a (the) task report(s), you can leave a comment or notify me.
| 5 | Everyone should complete at least one task a week. If one or two members appear to be doing all the work, your team should consider reevaluating your task delegation.

## Break
Date | [24 empty] | Unassigned
2021-12-13 | Timothy Giroux |  | tlg292@nau.edu |  |  |  | Kyle Steven Austria |  | kaa474@nau.edu |  |  |  | Gustavo Valencia |  | gmv43@nau.edu |  |  |  | Pengfei Liu |  | pl384@nau.edu |  |  |  | --
2022-01-09 | Task Name | Description & Expected Outcome | Start Date | Due Date | Actual Time (hr) | Progress | Task Name | Description & Expected Outcome | Start Date | Due Date | Actual Time (hr) | Progress | Task Name | Description & Expected Outcome | Start Date | Due Date | Actual Time (hr) | Progress | Task Name | Description & Expected Outcome | Start Date | Due Date | Actual Time (hr) | Progress | Task Name | Description & Expected Outcome | Start Date | Due Date | Actual Time (hr) | Progress
Done
1 | User Stories | 1.1, 1.2, 2.1, 2.2, 2.3 | 2021-12-10 | 2022-01-06 | 8 | 100%
2
3
4
8 | Actual Total Time: |  |  |  | 8 | hrs | Actual Total Time: |  |  |  | 0 | hrs | Actual Total Time: |  |  |  | 0 | hrs | Actual Total Time: |  |  |  | 0 | hrs | Actual Total Time: |  |  |  | 0 | hrs
Todo | Task Name | Description & Expected Outcome | Start Date | Due Date | Expected Time | Progress | Task Name | Description & Expected Outcome | Start Date | Due Date | Expected Time | Progress | Task Name | Description & Expected Outcome | Start Date | Due Date | Expected Time | Progress | Task Name | Description & Expected Outcome | Start Date | Due Date | Expected Time | Progress | Task Name | Description & Expected Outcome | Start Date | Due Date | Expected Time | Progress
1
2
3
4
0 | Expected Total Time: |  |  |  | 0 | hrs | Expected Total Time: |  |  |  | 0 | hrs | Expected Total Time: |  |  |  | 0 | hrs | Expected Total Time: |  |  |  | 0 | hrs | Expected Total Time: |  |  |  | 0 | hrs
Upcoming | Task Name | Description & Expected Outcome | Start Date | Due Date | Expected Time | Progress | Task Name | Description & Expected Outcome | Start Date | Due Date | Expected Time | Progress | Task Name | Description & Expected Outcome | Start Date | Due Date | Expected Time | Progress | Task Name | Description & Expected Outcome | Start Date | Due Date | Expected Time | Progress | Task Name | Description & Expected Outcome | Start Date | Due Date | Expected Time | Progress
1
2
3
4
0 | Expected Total Time: |  |  |  | 0 | hrs | Expected Total Time: |  |  |  | 0 | hrs | Expected Total Time: |  |  |  | 0 | hrs | Expected Total Time: |  |  |  | 0 | hrs | Expected Total Time: |  |  |  | 0 | hrs
| Additional comments questions or concerns: | [5 empty] | Additional comments questions or concerns: | [5 empty] | Additional comments questions or concerns: | [5 empty] | Additional comments questions or concerns: | [5 empty] | Additional comments questions or concerns:
Current Major Deliverables:
1
2
3
4
etc
Instructions:
| 1 | Every week your team should fill out the "Next Week" and "Upcoming" section together.
| 2 | You should fill in your respective "This Week" section as you finish your individual tasks.
| 3 | The unassigned section is mostly for upcoming tasks that the team has not delegated. If you have time and have not done many tasks this week, you might want to pick up an unassigned task.
| 4 | Record how long each task took in the time column. Actual time should be recorded when the task is finished (i.e. in the This Week section). Expected time should be recorded when the task is assigned (i.e. in the Next Week section).
| 5 | Times should be recorded in hrs. E.g. if a task took 1/2 an hour put 0.5, if a task takes 10 minutes put 0.17, ect.
| 6 | When adding a task right click last task row number and click "+ insert 1 row below"
Notes:
| 1 | Don't change previous weeks, google sheets has version history. I can see when and who changed a sheet.
| 2 | Don't inflate the time you spend on things. Worse than not investing enough time on the project, is appearing have to wasted time on something that shouldn't take that long.
| 3 | You should fill in your own tasks and review what others have gotten done.
| 4 | If there's ever a problem with a (the) task report(s), you can leave a comment or notify me.
| 5 | Everyone should complete at least one task a week. If one or two members appear to be doing all the work, your team should consider reevaluating your task delegation.