## Start Here
General Guidelines:
1. Be slow, systematic, and precise in testing. If there is not a clear understanding of the system to be tested and expected results, then clarify before testing to avoid damage!
2. Never erase old data, it can be useful for troubleshooting. If you failed a set of tests, put a copy of the test procedure below that one, and repeat the tests!
3. There is example data in these forms. Once you understand what you want to do, replace the example data with your project data.
4. Save your workbook with the Team number and short name (e.g. "15 robot arm")
Instructions:
1 | Complete the glossary below
2 | Insert your system requirements on the "Requirements" tab.
3 | Consider what testing you need to do, and complete the "Type of Test" column for all requirements.
4 | Complete documentation of at least 4 tests: 3 from (UTS, UTM) and one integration test. Copy and modify sheets as necessary
5 | Present an overview of your 4 tests as a PowerPoint presentation on the assigned date. Submit this Excel Workbook for grading.
6 | Complete the actual tests! Record your results and comments. You will pull some of this data to your reports.
7 | Prepare your Testing Report and submit
Glossary
term | definition:
White Box | Testing that is performed with full understanding of the processes happening internally to the unit under testing
Black Box | Testing that is performed without full understanding of the processes happening internally to the unit under testing, where the tester simply provides inputs and observes outputs
Unit Test | A test which gauges the efficacy of a single, self-contained subsystem, in order to assure the expected output is achieved
Matrix Test | A form of testing in which a series of pre-determined, varied inputs which are structurally the same are given to a system to test the function of a single process
Step-by-Step Test | A form of testing in which a series of instructions are performed within a system, perhaps with a single input, which are completed in a number of stages
test coverage | A term used to describe the extent to which a particular module or subsystem is comprehensively tested by a single test
integration testing | Testing that ensures that multiple subsystems within the product function nominally together, as opposed to the performance of individual modules
Acceptance test | Testing that is generally environment-specific, which determines whether the device specifications are satisfactory for the customer or client to accept the product
UUT | "Unit under Test," the particular module or subsystem which is being evaluated

## Requirements
Type of Test | Status | Req # | Requirement
|  | 1 | User Interface
Inspection | PASS | 1.1* | The drone must be operable using a graphical user interface
|  | 1.1.1 | Allows the operator to navigate the drone, configure inspection or navigation settings, or access data from the drone’s flight.
|  | 1.1.2 | This should be written in a common programming language such as Python or MATLAB
Inspection | PASS | 1.2 | The drone should be operable and configurable wirelessly
Inspection | PASS | 1.3 | The user will be able to see both the drone's positional data and video stream during its flight, and be able to issue commands mid-mission
|  | 2 | Image Processing
Integration | FAIL | 2.1* | The drone will use image processing in order to isolate and identify features relevant to the operator, which should be at least 80% accurate
Inspection | FAIL | 2.1.1 | There will be four recognizable features relevant to our project: gutters, windows, walls, and roofs
|  | 2.2 | Each of the structural features will be initially identified by a YOLOv4 neural network, with a reasonable degree of speed and accuracy
Step-by-step | FAIL | 2.2.1* | Each YOLOv4 feature should be recognizable with at least 90% accuracy
|  | 2.2.2 | The YOLOv4 system should output appropriately cropped images to be classified for damage severity
Inspection | PASS | 2.2.3 | In order to accomplish this, the team will collect at least 300 images for each category
|  | 2.3 | A variety of classification neural networks will be run on the detected features, specialized for each feature
Step-by-step | FAIL | 2.3.1 | The damage classifiers should be at least 90% accurate in distinguishing between faulty and intact features
Step-by-step | PASS | 2.4* | Feature detection within the video feed will trigger appropriate commands to be sent via MAVLink
|  | 2.4.1 | The YOLOv4 object detection event will instruct the drone to halt its mission in order to investigate
|  | 2.4.2 | If the feature is classified as defective, the drone will prompt the user to give input, otherwise, the mission will continue
|  | 3 | Drone Assembly
|  | 3.1 | LiPo battery capable of powering drone flight controller, motors, and auxiliary devices
|  | 3.2 | Maneuverable camera mount, capable of 3 degrees of freedom
|  | 3.3 | Flight control systems should strive to communicate over a single unified protocol
Inspection | PASS | 3.4 | Power should be supplied to all auxiliary components via the same power distribution board
|  | 3.5 | Drone will stream analog video data in real time to the ground control station
|  | 4 | Flight Path Navigation
| PASS | 4.1 | The drone must be operable using a remote controller
| PASS | 4.2 | The drone must be capable of semi-autonomous flight (not directly navigated by remote control)
| PASS | 4.2.1 | The mission flight mode will receive and quickly react to events in the form of MAVLink instructions
| PASS | 4.2.2 | The drone is capable of safe takeoff/landing protocols
|  | 4.2.3 | The drone's mission flight mode allows for the designation of regions of interest for surveying

## UTS, YOLOv4 Object Recognition
Test number | 1
Requirement Tested: | 2.2.1 | Each YOLOv4 feature should be recognizable with at least 90% accuracy
Test Case name: | YOLOv4 Object Recognition
Type | Black Box
Hardware version: | v1.0 | Tester: Noah Levie |  | Date: 3/16/21
Setup instructions: | Use the group's currently generated obj-weights file to initiate the YOLOv4 configuration and setup. Create a directory with test images that will each be inputted to the YOLO network, with at least two examples each of intact features and broken features.
Results
Test | Action | Expected Result | Pass | Fail | N/A | Comments
1 | Test the mean average precision of the YOLO classifier, using a pre-made test dataset | mAP should be at least 80% |  | mAP = 78.85%
2 | Test the average precision of window class detection | AP should be at least 80% |  | FALSE - AP=83.68%
3 | Feed in image without any trained features | Output should have no detections | TRUE
4 | Feed in image with one broken window | Model should detect and draw a box around the window | TRUE - Confidence=96%
5 | Feed in image with two broken window | Model should detect and draw a box around both of the windows | TRUE - Avg. Conf.=91%
6 | Feed in an image with one intact window | Model should detect and draw a box around the window | TRUE - Confidence=98%
7 | Feed in an image with two intact windows | Model should detect and draw a box around both of the windows | TRUE - Avg. Conf.=94%
8 | Test the average precision of gutter class detection | AP should be at least 80% |  | FALSE - AP=74.02%
9 | Feed in image with one clogged gutter | Model should detect and draw a box around the gutter | TRUE - Confidence=82%
10 | Feed in image with one clogged gutter | Model should detect and draw a box around the gutter |  | FALSE - Confidence=68%
11 | Feed in image with one clear gutter | Model should detect and draw a box around the gutter | TRUE - Confidence=84%
12 | Feed in image with one clear gutter | Model should detect and draw a box around the gutter | TRUE - Confidence=81%

## UTS, Damage Severity Classifier
Test number | 2
Requirement Tested: | 2.3.1 | The damage classifier should be at least 90% accurate in distinguishing between faulty and intact features
Test Case name: | Damage Severity Classifier
Type | Black Box
Hardware version: | v1.0 | Tester: Noah |  | Date: 3/18/21
Setup instructions: | Use the trained YOLO network to automatically crop images so that they just contain the feature we are trying to classify. Verify manually that all images are correct. Feed the image through its corresponding classifier network and verify that the model got it correctly.
Results
Step | Action | Expected Result | Pass | Fail | N/A | Comments
1 | Input cropped broken window | The image should be classified as defective | TRUE - Conf.=72%
2 | Input cropped unbroken window | The image should be classified as nominal | TRUE - Conf.=67%
3 | Run mean average precision (MAP) calculation on window test dataset | The result should be at least 80% |  | FALSE - AP=71% |  | These values should be improved with additional convolutional layers
4 | Input cropped full gutter | The image should be classified as defective | TRUE - Conf.=62%
5 | Input cropped clean gutter | The image should be classified as nominal | TRUE - Conf.=68%
6 | Run mean average precision (MAP) calculation on gutter test dataset | The result should be at least 80% |  | FALSE - AP=68% |  | These values should be improved with additional convolutional layers

## UTS, Action Generation
Test number | 3
Requirement Tested: | 2.4.2 | If the feature is classified as defective, the drone will prompt the user to give input, otherwise, the mission will continue
Test Case name: | Action Generation
Type | White Box
Hardware version: | v1.0 | Tester: Daniel |  | Date: 3/24/2021
Setup instructions: | The tester will stimulate the action generation model with different inputs, analyse the internal program logic, and make sure that the drone properly responds in the event of either a nominal or defective feature. Using the Gazebo flight simulation software, we simulate a building inspection mission and manually introduce various recognition stimuli. These include different commands indicating the detection of a defective/nominal window or gutter. The drone should then react accordingly, either prompting user input or continuing the mission.
Results
Step | Action | Expected Result | Pass | Fail | N/A | Comments
1 | Simulate defective gutters | Drone flight should be halted and the user should receive a prompt to continue mission or wait | TRUE
2 | Simulate nominal gutters | Mission should continue without interruption | TRUE
3 | Simulate defective gutters | Drone flight should be halted and the user should receive a prompt to continue mission or wait | TRUE
4 | Simulate nominal gutters | Mission should continue without interruption | TRUE
5 | Simulate defective windows | Drone flight should be halted and the user should receive a prompt to continue mission or wait | TRUE
6 | Simulate nominal windows | Mission should continue without interruption | TRUE
7 | Simulate defective windows | Drone flight should be halted and the user should receive a prompt to continue mission or wait | TRUE
8 | Simulate nominal windows | Mission should continue without interruption | TRUE

## UTM, Classifier Optimization
Test number | 4
Requirement Tested: | 2.3.1* | The damage classifiers should be at least 90% accurate in distinguishing between faulty and intact features
Test Case name: | Damage Severity Classifier Optimization
Type | Black Box
Hardware version: | v1.0 | Tester: Noah Levie |  | Date: 3/24/21
Setup instructions: | Using a series of nested for-loops, we will configure and train 27 different models on the same image dataset. We are using an image input size of 128x128 pixels, normalizing the training and testing data as necessary. We are furthermore using a batch size of 8, due to a relatively small dataset of 300 images of windows, and 15 epochs to avoid overfitting, as we have found previously. This will allow us to determine which configuration is the most effective for analyzing window images.
| Input |  |  | Results
Test | Number of Convolutional Layers | Number of Nodes Per Layer | Number of Dense Layers | Validation Loss - Validation Accuracy | Comments
1 | 1 | 32 | 0 | 1.2203 - 0.6511
2 | 2 | 32 | 0 | 0.6418 - 0.6889
3 | 3 | 32 | 0 | 0.5105 - 0.7642
4 | 1 | 64 | 0 | 1.3210 - 0.6410
5 | 2 | 64 | 0 | 0.6124 - 0.7161
6 | 3 | 64 | 0 | 0.5116 - 0.7724
7 | 1 | 128 | 0 | 1.4319 - 0.6415
8 | 2 | 128 | 0 | 0.6958 - 0.6288
9 | 3 | 128 | 0 | 0.6866 - 0.7345
10 | 1 | 32 | 1 | 0.6932 - 0.4973
11 | 2 | 32 | 1 | 0.6932 - 0.4973
12 | 3 | 32 | 1 | 0.5162 - 0.7703
13 | 1 | 64 | 1 | 0.6931 - 0.5029
14 | 2 | 64 | 1 | 1.2960 - 0.6976
15 | 3 | 64 | 1 | 0.5247 - 0.7782
16 | 1 | 128 | 1 | 1.4192 - 0.6581
17 | 2 | 128 | 1 | 0.7285 - 0.5406
18 | 3 | 128 | 1 | 0.4830 - 0.8060 | Highest Val Accuracy (0.8060), low overfit (0.0692), best configuration
19 | 1 | 32 | 2 | 1.0445 - 0.6843
20 | 2 | 32 | 2 | 0.5616 - 0.7500
21 | 3 | 32 | 2 | 0.4792 - 0.7831
22 | 1 | 64 | 2 | 1.3918 - 0.6716
23 | 2 | 64 | 2 | 0.7490 - 0.7324
24 | 3 | 64 | 2 | 0.5257 - 0.7972
25 | 1 | 128 | 2 | 1.3729 - 0.6811
26 | 2 | 128 | 2 | 1.2811 - 0.6729
27 | 3 | 128 | 2 | 0.5495 - 0.7897

## Integration, Feature Detection
Test number | 5
Requirements Tested: | 2.1* | The drone will use image processing in order to isolate and identify features relevant to the operator, which should be at least 80% accurate
| 2.2.1* | Each YOLOv4 feature should be recognizable with at least 90% accuracy
| 2.2.2 | The YOLOv4 system should output appropriately cropped images to be classified for damage severity
| 2.3.1 | The damage classifiers should be at least 90% accurate in distinguishing between faulty and intact features
| 2.4* | Feature detection within the video feed will trigger appropriate commands to be sent via MAVLink
Test Case name: | Feature Detection System Analysis
Type | Black Box
Hardware version: | v1.0 | Tester: Daniel Copley |  | Date:3/24/21
Setup instructions: | This test is designed to test the smooth cooperation and flow of data through the various image data processing components. We will be using various individual images to observe the latency and reliability of the overall system. Multiple steps are more binary, in the sense that we are evaluating whether they work or break, such as the cropping step. We have configured the main program to receive an image, call a YOLOv4 detection, crop the image with OpenCV based on the bounding box coordinates, pass the cropped image to the appropriate damage classifier, display the image, and output the proper command with regard to whether the feature in the image is nominal or defective.
Results
Step | Action | Expected Result | Pass | Fail | N/A | Comments
1 | Import an image of a broken window | Display the original image | Pass
2 | Run a YOLOv4 detection | Detect a broken window and draw appropriate bounding box | Pass
3 | Crop the image by outputted bounding box coordinates | Display cropped image | Pass
4 | Run a damage classification | Detect a defective window | Pass
5 | Display original image with detection label and bounding box | Display the original image labeled "Broken Window" with appropriate bounding box |  | Fail - detected as nominal
6 | Output corresponding command to drone and user interface | Instruct "drone" to pause flight and await user input to continue |  |  | N/A
7 | Import an image of a clogged gutter | Display the original image | Pass
8 | Run a YOLOv4 detection | Detect a clogged gutter and draw appropriate bounding box |  | Fail - did not detect
9 | Crop the image by outputted bounding box coordinates | Display cropped image |  |  | N/A
10 | Run a damage classification | Detect a defective gutter |  |  | N/A
11 | Display original image with detection label and bounding box | Display the original image labeled "clogged gutter" with appropriate bounding box |  |  | N/A
12 | Output corresponding command to drone and user interface | Instruct "drone" to pause flight and await user input to continue |  |  | N/A
13 | Import an image of an intact window | Display the original image | Pass
14 | Run a YOLOv4 detection | Detect an intact window and draw appropriate bounding box | Pass
15 | Crop the image by outputted bounding box coordinates | Display cropped image | Pass
16 | Run a damage classification | Detect a nominal window | Pass
17 | Display original image with detection label and bounding box | Display the original image labeled "Intact Window" with appropriate bounding box | Pass
18 | Output corresponding command to drone and user interface | Instruct "drone" to continue mission | Pass
19 | Import an image of a clean gutter | Display the original image | Pass
20 | Run a YOLOv4 detection | Detect a clean gutter and draw appropriate bounding box | Pass
21 | Crop the image by outputted bounding box coordinates | Display cropped image | Pass
22 | Run a damage classification | Detect a nominal gutter | Pass
23 | Display original image with detection label and bounding box | Display the original image labeled "Clean Gutter" with appropriate bounding box | Pass
24 | Output corresponding command to drone and user interface | Instruct "drone" to continue mission | Pass