# MEETING MINUTES

# Topic:  Progress Report

## Friday, October 18, 2019

## 12:00 pm– 3:00 pm

Minutes recorded by _Rachel Watanabe_________________

Meeting called by Rachel Watanabe

Attendees: Rachel Watanabe, Toren Schurb (was early but left for 10 minutes when it was meeting start time), and Jayne Sandoval (came at 12:30 pm)

Please bring:	Laptops/device to access online team docs; information to help fill out the pre-determined sections in the report; bring in finished sections you were assigned

Table 1.  Record of meeting.

| ## 12:00 pm to end | Work on Progress Report - Discussion led by Rachel Watanabe - Everyone worked on their individual assigned sections - Jayne: finished most of her sections - Rachel: finished most of her sections - Toren: still has more than half of his sections left | South Starbucks |
| --- | --- | --- |

Table 2.  Tasks Assigned.

| Task | Person Assigned | Due Date | Date Complete |
| --- | --- | --- | --- |
| Look into what the comparable wind farms are doing in terms of wildlife | Jayne | Original: 9/25/19 Extended: 10/20/19 |  |
| Work on Progress Report (Presentation 1 info) | Everyone | Original: 9/27/19 Extended: 10/18/19 |  |
| Work on Progress Report (Second half of the report) | Everyone | Original: 10/11/19 Extended: 10/18/19 |  |
| Work on Presentation 2 | Everyone | Original: 10/4/19 Extended: 10/7/19 | 10/7/19 |
| Practice for Presentation 2 | Everyone | 10/7/19 | 10/6/19 |
| Concept Generations for micro siting | Everyone | 10/2/19 | 10/2/19 |
| Create Openwind Presentation for Energy Club | Everyone | 10/14/19 | 10/15/19 |
| Start grabbing data files for team to use in Openwind (at least know where the team can get the files) | Jayne | Orignal: 10/14/19 Extended: 10/23/19 |  |

Next formal meeting:  10/18/19, Cline Libary, at 7:00 pm.