# MEETING MINUTES

# Topic:  Presentation 1 and Client Meeting

## Friday, September 13, 2019

## 11:30 am – 2:00 pm

Minutes recorded by _Rachel Watanabe_________________

Meeting called by Rachel Watanabe

Attendees: Rachel Watanabe, Toren Schurb and Jayne Sandoval

Please bring:	Laptops/device to access online team docs; Read and bring CWC 2020 Rule book w/questions; information to help fill out the presentation slides

Table 1.  Record of meeting.

| ## 11:30 am to 12:00 pm | Presentation 1 - Discussion led by Rachel Watanabe - Discussed new information that was found - organized slides and inserted information | EGR Internet Cafe |
| --- | --- | --- |
| ## 12:00 pm to 12:30 pm | ## Client Meeting with Professor Willy - Discussion led by Professor Willy - Asked more questions about the rules - Discussed what was the expected process for the team - Was told that the full version of the program we are to use is no longer free from the company and the competition is fighting to get access; however, it may take time to get - the two programs we are to use is Open Wind and SAM - Given major objectives from Professor Willy - Fall: select a final location and turbine with backups (based on micro-siting selection may have to change) - Spring: work on micro-siting, finalize the selection of location and turbine, finalize financial numbers - Told that to practice tutorials for Open Wind (will be given the tutorials at a later date) | EGR Rm 324c |
| ## 12:30 pm to end | Presentation 1 - Discussion led by Rachel Watanabe - Gathered and discussed more information based on client meeting and info needed for presentation - organized slides and inserted information | EGR 2nd Floor Study Alcove |

Table 2.  Tasks Assigned.

| Task | Person Assigned | Due Date | Date Complete |
| --- | --- | --- | --- |
| Team Charter Submission | Marina McCue | 9/6/19 | 9/6/19 |
| Read over CWC Rule Book & come prepared to next meeting with questions | Everyone | 9/11/19 | 9/11/19 |
| Contact Engineering Front deak about booking room 323 for meetings | Rachel Watanabe | 9/11/19 | 9/6/19 |
| Work on Presentation 1 slides | Everyone | Original: 9/13/19 Extended: 9/15/19 |  |
| Read over CWC 2019 top three site papers | Everyone | Original: 9/13/19 Extended: 9/15/19 |  |

Next formal meeting:  9/15/19, Cline Libary, at 5:00 pm.