# MEETING MINUTES

# Topic:  Presentation 1

## Sunday, September 15, 2019

## 5:00 pm – 6:30 pm

Minutes recorded by _Rachel Watanabe_________________

Meeting called by Rachel Watanabe

Attendees: Rachel Watanabe, Toren Schurb and Jayne Sandoval

Please bring:	Laptops/device to access online team docs; information to help fill out the presentation slides

Table 1.  Record of meeting.

| ## 5:00 pm to 5:45 pm | Presentation 1 - Discussion led by Rachel Watanabe - Discussed new information that was found - organized slides and inserted information | Cline Library |
| --- | --- | --- |
| ## 5:45 pm to end | ## QFD - Discussion led by Rachel Watanabe - Finalized ranks and correlation numbering - found RTI and ATI - determined our target values and tolerances - Inserted QFD to presentation 1 | Cline Library |

Table 2.  Tasks Assigned.

| Task | Person Assigned | Due Date | Date Complete |
| --- | --- | --- | --- |
| Work on Presentation 1 slides | Everyone | Original: 9/13/19 Extended: 9/15/19 | 9/15/19 |
| Read over CWC 2019 top three site papers | Everyone | Original: 9/13/19 Extended: 9/15/19 | 9/15/19 |
| Practice Slides for in-class presentation | Everyone | 9/16/19 |  |
| Meet with Dr. Oman to discuss concept generation and self-learning | Everyone | 9/16/19 |  |

Next formal meeting:  9/17/19, EGR Room 102, at 5:30 pm.