# MEETING MINUTES

# Topic:  Presentation 2

## Sunday, October 6, 2019

## 10:00 am – 12:30 pm

Minutes recorded by _Rachel Watanabe_________________

Meeting called by Rachel Watanabe

Attendees: Rachel Watanabe, Toren Schurb and Jayne Sandoval (late: 10:20 am)

Please bring:	Laptops/device to access online team docs; information to help fill out the presentation slides; bring in finished slides you were assigned

Table 1.  Record of meeting.

| ## 10:00 am to 11:30 am | Presentation 2 Editing and Final touch-ups - Discussion led by Rachel Watanabe - Rachel: commented on slides seeing what still needed to be addressed; worked on creating all the citations and in-text citations - Jayne: made edits to her slides - Toren: made edits to his slides | Cline Room 186 |
| --- | --- | --- |
| ## 11:30 am to 12:15 am | Practice Presentation 2 - Discussion led by Rachel Watanabe - The team practiced the presentation multiple times | Cline Room 186 |
| ## 12:15 am to end | Progress Report - Discussion led by Rachel Watanabe - once again cover who is doing which part of the paper and set concert deadlines | Cline Room 186 |

Table 2.  Tasks Assigned.

| Task | Person Assigned | Due Date | Date Complete |
| --- | --- | --- | --- |
| Look into what the comparable wind farms are doing in terms of wildlife | Jayne | Original: 9/25/19 Extended: 10/20/19 |  |
| Work on Progress Report (Presentation 1 info) | Everyone | Original: 9/27/19 Extended: 10/16/19 |  |
| Work on Progress Report (Second half of the report) | Everyone | Original: 10/11/19 Extended: 10/16/19 |  |
| Work on Presentation 2 | Everyone | Original: 10/4/19 Extended: 10/7/19 |  |
| Practice for Presentation 2 | Everyone | 10/7/19 | 10/6/19 |
| Concept Generations for micro siting | Everyone | 10/2/19 | 10/2/19 |

Next formal meeting:  10/9/19, MEP Room, at 4:00 pm.