# MEETING MINUTES

# Topic: Weekly Meeting with Professor Willy

## Friday, March 27, 2020

## 11:00 am– 11:30 am

Minutes recorded by _Rachel Watanabe_________________

Meeting called by Professor Willy

Attendees:  Rachel Watanabe, Toren Schurb, and Jayne Sandoval

Please bring:	Laptops/device to access online team docs; be prepared to update the team on any new info; Be on time for voice chat

Table 1.  Record of meeting.

| ## 11:00 am to end | Updates - Discussion led by Professor Willy - Updated Willy - Openwind micro sitting layout - the best team could do with the 45 turbines of the V120 is 97.5% - The Team agreed to stop using Openwind by Monday 3/30/20 to move on and work on other areas - O&M cost analysis - based on the document provided by Professor Willy - conducted two methods - one based on the produced kWh is on the high end based on the Market report - the one based on the capital cost is within industry standard based on Market Report - Based on an estimate from Vestas Rep the yearly O&M is within estimated range in well within industry standard - Poster - send Professor Willy an updated poster by next week Wednesday - make images of site ⅓ to ½ of the poster and overlap the wind rose - change title to match rulebook - set up the flow of the poster to match rulebook - cost section: change to get rid of zeros - change to millions of thousands - Vestas Rep. - gave an update on what was learned from Wednesday’s meeting with the Vestas Rep. - plan to send him a copy of the poster by Monday | Zoom |
| --- | --- | --- |

Table 2.  Tasks Assigned.

| Task | Person Assigned | Due Date | Date Complete |
| --- | --- | --- | --- |
| Select a final site location and turbine The team is in contact with a person from industry and he is trying to connect us with a person from Vestas and SG; thus, final decisions have been pushed back until after meetings Meeting with Vestas Rep. set for 3/25 | Everyone | Original: 2/15/20 @10pm Extended: 3/8/20 New date: 3/30/20 | This task is going to change |
| Review federal Wildlife regulations again and write up notes (with reference notation) into the final report outline | Jayne | 3/6/20 |  |
| Operational expense | Rachel | 3/13/20 | 3/13/20 |
| Capital expense | Toren | 3/13/20 | 3/13/20 |
| bankability and risk | Jayne | 3/13/20 |  |
| Look into the seasonal breakdown of reach met mast | Jayne | 3/20/20 | 3/13/20 |
| Complete assigned sections of the poster draft | Everyone | 3/13/20 | 3/13/20 |
| Bullet Point update for Willy | Everyone | 3/14/20 | 3/14/20 |
| Meeting Minutes | Rachel | 3/24/20 |  |
| Update Website | Toren | 3/27/20 |  |
| Complete assigned parts for the Final Product Report | Everyone | 3/27/20 |  |
| Finish the next draft of the poster | Everyone | 3/30/20 |  |
| Send Willy O&M spreadsheet | Rachel | 3/27/20 |  |
| Send Willy and Vestas Rep. updated draft poster | Toren | 3/31/20 |  |

Next formal meeting:  3/30/20, Microsoft Teams, at 10:30 am.