# MEETING MINUTES

# Topic: Elevator Pitch

## Wednesday, April 15, 2020

## 10:45 am– 11:55 pm

Minutes recorded by _Rachel Watanabe_________________

Meeting called by Rachel Watanabe

Attendees:  Rachel Watanabe, Toren Schurb, and Jayne Sandoval

Please bring:	Laptops/device to access online team docs; be prepared to update the team on any new info; Be on time for voice chat; be prepared to record the elevator pitch

Table 1.  Record of meeting.

| ## 10:45 am to 10:45 am | Updates - Discussion led by Rachel Watanabe - Jayne’s update on Bankability - asked Toren and Rachel questions - went over her numbers again - Toren - hasn’t gone through teams notes on his elevator pitch - hasn’t worked on the PowerPoint presentation that Rachel started | Microsoft Teams |
| --- | --- | --- |
| ## 11:00 to end | Elevator Pitch - Discussion led by Rachel Watanabe - elevator pitch - everyone re-read over the pitch document - made edits and discussed what needed to be kept and what could be excluded - PowerPoint for the pitch - the team worked on finishing the PowerPoint that goes with the pitch - Toren tasked with recording and sharing with the team by the end of the day since it wasn’t done during the meeting like planned | Microsoft Teams |

Table 2.  Tasks Assigned.

| Task | Person Assigned | Due Date | Date Complete |
| --- | --- | --- | --- |
| bankability and risk Bankability still needs to get done Bankability still needs to get done | Jayne Jayne Jayne | Original: 3/13/20 Extended: 4/1/20 Extended: 4/12/20 Extended: 4/16/20 | Risk: 4/1/20 |
| CUP draft | Everyone | 4/10/20 | 4/10/20 |
| Fully completed final report draft | Everyone | 4/16/20 |  |
| Make a formal PowerPoint Presentation | Everyone | 4/14/20 |  |
| Add a professional picture to Zoom | Everyone | 4/17/20 |  |
| elevator pitch speech doc | Toren | by end of day: 4/13/20 | LATE: 4/14/20 |
| Edit/comment on elevator pitch speech doc | Rachel & Jayne | 4/14/20 | 4/14/20 |
| make any necessary changes based on feedback to the pitch doc | Toren | before meeting: 4/15/20 | Late: during meeting 4/15/20 |
| elevator pitch presentation (ppt) | Everyone | before meeting: 4/15/20 | Rachel: 4/14/20 Jayne: before meeting (4/15/20) LATE: Toren: during meeting 4/15/20 |
| long presentation record | Everyone | 4/17/20 |  |

Next formal meeting:  4/17/20, Zoom, at 11:00 am.