## Sheet1
Week | Start Day | End Date | Agenda Items | Assignments Due | Note:
1 | 2020-08-12 | 2020-08-16 | Team Post Mortem Report | Team Post Mortem Report Due: 8/16
2 | 2020-08-17 | 2020-08-21 | Self-learning I Hardware Review | Self-learning I Due: 8/23
3 | 2020-08-24 | 2020-08-28 | Hardware Review
4 | 2020-08-31 | 2020-09-04 | Hardware Review ERs and TPs revamp | Hardware Review Due: 9/4 Peer Eval 1 Due: 9/6
5 | 2020-09-07 | 2020-09-11 | ERs and TPs revamp
6 | 2020-09-14 | 2020-09-18 | Implementation |  | Website Check 1 Due: 9/18
7 | 2020-09-21 | 2020-09-25 | Implementation | Implementation Due: 9/25
8 | 2020-09-28 | 2020-10-02 | Midpoint Presentation Hardware Review 2 | Midpoint Presentation Due: 9/28 Peer Eval 2 Due: 10/4
9 | 2020-10-05 | 2020-10-09 | Self-learning 2 Poster Draft Implementation 2 | Self-learning 2 Due: 10/9
10 | 2020-10-12 | 2020-10-16 | Poster Draft Implementation 2 | Poster Draft Due: 10/16 Hardware Review 2 Due: 10/16
11 | 2020-10-19 | 2020-10-23 | Final poster Final presentation |  | Website check 2
12 | 2020-10-26 | 2020-10-30 | Final poster Final presentation | Final Poster Due: 10/30
13 | 2020-11-02 | 2020-11-06 | Final presentation | Final presentation Due: 11/6
14 | 2020-11-09 | 2020-11-13 | Final Report
15 | 2020-11-16 | 2020-11-20 | Final Report | Final Report Due: 11/20 | Final Website Check
Formulas:
End Date = [Start Day]+4
Start Day = [Start Day, row above]+5