## Week 1
Monday | 11:30 - 1:00
Meeting with Dr. Oman Followed by short group meeting
Discussed state of design after 476
Started to decide on purchase requests
Friday | 11:30 -12:30
Postmortem, assigned roles
Sunday | 4:00-6:00
Final Edit of postmortem

## Week 2
Monday | 11:30-12:50
Meeting with Dr. Oman, followed by short group.
Disucussed topics for self learning assignment

## Week 3
Monday | 11:30 - 12:30
Meeting with Dr Oman followed by teams meeting
Assigned roles for hardware review
Discussed purchase requests
Thursday | 3:00-4:30
Worked on hardware review

## Week 4
Monday | 3:00-4:00
Team update hardware review work
started memo
Tuesday | 4:30 - 7:00
finalization of hardware review
created powerpoint documents and final memo

## Week 5
Tuesday | 4:30 - 5:30
Client meeting
new contact Terry
no budget from RF
manufacturing analysis?
possible smaller prototype
arctica model assembly
Sunday | 3:00-5:00
Outlining of implementation memo and midterm report

## Week 6
Wednesday | 4:30 - 5:30
Staff meeting w/Oman
discussed implentation memo
final purchasing
arduino options
Saturday | 12:00-2:00 PM
Device construction by Trevor & Nate followed by meeting with Leann
Discussed thermostat options
Planned fan purchase

## Week 7
Thursday | 4:30 - 6:30
implementation memo planning
divided work up
Summarize egineering requirements in memo
Plan for midpoint presentation
Sunday | 12:00-2:00 PM
finalize midpoint presentation
research into plexiglass
Practice run for presentation

## Week 8
Thursday | 6:00 - 8:00 PM
plan out purchases
start purchase requistions
Friday | 6:00 - 8:00 PM
finalize purchase requisitions
plan individual analysis topics

## Week 9
Thursday | 12:00 - 4:00 PM
device construction
assembled frame and aluminum back plates
update to Leann

## Week 10
Tuesday | 2:00 - 5:00 PM
Device construction
Paint all materials
Install support screws
begin fin cutting
Wednesday | 3:00 - 5:00 PM
Hardware review prep
divide work load
discuss final purchases
Friday | 12:00 - 12:20 PM
Hardware review with Oman
Arduino kit from oman to replicate Leann's
Speed up construction to begin testing

## Week 11
Monday | 1:00 - 4:00 PM
home depot trip to look at acrylic
Acrylic had a film on it. Very clear
add extra screws to frame
final paint coat
Cutting fins on table saw not an option
Wednesday | 2:00-2:30PM
meeting with client
update on progress
add assembly video to final deliverables
Wednesday | 2:30 -5:00
machine shop
cut out fins on sheet metal break
attempt to cut holes with hole saw
go to harbor freight to look at hole saws

## Week 12
Tuesday | 12:30 - 5:30 PM
Device construction
finish fin assembly
Wednesday | 12:00-1:00 PM
Meeting to discuss final deliverables
divide work load
discuss final purchases
Thursday | 3:00-5:00 PM
Device coonstruction
Friday | 12-1PM
Home Depot trip

## Week 13
Tuesday | 2:00 - 5:30 PM
Device construction
install entrance and exit ducting
last fins installed
Wednesday | 2:30-4:00 PM
minor modifications for fins
test fit acrylic panel
Friday | 1:00-5:30 PM
Device construction
acrylic sheet and caulking seal + final paint
Saturday | 12-3PM
Test fit fans and work on electronics

## Week 14
Tuesday | 11:00 -4:00 PM
Device construction
Finish prototype
wire all electronics
Wednesday | 12:30-4:00 PM
completed device testing
Friday | 1:00-7:30 PM
Final product meeting and meeting with team for final deliverables
Finalize construction manual

## Week 15
Thursday | 4:00 -6:00 PM
Start Final report
Friday | 12:30-4:00 PM
Finish final report