## Schedule
Finished | In Progress | Not Started | [39 empty] | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday
Major Task | Minor Task | Team Member | time axis 2021-08-23 to 2021-12-08
Proof of Concept |  | Team | 2021-08-23: Start; 2021-08-26: Finish
System Redisign |  | Team | 2021-08-27: Start; 2021-10-29: Finish
| Clutch | Connor | 2021-10-09: Finish
| Clutch & Flywheel CAD | Abdulh | 2021-10-11: Finish
| Flywheel | Daniel | 2021-10-08: Finish
| Shafts & Bearings | Daniel | 2021-10-08: Finish
| Electrical Sensor Design | Yen | 2021-10-20: Finish
| Electrical Equipment Mounts |  | 2021-10-20: Finish
| Electrical Equipment CAD | Abdulh | 2021-10-24: Finish
Fix Steering
Self Learning |  | Team | 2021-08-27: Start; 2021-09-05: Finish
Prototypes |  | Team | 2021-09-10: Start; 2021-09-18: Finish
| CAD FEA | Yujie
| Arduino | Yen
Hardware Review 1 |  | Team | 2021-09-23: Start; 2021-09-28: Finish
Order Parts |  | Yujie | 2021-09-28: Start; 2021-10-10: Finish
| Submit Work Order |  | 2021-10-15: Start; 2021-10-29: Finish
Website Check 1 |  | Yen | 2021-09-28: Start; 2021-10-01: Finish
Implementation Memo |  | Team | 2021-10-04: Start; 2021-10-08: Finish
| Design Changes/Intro/Future Work | Daniel | bar: 2021-10-04 to 2021-10-08
| Customer Requirements | Yen | bar: 2021-10-04 to 2021-10-08
| Engineering Requirements | Abdulh | bar: 2021-10-04 to 2021-10-08
| Engineering Requirements | Connor | bar: 2021-10-04 to 2021-10-08
| Future Work | Yujie | bar: 2021-10-04 to 2021-10-08
Midpoint Presentation |  | Team | 2021-10-08: Start; 2021-10-14: Finish
| Project Description | Yujie | bar: 2021-10-08 to 2021-10-14
| Design Description | Daniel | bar: 2021-10-08 to 2021-10-14
| Current State of System | Abdulh | bar: 2021-10-08 to 2021-10-14
| BOM | Daniel | bar: 2021-10-08 to 2021-10-14
| Sensor and Display (Current State) | Yen | bar: 2021-10-08 to 2021-10-14
| Tasks Completeed Breakdown | Connor | bar: 2021-10-08 to 2021-10-14
Implementation Plan | bar: 2021-10-08 to 2021-10-14
| Testing |  | 2021-10-08: Start; 2021-10-14: Finish
Manufacturing/Assembly |  | Team | 2021-10-29: Start; 2021-11-12: Finish
| Assemble Clutch | Connor | 2021-10-29: Start; 2021-11-01: Finish
| Assemble/Mount Sprockets and Shafts | Yujie | 2021-10-30: Start; 2021-11-03: Finish
| Reassemble Rear Wheel | Daniel | 2021-10-31: Start; 2021-11-04: Finish
| Mount Shaft/Clutch/Flywheel | Daniel | 2021-11-02: Start; 2021-11-08: Finish
| Run Cables & Chains/Mount Derailers | Yujie | 2021-11-05: Start; 2021-11-08: Finish
| Mount Sensors/Run Wires | Yen | 2021-11-06: Start; 2021-11-09: Finish
| Mount Display | Yen | 2021-11-06: Start; 2021-11-09: Finish
| Welding | Yujie | 2021-11-08: Start; 2021-11-12: Finish
Individual Analytical Analysis |  | Team | 2021-10-17: Start; 2021-10-27: Finish
Hardware Review 2 |  |  | 2021-10-27: Start; 2021-11-05: Finish
Polish Software |  | Yen | 2021-10-27: Start; 2021-11-05: Finish
Polishing Build |  |  | 2021-11-15: Start; 2021-12-03: Finish
Testing |  | Team | 2021-11-15: Start; 2021-11-22: Finish
| Test Clutch Plate Wear | Team | 2021-11-15: Start; 2021-11-22: Finish
| Test Clutch Efficiency | Team | 2021-11-18: Start; 2021-11-22: Finish
| Test Software/Display | Yen | 2021-11-14: Start; 2021-11-18: Finish
Website Check 2 |  | Yen | 2021-10-29: Start; 2021-11-05: Finish
Final CAD |  | Yujie | 2021-11-06: Start; 2021-11-12: Finish
UGRADS Poster |  | Team | 2021-11-06: Start; 2021-11-12: Poster Draft; 2021-12-08: Finish
| Sign Up for UGRADS |  | 2021-11-06: Start; 2021-11-07: Finish
Final Presentation |  | Team | 2021-11-07: Start; 2021-11-18: Finish
Assembly Manual |  | Team | 2021-11-07: Start; 2021-12-08: Finish
Final Report |  | Team | 2021-11-14: Start; 2021-12-08: Finish
Final Website Check |  | Yen | 2021-11-30: Start; 2021-12-07: Finish
Deliver Final Product |  | Daniel | 2021-12-01: Start; 2021-12-08: Finish

## What has been done
Team Member | Contributions to Date (This Semester) | No. | Engineerig Req. | Value
Connor | Clutch/Flywheel Design, Scheduling | 1 | Energy Stored | 600 J
Yen | Electrical/Software Subsystem Design, Scheduling, Website | 2 | Regen. Braking Efficiency | 0.15
Daniel | Clutch/Flywheel Design, Minor Component Design | 3 | Max. Speed | 20 mph
Yujie | Purchasing, CAD | 4 | Display Metrics | Yes/No
Abdulh | CAD | 5 | Usable Energy Threshold | 200 J