## Gantt Chart
Passive Cooling | [71 empty] | January | Feb | March | April | May
P13 - Passive People | [5 empty] | Legend: | On track |  |  |  |  | Low risk |  |  |  |  | Med risk |  |  |  |  | High risk |  |  |  |  | Unassigned | [44 empty] | Legend: |  | On track |  |  |  |  | Low risk |  |  |  |  | Med risk |  |  |  |  | High risk |  |  |  |  | Unassigned
Project Start Date: | 2022-09-05 | [5 empty] | September | [20 empty] | October | [27 empty] | November | [6 empty] | Spring 2023 | [7 empty] | January | [23 empty] | Feb | [31 empty] | March | [26 empty] | April | [26 empty] | May
Scrolling Increment: | 9 | [5 empty] | 2022-09-14 | 2022-09-15 | 2022-09-16 | 2022-09-17 | 2022-09-18 | 2022-09-19 | 2022-09-20 | 2022-09-21 | 2022-09-22 | 2022-09-23 | 2022-09-24 | 2022-09-25 | 2022-09-26 | 2022-09-27 | 2022-09-28 | 2022-09-29 | 2022-09-30 | 2022-10-01 | 2022-10-02 | 2022-10-03 | 2022-10-04 | 2022-10-05 | 2022-10-06 | 2022-10-07 | 2022-10-08 | 2022-10-09 | 2022-10-10 | 2022-10-11 | 2022-10-12 | 2022-10-13 | 2022-10-14 | 2022-10-15 | 2022-10-16 | 2022-10-17 | 2022-10-18 | 2022-10-19 | 2022-10-20 | 2022-10-21 | 2022-10-22 | 2022-10-23 | 2022-10-24 | 2022-10-25 | 2022-10-26 | 2022-10-27 | 2022-10-28 | 2022-10-29 | 2022-10-30 | 2022-10-31 | 2022-11-01 | 2022-11-02 | 2022-11-03 | 2022-11-04 | 2022-11-05 | 2022-11-06 | 2022-11-07 | 2022-11-08 | time axis 2023-01-16 to 2023-05-12
Milestone description | Category | Assigned to | Progress | Start | End | Days | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T |  | Milestone description | Category | Assigned to | Progress | Start | End | Days | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F
Project Setup | [63 empty] | Project Setup
Project Assigned | Milestone | Team | 100% | 2022-09-05 | 2022-09-05 | 1 | [57 empty] | Kick of meeting | Goal | Team | 100% | 2023-01-16 | 2023-01-23 | 7 | bar: M to M
SolidWorks Review | On Track | Team | 100% | 2022-09-05 | 2022-09-14 | 10 | [57 empty] | Hardware Status Update(50%) | Goal | Team | 100% | 2023-02-13 | 2023-03-06 | 21 | bar: M to T
Initial Client Meeting | Goal | Team | 100% | 2022-09-14 | 2022-09-14 | 1 | 2 | [56 empty] | Hardware Status Update(100%) | On Track | Team | 99% | 2023-02-13 | 2023-04-03 | 49 | bar: M to M
Team Charter | On Track | Team | 100% | 2022-09-12 | 2022-09-14 | 3 | [57 empty] | Testing Plan Draft | On Track | Team | 100% | 2023-01-16 | 2023-02-13 | 28 | bar: M to M
Presentation 1 | On Track | Team | 100% | 2022-09-12 | 2022-09-19 | 7 | [57 empty] | Initial Testing Result | On Track | Team | 100% | 2023-04-03 | 2023-04-21 | 18 | bar: T to S
Liteture Review | Low Risk | Tori | 75% | 2022-09-14 | 2022-09-23 | 10 | [57 empty] | Product and Final Testing Result | High Risk | Team | 100% | 2023-01-16 | 2023-04-24 | 98 | bar: M to M
Buget Formation | Low Risk | Logan/Sabin | 90% | 2022-09-14 | 2022-09-21 | 8 | [57 empty] | Symposium | High Risk | Team | 85% | 2023-01-16 | 2023-04-28 | 102 | bar: M to F
Schedule Formation | Med Risk | Logan | 90% | 2022-09-14 | 2022-09-21 | 8 | [57 empty] | Bi-Weekly Client Meetings
Bi-Weekly Client Meetings | [63 empty] | Client Meeting #2 | Goal | Team | 100% | 2023-01-20 | 2023-01-20 | 1 | bar: M to F
Client Meeting #2 | Goal | Team | 10% | 2022-09-28 | 2022-09-28 | 1 | [14 empty] | 2 | [42 empty] | Client Meeting #3 | Goal | Team | 100% | 2023-01-27 | 2023-01-27 | 1 | bar: M to F
Client Meeting #3 | Goal | Team | 10% | 2022-10-12 | 2022-10-12 | 1 | [28 empty] | 2 | [28 empty] | Client Meeting #4 | Goal | Team | 100% | 2023-02-03 | 2023-02-03 | 1 | bar: M to F
Client Meeting #4 | Goal | Team | 10% | 2022-10-26 | 2022-10-26 | 1 | [42 empty] | 2 | [14 empty] | Client Meeting #5 | Goal | Team | 100% | 2023-02-10 | 2023-02-10 | 1 | bar: M to F
Client Meeting #5 | Goal | Team | 10% | 2022-11-09 | 2022-11-09 | 1 | [57 empty] | Client Meeting #6 | Goal | Team | 100% | 2023-02-17 | 2023-02-17 | 1 | bar: M to F
Client Meeting #6 | Goal | Team | 10% | 2022-11-23 | 2022-11-23 | 1 | [57 empty] | Client Meeting #7 | Goal | Team | 100% | 2023-02-24 | 2023-02-24 | 1 | bar: M to F
Client Meeting #7 | Goal | Team | 10% | 2022-11-30 | 2022-11-30 | 1 | [57 empty] | Client Meeting #8 | Goal | Team | 0% | 2023-03-28 | 2023-03-28 | 1 | bar: T
Client Meeting #8 | Goal | Team | 10% | 2022-12-07 | 2022-12-07 | 1 | [57 empty] | Client Meeting #9 | Goal | Team | 0% | TBD | TBD | 1
Client Meeting #9 | Goal | Team | 10% | 2022-12-14 | 2022-12-14 | 1 | [57 empty] | Project Development
Project Development | [63 empty] | Kick of meeting | Milestone | Team | 100% | 2023-01-16 | 2023-01-23 | 7 | bar: M to M
NAU Green Fund Financing | High Risk | Logan/Sabin | 70% | 2022-09-12 | 2022-11-25 | 75 | [57 empty] | Project management | Milestone | Team | 100% | 2023-01-16 | 2023-01-25 | 9 | bar: M to W
Presentation 1 | Milestone | Team | 100% | 2022-09-19 | 2022-09-19 | 1 | [5 empty] | 1 | [51 empty] | Engineering Model Summary | Milestone | Team | 100% | 2023-01-16 | 2023-01-29 | 13 | bar: M to S
Peer Eval 1 | Low Risk | Individual | 100% | 2022-09-19 | 2022-09-23 | 5 | [57 empty] | Self Learning | Milestone | Individual | 100% | 2023-01-16 | 2023-02-05 | 20 | bar: M to M
Self Learning | Med Risk | Individual | 100% | 2022-09-19 | 2022-10-07 | 19 | [57 empty] | Peer Eval 1 | Low Risk | Individual | 100% | 2023-01-16 | 2023-02-13 | 28 | bar: M to M
Presentation 2 | Milestone | Team | 100% | 2022-10-10 | 2022-10-10 | 1 | [26 empty] | 1 | [30 empty] | Website Check #1 | Med Risk | Anubhav | 100% | 2023-01-16 | 2023-02-27 | 42 | bar: M to F
Peer Eval 2 | Low Risk | Individual | 100% | 2022-10-10 | 2022-10-14 | 5 | [57 empty] | Peer Eval 2 | Low Risk | Individual | 100% | 2023-02-13 | 2023-03-06 | 21 | bar: M to M
Preliminary Report | High Risk | Team | 100% | 2022-09-26 | 2022-10-21 | 26 | [57 empty] | Draft of the poster | Med Risk | Team | 100% | 2023-03-20 | 2023-03-27 | 7 | bar: M to M
Website Check | Med Risk | Anubhav | 100% | 2022-09-16 | 2022-10-28 | 43 | [57 empty] | Final poster and PPT | High Risk | Team | 100% | 2023-03-27 | 2023-04-21 | 25 | bar: M to F
Analytical Memo | Med Risk | Team | 100% | 2022-10-24 | 2022-11-06 | 14 | [57 empty] | Peer Eval 3 | Low Risk | Individual | 100% | 2023-03-06 | 2023-04-03 | 28 | bar: T to M
Presentation 3 | Milestone | Team | 95% | 2022-11-07 | 2022-11-07 | 1 | [57 empty] | Peer Eval 4 | Low Risk | Individual | 0% | 2023-04-03 | 2023-05-01 | 28 | bar: T to S
Peer Eval 3 | Low Risk | Individual | 5% | 2022-11-07 | 2022-11-11 | 5 | [57 empty] | Final CAD Packet | Low Risk | Individual | 100% | 2023-01-16 | 2023-04-03 | 77 | bar: M to T
CAD Development | [63 empty] | Final report and Final Website Check | Low Risk | Individual | 100% | 2023-02-27 | 2023-04-24 | 56 | bar: M to M
CAD Simulations | Med Risk | Anubhav/Sabin | 20% | 2022-10-24 | 2022-11-25 | 33 | [57 empty] | Client Handoff - Spec Sheet | Low Risk | Individual | 0% | 2023-01-16 | 2023-05-01 | 105
Final CAD | High Risk | Anubhav | 0% | 2022-10-24 | 2022-11-25 | 33
Final BOM | Med Risk | Team | 95% | 2022-09-30 | 2022-11-25 | 57 | [57 empty] | Manufaturing
[64 empty] | CNC part | Med Risk | Team | 100% | 2023-01-16 | 2023-01-30 | 14 | bar: M to M
[64 empty] | Assembling | Med Risk | Team | 100% | 2023-01-16 | 2023-04-21 | 95 | bar: M to F
[64 empty] | Final design | High Risk | Team | 100% | 2023-01-16 | 2023-03-31 | 74 | bar: M to F
To add more data, Insert new rows ABOVE this one