## Bill of material
Subsytem | Column12 | Column2 | Column3 | Column4 | Column5 | Lead time
Subsytem | Manufacturer/ Component Name | Component | Quantity | Price | Total
Electrical | Amazon MY1016Z3 | 24V Motors | 2 | 130 | 260 | On hand
Tracks | Verco Track Tracks | Tracks | 1 | 334.75 | 334.75 | Ordered
Electrical | Sabertooth Dual 60Amp motor driver | Electronis speed contoller | 1 | 189.99 | 189.99 | On hand
Electrical | 22 AH Battery | Batteries | 2 | 55 | 110 | On Hand
Frame | Oshcut | Frame | 1 | 326 | 326 | On Hand
Electrical | Fly sky fs-1a6b | Reciever/ Controller | 1 | 64.99 | 64.99 | On hand
Frame | Bolts | Frame bolts | 1 | 40 | 40 | On hand
Electrical | T Tocas 100 Amp Circuit Breaker with Manual Reset, 12V- 48VDC, Waterproof (100A | On off Switch | 1 | 26.99 | 26.99 | On hand
Misc | Spray paint | Clear Coat | 2 | 7 | 14
Electrical | Electrical box | Electrical box | 1 | 12 | 12 | prototyping
Electrical | Battery Tie down | Battery tie down | 1 | 20 | 20 | prototyping
Drive wheels | 3D Printed | 8 inch wheels | 4 | 9 | 36 | On hand
Drive | Machined auminum hub adapter | hub adapter | 2 | 50 | 100 | speak to machine shop
Drive | Front axle | axle 0.5 inch | 1 | 38 | 38 | On hand
Drive | Bearings Grainger | 0.5 in ID 1.25in OD | 4 | 5.5 | 22 | On hand
Electrical | Power and Ground Wires | Misc wire to connect componenets | 1 | 30 | 30 | On hand
Frame | Shaft Collars | Frame bolts | 2 | 10 | 20
Electrical | Motor Connectors | XT60 connector | 1 | 9 | 9 | On hand
|  |  |  | Cost | 1653.72
|  |  | Budget Spent $700 | 1653.72
|  |  | Budget Remaining |  | 346.28

## Manufacturing Plan
Column 1 | Column 2 | Column 4 | Column 5 | Column 6 | Column 7 | Column 8 | Column 9
Subsytem | Manufacturer/ Component Name | Quantity | Price | Total | Lead Time | Make Vs. Buy | Status on part
Electrical | Power and Ground Wires | 1 | 40 | 40 | 1 wk | Buy | Completed
Electrical | Electrical Box Wiring | 1 | 12 | 12 | 1wk | Make | Completed
Frame | Nutserts for frame | 1 | 10 | 10 | 1 day | Buy | Completed
Frame | Frame Welding | 1 | 0 | 0 | 2 wk | Make | Completed
Axle | Axle Shaft machining | 1 | 10 | 10 | 1 wk | Buy | Completed
Axle | Axle Bearings pressed into wheels | 4 | 5.5 | 22 | 1 wk | Buy | Completed
Axle | Axle Blocks machining | 2 | 20 | 40 | 2 wk | Make | Completed
Axle | Front Axle Assembley | 1 | 0 | 0 | 2 wk | Make | Completed
Drive | Wheel Adapter machining | 2 | 25 | 50 | 2 wk | Make | Completed
Drive | Tracks from Verco Track | 1 | 400 | 400 | 2 wk | Buy | On Hand
Misc | Paint and Finishing | [5 empty] | Completed
Color Code
On Hand
Ordered
Need to Order

## Purchasing Plan
Column 1 | Column 2 | Column 4 | Column 5 | Column 6 | Column 7 | Column 8 | Column 9
Subsytem | Manufacturer/ Component Name | Quantity | Price | Total | Lead Time | Make Vs. Buy | Status on part
Electrical | Amazon Motors | 2 | 130 | 260 | 0 | Buy | On hand
Electrical | Sabertooth Dual 60Amp motor driver | 1 | 189.99 | 189.99 | 0 | Buy | On hand
Electrical | Fly sky fs-1a6b | 1 | 60 | 60 | 0 | Buy | On hand
Electrical | Battery | 2 | 40 | 80 | 0 | Buy | On hand
Electrical | Circuit Breaker | 1 | 26.99 | 26.99 | 0 | Buy | On hand
Electrical | Power and Ground Wires | 1 | 40 | 40 | 1 wk | Buy | Ordered
Frame | Osh Cut Frame | 1 | 326 | 326 | 0 | Buy | On hand
Frame | Battery Tie down | 1 | 10 | 10 | 0 | Make | On hand
Axle | Axle Shaft | 1 | 10 | 10 | 1 wk | Buy | On hand
Axle | Axle Bearings | 4 | 5.5 | 22 | 1 wk | Buy | On hand
Axle | Axle Blocks | 2 | 20 | 40 | 2 wk | Make | On hand
Drive | Wheel Adapter | 2 | 25 | 50 | 2 wk | Make | On hand
Frame | Frame Bolts | 1 | 30 | 30 | 0 | Buy | On hand
Drive | Tracks from Verco Track | 1 | 400 | 400 | 2 wk | Buy | On hand
Drive | Harbor Freight 8 inch Wheels | 4 | 7 | 28 | 0 | Buy | On hand
Misc | Spray paint | 2 | 7 | 14 | 0 | Buy | On Hand
|  |  | Total USD $ | 1653.72
Color Code
On Hand
Ordered
Need to Order