## Sheet1
Test Plan | [8 empty] | Test Report
Specification | Unit Under Test | Test Description | Relevant DR's | Acceptance Criteria | Target Requirements | Test Responsibility | Test Equipment | Est. Completion | Act. Completion | Test Notes | Pass/Fail | Course of Action
J1 - J6 Motor Amperage | J1 - J6 Motors | Provide veried "Loads" in the form of hand resistance up until shortly before stall torques to understand general amperage pull compared to that of rated currents for each motor | CR 6/CR 7 | Motors do not exceed an amperage reading of 10 A to ensure protection of J1 - J6 Motor Drivers | All Must Pass | Mason / Brandon | J1 - J6 Motors, Variable Power Supply, 10 A Motor Driver, 20 AWG wire, AWM 2586 Wire, Arduino Software | 2024-03-08
Spindle Wiring & Rpm | End Effector | Wire the end effector in unison with the Varaible Frequency Drive to ensure purchased wiring is adequate and the Rpm's of the end effector can be adjusted | CR 2/CR 7/ ER 2 | End effector runs and has variable Rpm capabilities for wood/aluminum to guarentee future testing capabilites | All Must Pass | Mason / Brandon | 10 A Spindle, VFD, Variable Power Supply, AWM 2586 Wire | 2024-03-08
Modular Electrical | J1-J6 Motors, Power Supply, Joint Manufactured Equipment | Assemble the robotic arm in a "ground up" manner ensuring that manufactured equipment "fits" as intended and eletrical power can be supplied to jog motors at eacj joint level | CR 1/ CR 3 / CR 5 / ER 5 | Design can be assembled as intended & motors can jog at each respective joint level | All Must Pass | Whole Team | J1 - J6 Motors, Variable Power Supply, 10 A Motor Driver, 20 AWG wire, AWM 2586 Wire, Limit Switches, J1 - J6 Manufactured Parts, Roller Dolly, Complete Hardware, Arduino Software | TBD
Complete Arm Movment | Complete Robotic Design | Robotic design can move in the X,Y, and Z planes as intended | All | Robotic arm can complete task movments at various extensions for 10 minutes | Minimum Viable Product | Whole Team | J1 - J6 Motors, Variable Power Supply, 10 A Motor Driver, 20 AWG wire, AWM 2586 Wire, Limit Switches, J1 - J6 Manufactured Parts, Roller Dolly, Complete Hardware, Arduino Software | TBD
Real World Simulation | Complete Robotic Design | A real world simulation where the design moves in multiple planes & completes drilling operations | All | Movement is continuous & complete with a finshed drilling operations that meets CR's | Minimum Viable Product | Whole Team | J1 - J6 Motors, Variable Power Supply, 10 A Motor Driver, 20 AWG wire, AWM 2586 Wire, Limit Switches, J1 - J6 Manufactured Parts, Roller Dolly, Complete Hardware, Arduino Software | TBD
[13 empty] | Customer Requirement | CR met (Y/N) | Client Acceptable (Y/N) |  |  |  | Engineering Requirment | Target | Tolerance | Measured Value | ER met (Y/N) | Client Acceptable (Y/N)
[13 empty] | CR 1 - Working Volume (50" D, 4' Height ) | Y | 4Ft H 27 In radius / 3.5ft Height 36in Radius |  |  |  | ER 1 - Deflects < .1'' during drilling | .1'' | -.1''
[13 empty] | CR 2 - 1/4" Aluminum Drilling | Y |  |  |  |  | ER 2 - Spindle Speed 3000 Rpm | 3000 RPM | +/- 200 RPM | 3000+ RPM | Y | Y
[13 empty] | CR 3 - Human Input Responsive | [5 empty] | ER 3 - Motor Torque 100 N-m | 100 N-m | +/- 2 N-m
[13 empty] | CR 4 - .03" Drilling tolerance | [5 empty] | ER 4 - Human Input Responsive | Yes | N/A
[13 empty] | CR 5 - Portable | Y |  |  |  |  | ER 5 - Assembly < 150 lbs | 150 Lbs | +/- 10 Lbs | 122.65 lbs | Y | Y
CR 6 - Electric Power
CR 7 - Emergency Stop
CR 8 - Cost Efficient
[13 empty] | Engineering Requirment | Target | Tolerance | Measured Value | ER met (Y/N) | Client Acceptable (Y/N)
[13 empty] | ER 1 - Deflects < .1'' during drilling | .1'' | -.1''
[13 empty] | ER 2 - Spindle Speed 3000 Rpm | 3000 RPM | +/- 200 RPM | 3000 RPM + | Y | Y
[13 empty] | ER 3 - Motor Torque 100 N-m | 100 N-m | +/- 2 N-m
[13 empty] | ER 4 - Human Input Responsive | Yes | N/A
[13 empty] | ER 5 - Assembly < 150 lbs | 150 Lbs | + 10 Lbs | 122.65 lbs | Y | Y

## Torque-Speed Curves
J1 - NEMA 23- 10:1 |  |  |  |  | J2/3 - NEMA 23- 50:1
Torque (Nm) | Speed (rpm) | Left (kg) | Right (kg) | <— Power (W) —> | Torque (Nm) | Speed (rpm) | Set Up

## Spindle
VFD (Hz) | Spindle (RPM)
0 | 0
10.1 | 591.6
20.1 | 1204.7
30.1 | 1808.2
40 | 2535.7
50.4 | 3029.4
59.9 | 3574.7
70.5 | 4228.1
80.3 | 4856.9
90.4 | 5325.5
100 | 6017.1