## Project schedule
| Hamster project | [5 empty] | Project start: | [7 empty] | 2024-04-21
| NAU Capstone Team | Project lead | Joseph L |  |  |  | Display week: | [7 empty] | 29
[7 empty] | 2024-11-04 | [6 empty] | 2024-11-11 | [6 empty] | 2024-11-18 | [6 empty] | 2024-11-25 | [6 empty] | 2024-12-02 | [6 empty] | 2024-12-09 | [6 empty] | 2024-12-16 | [6 empty] | 2024-12-23
| TASK | ASSIGNED TO | PROGRESS | START | END | time axis 2024-11-04 to 2024-12-29
 | time axis 2024-11-04 to 2024-12-29
Do not delete this row. This row is hidden to preserve a formula that is used to highlight the current day within the project schedule.
Presention 1
| Meet with team | Team | 100% | 2024-04-21 | 2024-04-24 | 4
| Client Meeting and Advisor Meeting | Team | 100% | 2024-04-24 | 2024-04-26 | 3
| Charter Assignment | Team | 100% | 2024-04-26 | 2024-04-30 | 5
| Research and begin Presentation | Team | 100% | 2024-04-30 | 2024-05-05 | 6
| Finish Presentation | Team | 100% | 2024-05-06 | 2024-05-10 | 5
Presentation 2
| Select Parts | Keenan | 100% | 2024-05-11 | 2024-05-15 | 5
| Order Parts for first prototype | Rylee | 100% | 2024-05-13 | 2024-05-28 | 16
| Staff Meeting 2 | Team | 100% | 2024-05-31 | 2024-05-31 | 1
| Design CAD Model for casing | Jared | 100% | 2024-06-01 | 2024-06-03 | 3
| Homework 3 | Indicvidual assignment | 100% | 2024-05-28 | 2024-06-04
| Finish Presentation 2 | Joe | 100% | 2024-06-04 | 2024-06-06 | 3
| Peer Eval 2 | Team | 100% | 2024-06-07 | 2024-06-07
Presention 3 (Prototype 1)
| Assemble Prototype | Rylee | 100% | 2024-06-07 | 2024-06-10 | 4
| Test Prototype | Rylee | 100% | 2024-06-11 | 2024-06-18 | 8
| Begin Presentation and Continue Testing | Joe and Keenan | 100% | 2024-06-16 | 2024-06-27 | 12
| Website Check #1 | Rylee | 100% | 2024-06-18 | 2024-06-25
| Report #1 | Joe and Team | 100% | 2024-06-19 | 2024-06-26
| Staff Meeting 3 | Team | 100% | 2024-06-28 | 2024-06-28 | 1
| Analysis Memo | Team | 100% | 2024-06-25 | 2024-07-02
| Finish Presentation | Joe | 100% | 2024-06-27 | 2024-07-11 | 15
| Peer Eval 3 | Individual assignment | 100% | 2024-07-12 | 2024-07-12
2nd Prototype Demo
| Make Changes to Prototype | Jared | 100% | 2024-07-06 | 2024-07-09 | 4
| Begin Presentation and Continue Testing | Team and Rylee | 100% | 2024-04-20 | 2024-04-23 | 4
| Address risks | Keenan | 100% | 2024-04-24 | 2024-04-27 | 4
Report #2 | Report #2 | Team | 100% | 2024-04-27 | 2024-05-04
| Final CAD and Final BOM | Jared and Rylee | 100% | 2024-04-16 | 2024-04-26
| Finish Prototype 2 | Team | 100% | 2024-04-11 | 2024-04-29 | 19
| Homework 4 | Individual assignment | 100% | 2024-04-17 | 2024-05-01
| Project Management for 486C | Joe and Team | 100% | 2024-04-26 | 2024-05-03
| Website Check #2 | Rylee | 100% | 2024-04-15 | 2024-05-03
33% Build
| HW 00 (DONE) | Individual assignment | 100% | 2024-08-26 | 2024-08-27 | bar: 2024-11-04 to 2024-11-05
| Project Management for 486C (DONE) | Team | 100% | 2024-08-26 | 2024-08-29
| Purchase Parts (Behind Schedule- Did not order parts we thougth we didnt need) | Rylee | 100% | 2024-09-02 | 2024-09-05
| Engineering Calculations (On Schedule- Need more strain and torque test on shaft) | Joe, Keenan, Rylee | 100% | 2024-09-02 | 2024-09-06
| Finalize Design (On Schedule- Finishing up minor adjustment for easier printing) | Jared | 100% | 2024-08-30 | 2024-09-04 | bar: 2024-11-08 to 2024-11-13
| Self Learning (DONE) | Individual assignment | 100% | 2024-09-02 | 2024-09-13 | bar: 2024-11-11 to 2024-11-22
| Start Building for 33%( On schedule- Needed more parts but more than 33% done) | Team | 100% | 2024-09-04 | 2024-09-20 | 17
| Begin Presentation 1 (On Schedule) | Team | 100% | 2024-09-20 | 2024-09-23
| Finish 33% Build (On Schedule) | Team | 100% | 2024-09-23 | 9/232024
| Present in Class (Current) | Team | 100% | 2024-09-26 | 2024-09-26
| Peer Eval 1 (On schedule) | Individual assignment | 100% | 2024-09-25 | 2024-09-26
67% Build
| Start 67% Build (On Schedule- Ordering more parts to assemble) | Team | 100% | 2024-09-30 | 2024-10-15
| Website Check #3 (On Schedule- Gathering photos and info to put on Website) | Rylee/Jared | 100% | 2024-09-30 | 2024-10-08
| Finish 67% Build (On Schedule- After parts come in will be able to start 67% build) | Team | 100% | 2024-10-21 | 2024-10-23
| Start Testing (Ahead of Schedule- Start testing within 1 1/2 weeks, testing wheels) | Keenan | 100% | 2024-10-14 | 2024-11-04
| Start Poster (Not started yet but will start soon) | Team | 100% | 2024-10-15 | 2024-10-28
| Wiring for Battery ( On Schedule- Waiting for parts to be delivered) | Keenan | 100% | 2024-10-03 | 2024-10-07
| Update BOM and purchase order (Done) | Rylee | 100% | 2024-10-02 | 2024-10-15
| Finish purchase order (Done) | Rylee | 100% | 2024-10-01 | 2024-10-13
| Redesign CAD (Tolerencing and adding Louvers) (Done) | Jared | 100% | 2024-10-01 | 2024-10-11
| Sreach for new parts for Purchase Order- Screen, Fuses, Wiring ( On Schedule) | Rylee/Keenan | 100% | 2024-10-07 | 2024-10-13
| UGRAD/Efest Registration | Joe | 100% | 2024-10-17 | 2024-10-24
| Work on improving encoder and making interface for friendly (On Schdule) | Joe | 100% | 2024-10-01 | 2024-11-21
| Peer Eval 2 (Pending for after class) | Individual assignment | 100% | 2024-10-16 | 2024-10-18
100% Build
| Start 100% Build (Testing Phase) | Team | 100% | 2024-10-18 | 2024-11-07 | bar: 2024-12-06 to 2024-12-26
| Finalize testing plan | Keenan/Jared | 100% | 2024-10-18 | 2024-11-01 | bar: 2024-12-06 to 2024-12-20
| Start poster | Team | 100% | 2024-10-21 | 2024-10-31 | bar: 2024-12-09 to 2024-12-19
| Finalize CAD Design with minor tweaks | Jared | 100% | 2024-10-22 | 2024-10-22 | bar: 2024-12-10
| Finalize code for testing | Joe | 100% | 2024-10-19 | 2024-11-02 | bar: 2024-12-07 to 2024-12-21
| Assemble Operation/Assembly Manual | Rylee/Keenan | 100% | 2024-11-01 | 2024-12-05 | bar: 2024-12-20 to 2024-12-29
| Update BOM and purchasing plan | Rylee | 100% | 2024-10-25 | 2024-11-07 | bar: 2024-12-13 to 2024-12-26
| Work on Final report | Team | 100% | 2024-10-21 | 2024-12-03 | bar: 2024-12-09 to 2024-12-29
| Peer Eval 3 | Individual assignment | 100% | 2024-11-14 | 2024-11-15
| Finalize website | Rylee/Jared | 85% | 2024-11-25 | 2024-12-04
Product Demo & Testing Results
| Assemble Operation/Assembly Manual | Team | 80
| Efest | Team
| Client Handoff | Team
Insert new rows ABOVE this one
Formulas:
Display week: = [Display week:, row below]

## About (hidden)
SIMPLE GANTT CHART by Vertex42.com
About This Template
This template provides a simple way to create a Gantt chart to help visualize and track your project. Simply enter your tasks and start and end dates - no formulas required. The bars in the Gantt chart represent the duration of the task and are displayed using conditional formatting. Insert new tasks by inserting new rows.
Guide for Screen Readers
There are 2 worksheets in this workbook. TimeSheet About The instructions for each worksheet are in the A column starting in cell A1 of each worksheet. They are written with hidden text. Each step guides you through the information in that row. Each subsequent step continues in cell A2, A3, and so on, unless otherwise explicitly directed. For example, instruction text might say "continue to cell A6" for the next step. This hidden text will not print. To remove these instructions from the worksheet, simply delete column A.
Additional Help
Click on the link below to visit vertex42.com and learn more about how to use this template, such as how to calculate days and work days, create task dependencies, change the colors of the bars, add a scroll bar to make it easier to change the display week, extend the date range displayed in the chart, etc.
How to Use the Simple Gantt Chart
More Project Management Templates
Visit Vertex42.com to download other project management templates, including different types of project schedules, Gantt charts, tasks lists, etc.
Project Management Templates
About Vertex42
Vertex42.com provides over 300 professionally designed spreadsheet templates for business, home, and education - most of which are free to download. Their collection includes a variety of calendars, planners, and schedules as well as personal finance spreadsheets for budgeting, debt reduction, and loan amortization.
Businesses will find invoices, time sheets, inventory trackers, financial statements, and project planning templates. Teachers and students will find resources such as class schedules, grade books, and attendance sheets. Organize your family life with meal planners, checklists, and exercise logs. Each template is thoroughly researched, refined, and improved over time through feedback from thousands of users.