## Sheet1
Currently Manufactured | [5 empty] | 66% Build | [5 empty] | 100% Build
Manufactured Item | Picture | Components | Manufacture Steps | Time Spent on Step (hours) | Percent Work of Project | Manufactured Item | Picture | Components | Manufacturing Steps | Time Spent on Step (hours) | Percent Work on Project | Manufactured Item | Picture | Components | Manufacturing Steps | Time Spent on Step (hours) | Percent Work on Project
Test Box (80%) |  | 2x4 inch beams | Cut plywood | 1 | 2.123% | Chiller (50%) |  | Refrigerator | Purchase the refrigerator | 1 | 2.123% | Test Box Data Collected (to be compared to theoretical model) |  | Thermocouples | Reconnect all the pieces of the test box | 0.5 | 1.062%
|  | Plywood | Cut 2x4 in beams | 1 | 2.123% |  |  | Pump | Wire vinyl tubes through chiller system | 4 | 8.493% |  |  | Pico DataLogger | Insert the TES device into the test box | 1 | 2.123%
|  | Insulation | Connect plywood to beams | 5 | 10.62% |  |  | Glycol | Add the pump | 2 | 4.246% |  |  |  | Record temperatures in the text box as TES discharges | 5 | 10.62%
|  | Hot glue | Glue insulation onto sides | 0.5 | 1.062% |  |  | Vinyl tubes |  |  | 0% |  |  |  | Complete theoretical calculations | 2 | 4.246%
|  | Glue spray |  |  | 0% | Test Box (100% built) |  | Built test box sides | Connect walls to each other | 2 | 4.246% |  |  |  | Compare theoretical numbers to experimental | 1 | 2.123%
|  | Screws |  |  | 0% |  |  | Thermocouples | Order Pico data logger | 0.1 | 0.2123% | Water bars |  |  | Reiterate water bar based on test box results | 1 | 2.123%
Concrete Block (75%) |  | Concrete | Construct the wooden container | 4 | 8.493% |  |  | Pico data logger | Begin testing process | 5 | 10.62% | Concrete block |  |  | Reiterate concreate block based on test box results | 1 | 2.123%
|  | Water | Add the copper wire to the center | 0.5 | 1.062% |  |  | Bolts |  |  | 0% |  |  |  | Total | 11.5 | 24.42%
|  | 2x4 in beams | Pour concrete | 0.5 | 1.062% |  |  | Knuts |  |  | 0% |  |  |  | Percent Completed |  | 100%
|  | Copper wire | Hit out the bubbles | 3 | 6.369% | Water Bars (80%) |  | New PEX caps | Repeat steps from first iteration but with new caps | 1 | 2.123%
|  |  | Remove from wooden container | 0.1 | 0.2123% |  |  | PEX pipe | Connect the chiller to the water bar | 2 | 4.246%
Water bars (50%) |  | PEX pipes | Apply cap to one end of PEX pipe | 0.3 | 0.6369% |  |  | Copper tubing |  |  | 0%
|  | Water | Insert the copper pipe through the one PEX pipe | 0.1 | 0.2123% |  |  | Glue |  |  | 0%
|  | Copper wire | Use glue to seal one end | 0.1 | 0.2123% | Concrete Block (100%) |  | Previously made concrete block | Connect the chiller to the contrete box | 2 | 4.246%
|  | PEX caps | Add water to the inside of the PEX pipe | 0.1 | 0.2123% |  |  | Vinyl tubes |  |  | 0%
|  | Glue | Add cap to the other end | 0.2 | 0.4246% |  |  |  | Total | 19.1 | 40.55%
|  |  | Glue the other end | 0.1 | 0.2123% |  |  |  | Percent Completed |  | 75.58%
|  |  | Total | 16.5 | 35.03%
|  |  | Cumulative Project Total Time (hr) | 47.1