## Project schedule
| SRP Thermal Mass | [5 empty] | Project start: | [7 empty] | 2024-08-01
| SRP | Project lead |  |  |  |  | Display week: | [7 empty] | 5
SIMPLE GANTT CHART by Vertex42.com
| https://www.vertex42.com/ExcelTemplates/simple-gantt-chart.html | [5 empty] | 2024-08-26 | [6 empty] | 2024-09-02 | [6 empty] | 2024-09-09 | [6 empty] | 2024-09-16 | [6 empty] | 2024-09-23 | [6 empty] | 2024-09-30 | [6 empty] | 2024-10-07 | [6 empty] | 2024-10-14
| TASK | ASSIGNED TO | PROGRESS | START | END | time axis 2024-08-26 to 2024-10-20
 | time axis 2024-08-26 to 2024-10-20
Initial Tasks
Initial tasks | Update Gantt chart | Courtney | 100% | 2024-08-01 | 2024-08-26 | 26
| Submit Purchase Request | Maciej | 100% | 2024-08-26 | 2024-09-05
| Assign parts | Courtney | 100% | 2024-08-26 | 2024-09-05 | 11
| Project Management Assignment |  |  |  | 2024-08-31
Updates from last semester | Update Header Information | Janelle | 100% | 2024-08-26 | 2024-08-31 | 6
| Update Gantt Chart | Courtney | 100% | 2024-08-26 | 2024-08-31
| Update design efforts for what was completed over summer | Steven | 100% | 2024-08-26 | 2024-08-31 | 6
| Update purchasing plan | Maciej | 100% | 2024-08-26 | 2024-08-31
| Update manufacturing plan | Aaron | 100% | 2024-08-26 | 2024-08-31 | 6
| Submit assignment | Courtney | 100% | 2024-08-31 | 2024-08-31
| Engineering Calculations Assignment |  |  |  | 2024-09-07
Top Level Design Summary | State problem you're trying to solve/solution | Maciej | 100% | 2024-08-31 | 2024-09-07 | 8
| Show image of top-level CAD/engineering drawings | Aaron | 100% | 2024-08-31 | 2024-09-07 | 8
| Describe sub systems | Aaron | 100% | 2024-08-31 | 2024-09-07 | 8
| Show updated QFD | Janelle | 100% | 2024-08-31 | 2024-09-07 | 8
Summary of Codes and Regulations | Summarize codes and regulations that apply to your design space | Maciej/Steven | 100% | 2024-08-31 | 2024-09-07 | 8
Summary of Equations and Solutions | Cooling Load/Mass of Materials Needed | Courtney | 100% | 2024-08-31 | 2024-09-07 | 8
| Summarize conditions that led to your 'load cases' | Courtney | 100% | 2024-08-31 | 2024-09-07
| NPV | Maciej | 100% | 2024-08-31 | 2024-09-07 | 8
| Resistive Network | Janelle | 100% | 2024-08-31 | 2024-09-07
| Thermo Control Volume deltaT(mdot) air | Steven | 100% | 2024-08-31 | 2024-09-07
| Lumped capacitance method (dT) | Aaron | 100% | 2024-08-31 | 2024-09-07
| External convective heat coefficent (hbar) | Steven | 100% | 2024-08-31 | 2024-09-07
Flow Charts and Diagrams | Functional Decomposition | Courtney | 100% | 2024-08-31 | 2024-09-07
Moving Forward | Write Conclusion | Janelle | 100% | 2024-08-31 | 2024-09-07
| Format Document | Aaron | 100% | 2024-08-31 | 2024-09-07
| Hardware Status Update - 33% build |  |  |  | 2024-09-25
Purchasing Plan | Bill of Materials | Maciej | 100% | 2024-08-27 | 2024-09-25
| Submit purchasing request to get ready for 67% build | Maciej | 100% | 2024-08-27 | 2024-09-25
| Top level Budget | Maciej | 100% | 2024-08-27 | 2024-09-25
| QFD Calcs- COST | Maciej | 100% | 2024-08-27 | 2024-09-25
| QFD Calcs - NPV | Maciej | 100% | 2024-08-27 | 2024-09-25
Design Efforts | QFD Calcs-SAFETY | Steven | 100% | 2024-08-27 | 2024-09-25
| Tap the AC unit vapor compression cycle | Steven | 100% | 2024-08-27 | 2024-09-25
| Build the TES test Box | everyone | 100% | 2024-08-27 | 2024-09-25
| QFD Calcs-NPV | Maciej | 100% | 2024-08-27 | 2024-09-25
| Factor of Safety | Steven | 100% | 2024-08-27 | 2024-09-25
| QFD Calcs-MAINTENANCE | Steven | 100% | 2024-08-27 | 2024-09-25
| QFD Calcs-WEIGHT | Aaron | 100% | 2024-08-27 | 2024-09-25
| QFD Calcs-LATENT HEAT | Courtney | 100% | 2024-08-27 | 2024-09-25
| QFD Calcs-SENSIBLE HEAT | Courtney | 100% | 2024-08-27 | 2024-09-25
| Lay concrete with water | Maciej, Steven, Aaron | 100% | 2024-08-27 | 2024-09-25
| Build water/TES | Janelle, Courtney, Aaron | 100% | 2024-08-27 | 2024-09-25
| CAD | Steven/Aaron | 100% | 2024-08-27 | 2024-09-25
| Plan for chiller | Steven/Willy | 100% | 2024-08-27 | 2024-09-25
Manufacturing Plan | Write out manufacturing plan | Courtney | 100% | 2024-08-27 | 2024-09-25
Demonstration | Bring hardware to class to demonstrate functionality | everyone | 100% | 2024-08-27 | 2024-09-25
| PowerPoint Presentation | Janelle | 100% | 2024-08-27 | 2024-09-25
Gantt Chart Update | Update Gantt Chart | Courtney | 100% | 2024-08-27 | 2024-09-25
| Website Check #1 |  |  |  | 2024-10-11
Website | Update Pictures | Courtney | 100% | 2024-09-15 | 2024-10-11 | 27
| Add Resumes | Courtney | 100% | 2024-09-15 | 2024-10-11
| Update LinkedIn | Courtney | 100% | 2024-09-15 | 2024-10-11
| Update Pages | Courtney | 100% | 2024-09-15 | 2024-10-11 | 27
| Hardware Status Update - 67% build |  |  |  | 2024-10-16
Purchasing Plan | Bill of Materials | Maciej | 100% | 2024-09-25 | 2024-10-16 | 22
| Submit purchasing request to get ready for 100% build | Maciej | 100% | 2024-09-25 | 2024-10-16
| Top level Budget | Maciej | 100% | 2024-09-25 | 2024-10-16
| QFD Calcs- NPV | Maciej | 100% | 2024-09-25 | 2024-10-16 | 22
Design Efforts | Make CAD ready for presentation | Aaron/Steven | 100% | 2024-09-25 | 2024-10-16 | 22
| Purchase refrigerator for chiller | Maciej | 100% | 2024-09-25 | 2024-10-16
| Wire vinyl tubes through chiller system | everyone | 100% | 2024-09-25 | 2024-10-16
| Add the pump to the chiller | everyone | 100% | 2024-09-25 | 2024-10-16
| Connect the walls to each other (test box) | everyone | 100% | 2024-09-25 | 2024-10-16
| Order Pico data logger | Maciej | 100% | 2024-09-25 | 2024-10-16
| Create new iteration of water bar | everyone | 100% | 2024-09-25 | 2024-10-16
| connect chiller to water bar | everyone | 100% | 2024-09-25 | 2024-10-16
| Connect chiller to the concrete box | everyone | 100% | 2024-09-25 | 2024-10-16
| Take pictures of design for presentation | everyone | 100% | 2024-09-25 | 2024-10-16 | 22
| Update calculations | Janelle/Steven | 100% | 2024-09-25 | 2024-10-16 | 22
Manufacturing Plan | Write what has already been manufactured | Courtney | 100% | 2024-09-25 | 2024-10-16 | 22
| Write what needs to still be manufactured | Courtney | 100% | 2024-09-25 | 2024-10-16 | 22
Demonstration | Bring hardware to class | Maciej | 100% | 2024-09-25 | 2024-10-16 | 22
| Prepare Old Man Jokes | Maciej, Janelle, Courtney, Aaron | 100% | 2024-09-25 | 2024-10-16
| PowerPoint Presentation | Janelle | 100% | 2024-09-25 | 2024-10-16 | 22
Gantt Chart Update | Update Gantt Chart | Courtney | 100% | 2024-10-12 | 2024-10-16 | 5
| Ugrad Efest Registration |  |  |  | 2024-10-24
Registration | Registration | Janelle | 100% | 2024-10-16 | 2024-10-24 | 9
| Abstract | Janelle | 100% | 2024-10-16 | 2024-10-24 | 9
| Paragraph | Janelle | 100% | 2024-10-16 | 2024-10-24 | 9
| Draft of Poster |  |  |  | 2024-10-31
Poster Contents | Abstract | Janelle | 100% | 2024-10-01 | 2024-10-31 | 31
| Engineering and Customer Requirements | Janelle | 100% | 2024-10-01 | 2024-10-31
| Methods | Aaron/Maciej | 100% | 2024-10-01 | 2024-10-31
| Results and Conclusions | Aaron/Maciej | 100% | 2024-10-01 | 2024-10-31
| Pictures | Aaron/Maciej | 100% | 2024-10-16 | 2024-10-31 | 16
Submit | Submit | Aaron/Maciej | 100% | 2024-10-29 | 2024-10-31 | 3
| Finalized Teseting Plan |  |  |  | 2024-11-01
Design Requirements Summary | Engineering and Cusstomer Requirements (talk to Dr. Acker about what he wants for this) | Janelle | 100% | 2024-10-20 | 2024-11-01 | 13
Top Level Testing Summary | List tests you will be performing in a table | Courtney | 100% | 2024-10-20 | 2024-11-01 | 13
Detailed Testing Plans | Test/Experiments summary | Steven | 100% | 2024-10-20 | 2024-11-01 | 13
| Add steps to Gantt Chart | Courtney | 100% | 2024-10-25 | 2024-11-01
| Procedure | Courtney | 100% | 2024-10-20 | 2024-11-01 | 13
| Results | Janelle | 100% | 2024-10-20 | 2024-11-01 | 13
| Conclusion | Steven | 100% | 2024-10-20 | 2024-11-01 | 13
Specification Sheet Preparation | Customer Requirement Table Met/not met | Janelle | 100% | 2024-10-20 | 2024-11-01
| Engineering Requirements table met/not met | Janelle | 100% | 2024-10-20 | 2024-11-01
QFD | QFD Calcs- COST | Maciej | 100% | 2024-10-20 | 2024-11-01
| QFD Calcs - NPV | Maciej | 100% | 2024-10-20 | 2024-11-01
| QFD Calcs-MAINTENANCE | Steven | 100% | 2024-10-20 | 2024-11-01
| QFD Calcs-SAFETY | Steven | 100% | 2024-10-20 | 2024-11-01
| QFD Calcs-THERMAL EFFICIENCY | Steven | 100% | 2024-10-20 | 2024-11-01
| Hardware Status Update 100% build |  |  |  | 2024-11-07
Design Efforts | CAD | Aaron | 100% | 2024-10-16 | 2024-11-07 | 23
| Update engineering calculations | everyone | 100% | 2024-10-16 | 2024-11-07
Purchasing Plan | Bill of Materials | Maciej | 100% | 2024-10-16 | 2024-11-07 | 23
| Submit purchasing request to get ready for 100% build | Maciej | 100% | 2024-10-16 | 2024-11-07
| Top level Budget | Maciej | 100% | 2024-10-16 | 2024-11-07
| QFD Calcs- NPV | Maciej | 100% | 2024-10-16 | 2024-11-07 | 23
Manufacturing Plan | Take images of design | Courtney/Steven | 100% | 2024-10-16 | 2024-11-07 | 23
| Finalize manufacturing plan | Courtney | 100% | 2024-10-16 | 2024-11-07 | 23
Demonstration | PowerPoint Presentation | Janelle | 100% | 2024-10-16 | 2024-11-07 | 23
| Bring final demonstration system to class | Maciej/Aaron | 100% | 2024-10-16 | 2024-11-07
Gantt Chart | Gantt Chart Update | Courtney | 100% | 2024-10-16 | 2024-11-07 | 23
| Final Poster and Powerpoint |  |  |  | 2024-11-14
Poster | Update Abstract | Maciej | 100% | 2024-11-01 | 2024-11-14 | 14
| Update pictures | Maciej | 100% | 2024-11-01 | 2024-11-14
| Update engineering and customer requirements | Maciej | 100% | 2024-11-01 | 2024-11-14
| Update methods | Courtney | 100% | 2024-11-01 | 2024-11-14
| Update results and conclusion | Courtney | 100% | 2024-11-01 | 2024-11-14
Powerpoint | Background | Steven | 100% | 2024-11-01 | 2024-11-14
| Customer and engineering requirements/QFD | Janelle | 100% | 2024-11-01 | 2024-11-14
| Benchmarking | Janelle | 100% | 2024-11-01 | 2024-11-14
| Literature review | everyone | 100% | 2024-11-01 | 2024-11-14
| Mathematical modeling | everyone | 100% | 2024-11-01 | 2024-11-14
| Functional Decomposition chart | Courtney | 100% | 2024-11-01 | 2024-11-14
| Insert concept generation | Courtney/Steven | 100% | 2024-11-01 | 2024-11-14
| Selection criteria | Janelle | 100% | 2024-11-01 | 2024-11-14
| Concept selection | Janelle | 100% | 2024-11-01 | 2024-11-14
| Factor of Safety | Steven | 100% | 2024-11-01 | 2024-11-14
| Schedule/Gantt Chart | Courtney | 100% | 2024-11-01 | 2024-11-14
| Budget | Maciej | 100% | 2024-11-01 | 2024-11-14
| Bill of Materials | Maciej | 100% | 2024-11-01 | 2024-11-14
| FMEA | Steven | 100% | 2024-11-01 | 2024-11-14
| Final hardware | Steven | 100% | 2024-11-01 | 2024-11-14
| Future Work | Courtney | 100% | 2024-11-01 | 2024-11-14 | 14
| Initial Testing Results |  |  |  | 2024-11-21
Design Requiremetns Summary | Sumarize design requirements | Janelle | 100% | 2024-11-01 | 2024-11-21 | 21
| Engineering and customer requiremetns update | Janelle | 100% | 2024-11-01 | 2024-11-21
Top level testing summary | Make table of tests being performed | Courtney | 100% | 2024-11-01 | 2024-11-21
Detailed Testing Plans | Test/experiment summary | Steven | 100% | 2024-11-01 | 2024-11-21
| Procedure | Courtney | 100% | 2024-11-01 | 2024-11-21
| Results | Janelle | 100% | 2024-11-01 | 2024-11-21
Specification Sheet Preparation | Summarize results table | Steven | 100% | 2024-11-01 | 2024-11-21
| Make table if requirements were met or not | Janelle | 100% | 2024-11-01 | 2024-11-21
QFD | QFD | Janelle | 100% | 2024-11-01 | 2024-11-21
| Final CAD packet |  |  |  | 2024-11-22
CAD Requirements | Create PDF of final CAD packet | Aaron | 100% | 2024-11-01 | 2024-11-22 | 22
| Bill of Materials | Maciej | 100% | 2024-11-01 | 2024-11-22 | 22
| Check that drawings adhere to ASME GD&T standards | Aaron | 100% | 2024-11-01 | 2024-11-22
| Compile info needed to manufacutre and build design | Steven | 100% | 2024-11-01 | 2024-11-22
| Create zip file | Aaron | 100% | 2024-11-01 | 2024-11-22
| Final Testing Results |  |  |  | 2024-11-27
Design Requiremetns Summary | Copy paste enginering and customer requirements from previous assignment | Janelle | 100% | 2024-11-01 | 2024-11-27 | 27
Top Level Testing Summary | Update table of experiments/tests and results | Courtney | 100% | 2024-11-01 | 2024-11-27
Detailed Testing Plans | Update test/experiment summary | Steven | 100% | 2024-11-01 | 2024-11-27
| Procedure | Courtney | 100% | 2024-11-01 | 2024-11-27
| Results | Janelle | 100% | 2024-11-01 | 2024-11-27
Specification Sheet | Finalize tables for customer and engineering requirements | Janelle | 100% | 2024-11-01 | 2024-11-27
QFD | QFD | Janelle | 100% | 2024-11-01 | 2024-11-27
| Final Report |  |  |  | 2024-12-03
Report Sections | Background | Janelle | 100% | 2024-11-01 | 2024-12-03 | 33
| Requirements | Janelle | 100% | 2024-11-01 | 2024-12-03
| Design Space Research | everyone | 100% | 2024-11-01 | 2024-12-03
| Concept Generation and Design Selected | Janelle | 100% | 2024-11-01 | 2024-12-03
| Project Management | Janelle | 100% | 2024-11-01 | 2024-12-03
| Final Hardware | Steven | 100% | 2024-11-01 | 2024-12-03
| Testing | Courtney/Steven/Janelle | 100% | 2024-11-01 | 2024-12-03
| Risk Analysis and Mitigation | Steven | 100% | 2024-11-01 | 2024-12-03
| Looking Forward | Janelle | 100% | 2024-11-01 | 2024-12-03
| Conclusion | Janelle | 100% | 2024-11-01 | 2024-12-03
Final Formatting | Check Formatting | Janelle | 100% | 2024-11-01 | 2024-12-03
| Final Website Check |  |  |  | 2024-12-04
Website Requirements | Team short intro video | Courtney | 100% | 2024-11-24 | 2024-12-04 | 11
| Include pictures/action shots | Courtney | 100% | 2024-11-24 | 2024-12-04
| Email Brian Hanabury for advertising | Courtney | 100% | 2024-11-24 | 2024-12-04
| Make LinkedIn post | Courtney | 100% | 2024-11-24 | 2024-12-04 | 11
| Website is live | Courtney | 100% | 2024-11-24 | 2024-12-04
| Final Project Demo |  |  |  | 2024-12-05
Product Demonstration | Plan demonstration for class | everyone | 50% | 2024-11-25 | 2024-12-05 | 11
| Operation/Assembly Manual |  |  |  | 2024-12-05
Manual Requirements | Assembly | Aaron | 0% | 2024-11-05 | 2024-12-05 | 31
| Disassembly | Steven | 0% | 2024-11-05 | 2024-12-05
| Operation | Courtney | 0% | 2024-11-05 | 2024-12-05
| Maintenance Instructions | Janelle | 0% | 2024-11-05 | 2024-12-05
| A troubleshooting section for potential failures | Steven | 0% | 2024-11-05 | 2024-12-05
| Expo PPT and Poster Presentation Delivery Results |  |  |  | 2024-12-06
Insert new rows ABOVE this one
Formulas:
Display week: = [Display week:, row below]

## About
SIMPLE GANTT CHART by Vertex42.com
About This Template
This template provides a simple way to create a Gantt chart to help visualize and track your project. Simply enter your tasks and start and end dates - no formulas required. The bars in the Gantt chart represent the duration of the task and are displayed using conditional formatting. Insert new tasks by inserting new rows.
Guide for Screen Readers
There are 2 worksheets in this workbook. TimeSheet About The instructions for each worksheet are in the A column starting in cell A1 of each worksheet. They are written with hidden text. Each step guides you through the information in that row. Each subsequent step continues in cell A2, A3, and so on, unless otherwise explicitly directed. For example, instruction text might say "continue to cell A6" for the next step. This hidden text will not print. To remove these instructions from the worksheet, simply delete column A.
Additional Help
Click on the link below to visit vertex42.com and learn more about how to use this template, such as how to calculate days and work days, create task dependencies, change the colors of the bars, add a scroll bar to make it easier to change the display week, extend the date range displayed in the chart, etc.
How to Use the Simple Gantt Chart
More Project Management Templates
Visit Vertex42.com to download other project management templates, including different types of project schedules, Gantt charts, tasks lists, etc.
Project Management Templates
About Vertex42
Vertex42.com provides over 300 professionally designed spreadsheet templates for business, home, and education - most of which are free to download. Their collection includes a variety of calendars, planners, and schedules as well as personal finance spreadsheets for budgeting, debt reduction, and loan amortization.
Businesses will find invoices, time sheets, inventory trackers, financial statements, and project planning templates. Teachers and students will find resources such as class schedules, grade books, and attendance sheets. Organize your family life with meal planners, checklists, and exercise logs. Each template is thoroughly researched, refined, and improved over time through feedback from thousands of users.